## Slide 1: North Africa & West Asia region Review of on-going activities and future prospects Ali Nefzaoui CRP-DS NA & WA Region Coordinator
CRP-DS Science and Implementation Workshop
30th June – 4th July, 2014
Holiday Inn Hotel - Amman, Jordan

## Slide 2: Outline
NA&WA FS challenges & opportunities
Goals to achieve through CRP-DS
NA&WA FS action & satellite sites
Major Agricultural livelihoods (ALSs)
Research hypotheses
Working scale
Collaboration & partnership
Highlight on major achievements
Capacity development
Recommendations

## Slide 3: NA&WA FS Challenges to Overcome
In low potential areas (SRT2), aquifer degradation both in terms of level and quality.
High temporal variation in precipitation with annual variation between 23 and 60% with precipitation occurring almost entirely in the winter. This variability, along with climate change projections that predict a reduction in precipitation by 10-30% by the end of the century, pose severe challenges to rainfed cropping.
Poor households, often utilizing less than one hectare of land (10-40 %)
Due to unavailability of credit, on poor rainfall years when stock losses are heavy, most households are not able to immediately restock their flocks and herds.
In both favorable and marginal areas there is a distinct rejection of pastoral activity by the younger generation that is leading to out migration.
A lack of skilled agricultural and pastoral labor could become a serious problem in the agricultural sector.

## Slide 4: NA&WA FS Opportunities
Highly mechanized agricultural systems exist within the SRT 2 area. In the SRT2 area there is also a strong preexisting network of traders for high value items like dairy products, sheep, and fruit. A complex relationship between middlemen and on farm producers.
The growing period in the SRT3 areas of North Africa are quite long ranging between 200 to 240 days. Because of favorable temperature regimes across most of the site it provides excellent conditions for growing a diverse range of climatically adapted crops.
Most of the soils in favorable areas are good agricultural soils and are already under cultivation. This makes the potential for substantial short to medium term production gains more likely.
Moderate to high access to improved varieties
SRT 3 areas are well enough connected to the EU market.
A great number of potential R4D and development partners are already at work in this region creating opportunities for synergy.

## Slide 5: What we want to achieve in NA&WA Flagship through the CRP-DS?
to reduce vulnerability to system shocks and climate change in dry resource poor areas with poor institutions and poor market connectedness,
to sustainably intensify production in less marginal areas which tend to have better institutional support and access to markets
The goal is ‘sustainable intensification’ and investment for long-term food security

## Slide 6
CGIAR Research Program on Dryland Agricultural Production Systems – Launch Meeting, Amman 21-23 May 2013
NA&WA Flagship Sites
High potential areas
Low potential areas

## Slide 7
Sites characterization
Biophysical descriptors
Climate
Topography
Soils)
Water resources
Land use/land cover
Land degradation
Socio-economic descriptors
Demography
Agricultural systems
Governance, institutions, policies
Opportunities for agricultural research
NA&WA Flagship Sites

## Slide 8: Major Agricultural Livelihood Systems in NA&WA
ALS | Brief description | Major constraints | Sites
Agropastoral Systems | Agricultural livelihood based on small ruminants, barley crop, small scale irrigation | Overgrazing, feed imbalances, land degradation, water scarcity, climate variability, conflicts over resources, youth unemployment | Tafilah-Salamya, Beni Khedache-Sidi Bouzid, Karkheh River Basin
Intensive rainfed Systems | Wheat-based cropping system, land fragmentation, horticulture is intensifiable and market-oriented including for export, intensive dairy cattle production | Land degradation, nutrient deficiencies, water scarcity, climate variability, youth unemploymeent | Meknes-Saies, Karkheh River Basin

## Slide 9: Major Agricultural Livelihood Systems in NA&WA
ALS | Brief description | Major constraints | Sites
Tree-based Systems | Mixed tree-crop-livestock, variant of agropastoral (Jordan & Tunisia: olive-figs - almonds-barley - sheep) & intensive rainfed; rainfed (Meknes: wheat-fruit trees-dairy cattle) | Fast degradation of natural resources, overgrazing, land degradation, climate variability, youth unemployment | Tafilah-Salamya, Beni Khedache-Sidi Bouzid, Meknes-Saies
Irrigated Crop Systems | Market-oriented vegetable and fruit; high yielding wheat and forage crops, dairy cattle. | Land constrained by groundwater depletion, salinization, heat stress, youth unemployment | Nile Delta

## Slide 10: Hypotheses for the NA & WA Flagship
The use of innovation platform (IP) will help halt land degradation and restore ecosystems and improve livelihoods
Rangeland production systems can be made less risky and more resilient by integrated technical, institutional and policy innovations that aim at rangeland rehabilitation and sustainable management
Irrigated production systems can be sustainably intensified through policies and institutions that ensure efficient use of land and water resources.
Use of innovation systems approach will enhance the adoption and utilization of improved technologies, markets and policies
System analysis of production and market system performance will allow optimal intensification of the production and market systems and the assessment of potential impact of innovations both in socio-economic and ecological terms.

## Slide 11: Hypotheses for the NA & WA Flagship
Some form of farm aggregation (association/ organized farmers groups) will lead to the realization of economies of size, thereby leading to increased access to innovations, improved market efficiencies, competitiveness and value addition
Rainfed wheat-based system can be sustainably intensified and diversified through crop-tree-livestock integration, agricultural innovations, and institutional arrangements providing pathways out of poverty
Equitable distribution of responsibilities and benefits along the value chain among men, women and youth will enhance development of the target areas;
Achieving gender equality will greatly contribute to the elimination of hunger and poverty through achieving equality between women and men in sustainable agricultural production and rural development efforts.

## Slide 12: The working scale…
 | Meknes, Morocco | BK – SB, Tunisia | Tafilah-Salamya, Jordan/ Syria | Nile Delta, Egypt | Karkhe River Basin, Iran
Area, km2 | 1,694 | 17,920 | 36,600 | 39,300 | 50,000
Population, million | 0.714 | 1.527 | 8.3 | 36.49 | 3.6
% Rural | 20 | 41 | 60-70 | 60 | 38

## Slide 13: Collaboration frameworks and partnerships working mechanisms
ICARDA is nearly the only center intervening in NA&WA flagship
ICARDA developed over decades a strong partnership with NARES over NA & WA region
Partners:
  Local partners: NARES, Universities, farmers’ organizations, NGOs, development agencies, Private sector, Decision makers
  Regional & International agencies: ARI (CIRAD), ACIAR, FAO, IFAD, AFESD, EU, GTZ, UNDP, etc.

## Slide 14: Example: Beni Khedache site, Tunisia
Beni Khedache platform (Tunisia)
Government agencies:
Governorate, County, Agriculture (CRDA, OEP, APIA),
Environment,
Development (ODS)
Civil society & non government organizations:
NGOs, GDA,
Socio-professionals (UTAP, UTICA, etc.)
Research /University institutions:
IRA, Techno Park Medenine, IO, UG, etc
Bilateral / multilateral cooperation:
MAU, AU, EU members, Japan, China, USA,
Regional/International agencies: ICARDA, OSS, UNU, UNCCD, UNFCC, UNCB, NATO, FAO, UNESCO, UNDP, IRD, etc.

## Slide 15: Collaboration frameworks and partnerships working mechanisms
For each site a NARES-ICARDA team is established involving both research centers and universities
A MOA of agreement is being signed between ICARDA and NARES
ICARDA regional/country offices are in charge of the daily budget management
For each site an ICARDA focal point and NARES focal point have been nominated
For each activity a leader from ICARDA and a leader from NARES is nominated

## Slide 16: Achievements
Joint research teams established for the five sites in NA&WA region with a total number of 50 scientists from ICARDA and more than 100 scientists from NARS. Planned activities are being implemented at the five sites.
20 technologies/practices are under research in 4 ALSs (pastoral, agropastoral, rainfed, irrigated) over a total area of 38000 ha and where 5260 farmers are collaborating with the program.
25 to 40 % of these technologies/practices have an explicit target of women farmers and this ratio will be increasing in the future.

## Slide 17: CRP-DS revised IDOs
SLOs
IDO1
Resilience
IDO2
Wealth & Wellbeing
IDO3
Food access
IDO4
NRM
IDO5
Gender empowmt
IDO6
Capacity to innovate
More resilient livelihoods for vulnerable HH in marginal areas
More sustainable & higher income & well-being for sustainable HH
Women & children have access to greater quantity & diversity of food
More sustainable & equitable mgt of land, water, energy & biodiversity
Women & youth have better access to and control over resources & market and more equitable share of income & food ..
Increased & sustainable capacity to innovate allowing to seize new opportunities ..

## Slide 18: Phases 2014 (with little variation between ALSs)
Discovery | Proof of concept | Pilot
Policies on natural resources | Water harvesting & soil conservation | Water & land productivity in irrigated & rainfed system
System vulnerability | Managing rangelands | Conservation agriculture
Bio-economic farm models | In situ agro-biodiversity | Livestock productivity
Innovation platforms & scenarios | Seed systems & dissemination | Cereal & legume systems adaptation
High-value chain clusters |  | Cereal & legume system IPM-
Post- harvest & market access |  | 
Gender in Drylands |  | 
Aggregation for smallholder |  | 
Managing salinity |  | 

## Slide 19: Highlights of major achievements

## Slide 20: IDO 1/ resilience – Analysis of systems vulnerability
Objective: Determine the causes of system vulnerability and local coping mechanisms
Achievement:
  On-going establishment of a baseline data by characterizing the communities in the target sites;
  A questionnaire was prepared and developed for baseline surveys in the target sites of CRP1-1.
  Secondary data were collected, and rapid rural appraisal (RRA) was completed in Morocco and a draft report on “System vulnerability and production system dynamics in the Sais region of Morocco” was prepared.
Phase:
  Discovery

## Slide 21: IDO1, IDO2, and IDO4 – Conservation Agriculture
Objective: To adapt conservation agriculture for rapid adoption by smallholders in the context of produce more food/feed with less resources and inputs
Outcome: To generate and customise improved resilience options for vulnerable households
Phase: Pilot/Outscaling

## Slide 22: IDO1, IDO2, and IDO4 – Conservation Agriculture
Achievements
Conservation agriculture (CA) practices continued to expand to over 39,000 ha for nearly 5080 farmers in NA&WA (Jordan, Syria, Tunisia, Morocco, Iraq).
The key driving force for this expansion is the conception and production of locally-made low cost zero till seeders in partnership with the private sector.
Two projects funded by ACIAR are having considerable success in promoting conservation agriculture in Iraq and Syria (west Asia) and Algeria, Morocco and Tunisia (North Africa).
Results showed an increased cereal yields by 15-19% and net income by 29%.
In Iraq, the total area under conservation agriculture reached in 2012/13 10,800 ha (http://bookshop.cabi.org/?page=2633&pid=2627&site=191), (http://www.icarda.org/tools/conservation-agriculture-yield-lower-cost)

## Slide 23
23
Action Site – Meknes
IDO1/resilience-IDO4/NRM – Conservation Agriculture (Preliminary results)
Chart: 
| Vicia ervilia | Vicia ervilia | Vicia ervilia | Barley (6 row) | Vicia sativa | Barley (2 row)
ZT Biological yield | 2000 | 3833.3333 | 1866.6667 | 2800 | 2750 | 1146.6667
CT Biological yield | 993.3333 | 2666.6667 | 1200 | 2600 | 2283.3333 | 1716.6667
ZT Grain yield | 793.3333 | 926.6667 | 353.3333 | 610 | 973.3333 | 216.6667
CT Grain yield | 343.3333 | 1323.3333 | 533.3333 | 350 | 683.3333 | 463.3333
Demonstration fields
10 farms in El Karaq and 10 farms in Madaba hosted CA combined or not with alley cropping
Wheat and chickpea in Meknes site, Morocco
Wheat grain yield (q/ha)
Chickpea grain yield (q/ha)
Notes: 23

## Slide 24
Capacity Development
Participation in training courses
4 members of CRP DS team (2 from Tunisia and 2 from Jordan) participated in international training workshop on Agro-ecological monitoring held in Amman, April 3-12, 2014.
Traveling workshop
  members of CRP DS from NARS and young scientists from ICARDA participated in the traveling workshop on CA in Algeria, Morocco and Tunisia under the framework of ICIAR CANA project
PARTICIPATION IN THE INTERNATIONAL CONGRESS ON CA (CANADA, JUNE and JULY 2014)
  members of CRP DS from NARS in Tunisia and Morocco and young scientists from ICARDA participated in the International Congress on CA held in Canada on June 2014
  and about food legum under CA in Canada, July 2014
Post-Graduate studies on CA in the action sites
  3 PhD students (2 from Tunisia and 1 from Morocco) are preparing a PhD thesis on CA in the action sites.
IDO1, IDO2, and IDO4 – Conservation Agriculture (capacity development)

## Slide 25: IDO1 Resilience-IDO4/NRM - Livestock
Objective: Boosting Resilience and Productivity of the livestock production systems at the household level through a more sustainable and integrated mobilization of existing resources and innovative perceptions to attenuate the impact of environmental and economic stressors
Phase: Pilot

## Slide 26: IDO1 Resilience-IDO4/NRM - Livestock
Technical platform | Type of activities and quantified target | State of progress as to the 2014-2015
System characterization | Conducting livestock production system charcaterization (100 HH in El-Krak, 200 HH in Sidi Bouzid, 150 HH in Meknes, 50 HH in Chefchaouane) | 30%
Feed resources and feeding system improvement | Updating a feeding survey, highlighting the major factors for nutrient deficiencies and assessing efficiency of water productivity for livestock (30 flocks in Sidi Bouzid, 20 flocks in Jordan, 6 dairy herds in Mekness | 50% for sampling activities
Animal health and diseases | Epidemiological surveys updating dominating animal diseases in Sidi Bouzid and in El-Karak | 20%
 | Prevalence and risk factors of major zoonotic sheep and goats abortive diseases (Toxoplasmosis, Brucellosis, Chlamydiosis) in Jordan and Tunisia (New activity) | 10%
Animal products quality, safety and processing | Sheep and goat milk quality and processing (25 sheep milk and 20 goat milk processors in Jordan and Morocco respectively) | 30% (see next slide)
 | Safety of sheep milk products in Jordan (120 samples of Jameed, Bulk milk samples; linkage with CRP Livestock and Fish) | 30% for sampling activities

## Slide 27
Technical platform | Type of activities and quantified target | State of progress as to the 2014-2015 phase
Sheep genetics (Sidi Bouzid, Tunisia) | Identifying crossing practices and their impact on productivity (identifying fattening and breeding practices; value chain analysis of fattened lambs; mapping spatial distribution of crossing practices) | 53 GPS coordinates and associated data (20%)
 | Identification of genetic markers for productive and adaptive traits (prolificacy, parasite resistance) | Elaboration of an appropriate recording scheme for phenotypic data
Integrated interventions aiming at boosting flock fertility and reducing offspring losses (El-Karak, Jordan) Animal products quality, safety and processing | Ram breeding soundness examination in Eraq and Khrisha villages (86 rams and bucks examined) | Recommendations on ram keeping/culling, Data collected for further analysis and reporting
 | Systematic ultrasound-based pregnancy diagnosis of sheep flocks and alternative measures to reduce bareness | Due at the end of mating season (July-August)
 | Reducing prevalence of neo-natal mortality and addressing risk factors | Due to start before the lambing season (September)
IDO1 Resilience-IDO4/NRM - Livestock

## Slide 28: Enhancing dairy processing skills and market access of rural women and local processors (activity with an important gender dimension)
Expected outcomes
Enhance small ruminant producers productivity and resilience
Create job opportunities, especially for women.
Improve and diversify the family income resources
Morocco
testing of dairy culture for “Lban” production to enhance product quality
Jordan
Developing methods to enhance product quality (Jameed)
Focus on
Product quality
Energy saving
Reduced water consumption
IDO1 Resilience-IDO4/NRM - Livestock

## Slide 29
Short term courses and trainings
  Sheep breeding: data recording, management and valorization (Amman – Jordan 5-7 May 2014)
  Jameed, Butter and ghee processing in 5 women-led processing units (El-karak, jordan April-May and June 2014)
  Technical itineraries to improve fertility in sheep and goat breeds (El-Karak – jordan April 2014)
  Goat milk processing and impact of new fermenting cultures (Chefchaouane-morocco June 2014)
long term DEGREE trainings
  4 PhD in tunisia: crossing and fattening practices; genetic markers for productive and adaptive traits; water productivity by sheep and goats; etiology of small ruminants abortive diseases
  1 Master in Morocco on water productivity for Dual purpose milk and meat cattle production
IDO1 Resilience-IDO4/NRM – Livestock/ Capacity development

## Slide 30: IDO1/Resilience-IDO4/NRM Rangeland management
Objective: Enhancing resilience and productivity of the pastoral and agro-pastoral production systems at the community level through a more sustainable and integrated mobilization of existing resources and innovative perceptions to attenuate the impact of environmental and economic stressors.
Phase: Proof of concept

## Slide 31
Developing non-destructive techniques for estimating rangeland vegetation productivity
Tunisia
Jordan
Rehabilitating salt affected rangelands (Sebkha)
Enhancing the use of cactus to promote livelihood of agro-pastoralists
Evaluating integrated alley cropping and conservation agriculture in pastoral landscape depressions
Rehabilitating degraded rangelands
Rangeland restoration of degraded mountainous areas through water harvesting techniques, rest and direct seeding of Periploca angustifolia and Retama raetam.
IDO1/Resilience-IDO4/NRM Rangeland management

## Slide 32
Short-term courses and trainings:
JICA Training on New techniques for sustainable sheep and goat production held in Jordan (26 January – 6 February 2014)
Group training on Agro-ecological monitoring held in Jordan (Lead by Mounir)
Group training on Agro-forestry practices (Alley-cropping) held in Jordan
Seminar on best practices of Cactus in Eraq (Lead by Paolo – 17 April 2014)
Field day to promote cactus in Eraq site (Lead by Hichem - 28 April – 2014)
Field day on grazing management in Majdya site (Lead by Abu Zanat – 27 May 2014)
Field day Zammour (Lead by IRA)
Long-term courses:
1 PhD student on cactus (University of Palermo, Italy)
1 PhD student on integration of alley cropping and CA (INAT, Tunisia)
1 MSc on cactus genetic variation (UNIVERSIDADE FEDERAL RURAL DE PERNAMBUCO Brazil)
1 MSc on halophytes (University of Science de Sfax, Tunisia)
1 MSc on halophytes eco-physiology (University of Copenhagen, Denmark)
IDO1/Resilience-IDO4/NRM Rangeland management

## Slide 33: IDO1 Resilience-IDO4/NRM - Agrobiodiversity
Objectives:
Assess the status and trends of agrobiodiversity in selected sites using eco-geographic/botanic surveys
Use of GIS/RS tools to assess the changes in agrobiodiversity
Develop and recommend management plans to promote in-situ conservation of dryland Agrobiodiversity in the selected areas

## Slide 34: IDO1/Resilience-IDO4/NRM - Agrobiodiversity
Cultivation of local and exotic medicinal and aromatic/herbal plants as a source of income to support the in situ conservation and sustainable use of Dryland Agrobiodiversity [Erak site, Crocus sativus, Thymus spp, Salvia spp, cut herbs (Rocca, Basil, Thyme, etc..)]
Workshop on MAPS:
  Development of concept note of the regional strategy for conservation and use of MHAP.
  Draft ideas to implement sub-regional projects on establishing value chain on MHAPs
  Develop a list of mechanisms for collaboration in research for utilization of MHAP genetic resources at NA&WA region (Regional network for promoting the conservation and sustainable use of MHAP in NENA region)
Assess and monitor Agrobiodiversity and its trends using ecogeographic/botanical surveys (Transects and quadrats methods for natural habitats) and farming system surveys in Jordan and Tunisia sites

## Slide 35: IDO2/Wealth & wellbeing – Cereal & Legume system adaptation
Test and validate with farmers the performance of advanced breeding lines of cereals and food legumes for improved tolerance to abiotic and biotic stresses in wheat-grain legume cropping system in Meknes and Nile Delta
Release farmer’s preferred varieties among wheat and food legumes elite advanced lines to fit better the users requirements and to facilitate their adoption

## Slide 36
Meknès-Sais site (Intensive rainfed)
2 on-farms demonstration trials of advanced lines : Sebt Jehjouh and Sidi Sliman were implemented for participatory evaluation
Sebt Jehjouh
Lentil: 13 advanced lines + 2 checks
Chickpea: 7 advanced lines + 2 checks
Faba bean: 11 advanced lines + 2 checks
Durum wheat: 16 advanced lines + 4 checks
Bread wheat: 10 advanced lines + 2 checks
Sidi Slimane
Chickpea: 7 advance d lines + 3 checks
Faba bean: 11 advanced lines + 2 checks
Durum wheat: 16 advanced lines + 4 checks
Bread wheat: 10 advanced lines + 2 checks
  Sidi Slimane: Cereals and Legumes planting
(Sebt Jehjouh: 4 weeks after planting)
Sidi Slimane (14 Feb 2014)

## Slide 37
IDO2/Wealth & wellbeing – Cereal & Legume IPM
Objectives
  On- farm promotion of already available IPM options to increase crop productivity
  Development of new IPM options for the management of emerging biotic constraints for the cereal and food legume systems, and
  Human capacity building
Two ALS: Intensive rainfed (Meknes) and irrigated (Nile Delta)
Phase: Piloting

## Slide 38
In both sites 2013/14 season data are under preparations
In Nile Delta, IPM of parasitic weeds on faba bean gave 22.4% yield advantage
IPM of faba bean virus gave promising results in Egypt
In Meknes sites, IPM of Parasitic weeds on faba bean showed promising results
Weed surveys in the action sites showed Bromus sp. can cause 68% decrease of crop yield in highly infested fields.
Two researchers were trained in plant viruses detection techniques
IDO2/Wealth & wellbeing – Cereal & Legume IPM

## Slide 39
Results (based on disease score), ARC Cairo Station:
Virus infection level was higher in untreated plots (D0) compared to treated plots (D1 and D2).
Seed treatment with Apron Star (ApS) and Celest top (CT) showed significant reduction in virus infection for all genotypes.
Dose 1 (ApS=1.25g/kg; CT=0.75cc/kg) is apparently sufficient to decrease infection
Effect of seed dressing with Celest Top on virus infection of faba bean (Giza 4 and Misr 3) (right) under natural infection in ARC Cairo station as compared to untreated plots (left)
Misr 3 Giza 4
Misr 3 Giza 4
Highlights…
Chart: Egyption Faba bean Varieties
| Giza 4-ApS | promising L6-ApS | Misr 3-ApS
D0 | 4 | 3 | 3
D1 | 1 | 2 | 1
D2 | 1 | 1 | 1
Chart: Egyption Faba Bean Varieties
| Giza 4-CT | promising L6-CT | Misr 3-CT | Nubaria 1-CT
D0 | 4 | 4 | 3 | 3
D1 | 1 | 2 | 1 | 1
D2 | 1 | 1 | 1 | 1
Apron Star (ApS)
Celest top (CT)
Treated with Celest top
Un-treated

## Slide 40
Chart: Egyption Faba bean Varieties
| Giza716-ApS | Giza 3-ApS | Sakha 1-ApS
D0 | 2.3 | 1.5 | 2
D1 | 1.5 | 1 | 2.5
D2 | 1 | 0.5 | 1
D3 | 1.25 | 1 | 1.25
Chart: Egyption Faba bean Varieties
| Giza716-CT | Giza 3-CT | Sakha 1-CT
D0 | 2 | 0.75 | 2
D1 | 1.5 | 0.75 | 1.25
D2 | 1.5 | 0.75 | 1.5
D3 | 1 | 1 | 1.5
Results of Gemmiza station:
Virus infection level in Gemmiza station was lower than ARC Cairo station in untreated plots (D0).
Efficiency of seed treatment was less evident than ARC Cairo, but disease score data showed positive effect
We can recommend to use D2 (2.5 g/kg) for ApS and D1 (0.75 cc/kg) for CT.
Giza 3 is more tolerant than the other two genotypes
Effect of seed dressing with Apron Star (D2) on virus infection of faba bean (Sakha 1) (right) under natural infection in Gemmiza field conditions as compared to untreated plots (left)
Sakha 1
Highlights…
Apron Star (ApS)
Celest top (CT)
Treated with Apron Stat
Un-treated

## Slide 41: IDO2/ Wellbeing – Seed system & dissemination
Objectives
Analysis of cereals and legumes seed system constraints
Initiating alternative seed delivery systems using Village-Based Seed Enterprises (VBSEs)
Achievements
Understanding the cereal (wheat) and legume fabab bean) seed system constraints in Meknes site
Development of alternative seed delivery system:
  Six communities of 60 farmers with 600 ha of land identified
  Seed (40 q) of new legume varieties for local seed production provided
  An integrated seed processing machine ordered and delivered
Capacity development:
  6 communities & 300 farmers benefited from technical backstopping
  3 integrated mobile seed processing machines provided to pioneer farmers

## Slide 42: IDO3/Women & children have access to greater quantity & diversity of food
Objectives:
  Identify options for new income generating activities and employment opportunities for women and youth in selected value chains to improve households’ livelihoods (Assess gender barriers to greater access to natural resources (including land), inputs, credits and markets, and for sustainable management of natural resources) ; (Develop and test new mechanisms for empowering rural women and youth to equitably share responsibilities and benefits of agricultural development
How:
  Gender Mainstreaming of technologies related to Crop-Livestock Systems
  Collecting Sex Disaggregated Data in all CRP-DS sites for Gender Analysis

## Slide 43: Gender Mainstreaming/Integrative Research (Technologies at the Center)
Major Objectives | Achievements
Gender Mainstreaming of technologies related to Crop-Livestock Systems in Karak, Jordan | -Identification of main technologies utilized in crop-livestock systems and related conditions for adoption -Collaboration with 6 extension and research staff from NCARE and a graduate student in gender studies from the University of Guelph, Canada -Farm visits and interactions with farmers
Analyzing and Collecting Sex Disaggregated Data in all CRP Dryland Systems Action Sites | -DS Baseline Survey engendered in collaboration with Cheryl Doss, Yale University -Collaboration with the International Centre for Women's Leadership, St. Francis University, Nova Scotia, Canada for capacity development of biophysical scientists

## Slide 44: IDO4/NRM & IDO1/Resilience –Soil & Water Conservation
Objectives: Introduce, test and promote soil conservation and water harvesting interventions to optimize the use of land and water resources, improve productivity and reduce land degradation.
Methodology: Soil conservation and water harvesting interventions will be implemented as a land management packages (appropriate technologies integrated with water, crop and soil management packages through participatory approach). Modelling and observatory systems will be used to ensure positive impact and to test scenarios under different climate change and land use patterns. These tools should facilitate out-scaling to similar environment and enhance adoption at large scales.
Sites: Tafila & Salamyieh (Karak & Majidya ; Beni Khedache -Sidi Bouzid; Karkheh river basin
Phase: Proof of concept/pilot

## Slide 45: IDO4/NRM & IDO1/Resilience –Soil & Water Conservation
Beni Khedache & Zoghmar
  Data collection (site presentation, stock-take and projects on water and soil conservation management, …)
  Preparation of a questionnaire concerning water and soil conservation techniques
  2 PHD students engaged on modeling water balance and solid transport in semi-arid areas and agro economic aspects and gender issues
  Drafting reports on:
    analysis of actual situation and problems in the study site,
    Identification and characterization of the experimental fields
    collection, analysis and preparation of input data for modeling

## Slide 46: IDO4/NRM & IDO1/Resilience
Tafilah – Salamya site:
  Water harvesting techniques and planting of shrubs in addition to grazing management conducted with local communities in Majidiyya and Muhareb showed the potential for improving rangelands’ contribution to livestock feeding and the reviving of native species including some wild relatives of crops of global
  More than 3 pastoral communities were shown to be making profit from the area rehabilitated.

## Slide 47
Beni Khedache, Tunisia

## Slide 48
Hill reservoirs (Zoghmar)

## Slide 49: Hydrological Monitoring at hill lakes reservoirs
49
Hydrological data
Recording of water levels and precipitation
Recording precipitation and evaporation

## Slide 50
Contour benches, Zoghmar
Tabia, Zoghmar

## Slide 51
51
Hydrological functioning of inter-bench plots
Fallow plot
Tilled plot
Rain gauge and limnigraph

## Slide 52: Soil & water conservation in the Jordanian site
Watershed modeling and monitoring activities continue in Al-Majidyya site
Water harvesting and soil conservation interventions (Vallerani intermittent pits in 30 ha) in Erak watershed - Karak
Soil conservation, intercropping and erosion monitoring experiment (University of Jordan station – Shafa Badran)

## Slide 53: IDO4/NRM and IDO4/Wellbeing - Irrigation
On-farm trials in different locations of Meknes site to evaluate the effect of supplemental irrigation on the yield of wheat bread, vegetables (potatoes and onion) and olive trees.
Results indicate that the best period of supplemental irrigation application on wheat was sowing (20 mm) and tillering (40 mm).
For potatoes and olive trees, the application of 75% of FSI allowed the saving of irrigation water without yield reduction
In Egypt results from demonstrations’ in farmers’ fields show the advantage from using the raised-bed technique. In 2012-2013 the technology allowed 24 % saving in irrigation water, 34 % increase in wheat yield and 78% improvement in water use efficiency.

## Slide 54: IDO5/Gender empowerment
Major Objectives | Achievements
Understand how innovations (soft and hard) change men’s and women’s roles in irrigated agriculture in Kafr El Sheikh and Noubariya in Egypt | -Examining how class, education, land access, culture, and government policies interact to enable or impede men and women from accessing and benefitting from innovations in the Dry Areas -Farm visits and interactions with farmers - Book chapter completed on women, political ecology, and cactus in 5 villages of the Intilaq settlement (in the Noubariya)
Understand how extension system in Karak, Jordan can become more gender-responsive | -Graduate student in General Management at Mo’ta University completed literature review and conducting fieldwork with extension agents and farmers in Karak for identifying gaps between gender-specific needs and services provided

## Slide 55
Major Objectives | Achievements
Understand how agency, gender norms, and innovations interact to improve equality and empowerment of women* | -Team of 4 formed in Morocco comprising of consultant gender specialists and NARES researchers for starting fieldwork on July 20, 2014 -Focus is placed on ICARDA technologies
*Part of a cross-CRP global study, entitled “Innovation and Development through Transformation of Gender Norms in Agriculture and Natural Resource Management”.
IDO5/Gender empowerment (ctd.)

## Slide 56: IDO6/Capacity to innovate/ Policies on NR
Objectives: evaluate the impacts of water, energy and land policies on rangeland ecosystems, on use of farm resources and on livelihoods of small holder farmers
Methodology:
  Literature surveys
  Existing household surveys
  Econometric analysis
  General equilibrium
Outputs: to produce empirical evidence, analysis and recommendations on water, energy and land policies. It is also expected to organize one sensitization workshop in Morocco and in Tunisia, and to produce at least two policy briefs.
Outcomes: Increased awareness of policy makers and relevant influential stakeholders on the need for action to promote more sustainable practices of water use reduce. Increased participation of stakeholders (farmer, professionals, and policy makers) in the dialogue on water management.

## Slide 57: IDO6/Capacity to innovate/ Policies on NR
Review of current water management policies were completed in Egypt, Jordan, Morocco and Tunisia.
A large global conference was held on water and food security attended by about 300 participants, including about a dozen ministries and national agricultural leaders. Case studies of national policies were presented, addressing water and food security. The meeting included a dialogue among professionals and policy makers on how to address the twinned challenges of water and food security.

## Slide 58
Objective:
Assist stakeholders to form innovation platforms that have influence over the enabling environment which supports agricultural research for development and link that to community based development activities-
Focus: to create strong policy and intuitional support for agricultural innovations and out-scaling of them for greater number of beneficiaries
Multiple level approach:
  Area based learning platforms that contextualize the need for specific research and support services,
  Regional innovation platforms
  National innovation platform
IDO6/Capacity to innovate/ IPs

## Slide 59: IDO6/Capacity to innovate/ IPs & Innovation clusters
Five innovation platforms (IPs) are being initiated for the five sites and involving all stakeholders, including community representatives, extension, development agencies, NGOs, local decision makers, scientists, and private sector.

## Slide 60
INNOVATION PLATFORM in Zoghmar community in Sidi-Bouzid on December 23, 2013
A total of 190 participants from :
Small farmers, policy makers
International partners (FAO, ICARDA),
National development organizations (CRDA Sidi-Bouzid, INGC, OEP), Extension, Agroprocessors
National research institutions (INRAT, EMVT, CRRA Sidi-Bouzid),
NGO’s and local media attended the meeting.

## Slide 61
To identify the main constraints of smallholder farmers in Zoghmar community.
Stakeholders shared their experiences in working groups
Opportunity:
To identify institutional support to the program.
to adjust activities

## Slide 62
6 learning alliances initiated in partnership with national partners:
    Meknes site, Morocco (Sidi Slimane, Bittit, Ain Jamaa);
    Medenine, Tunisia (Beni Khedeche);
    Karak, Jordan(Al Erak, Al Kresha)
2 learning alliances initiated by ICARDA in 2013 (Egypt, Southwestern Morocco), under an IDRC funded bilateral project, are being monitored and studied;
Each learning alliance has identified commodities of priority that are being studied by the post-harvest loss and market access activity (value chain analysis);
Assessments of pathways for research and farm advisory services to effectively utilize well organized local organizations as conduits for scaling out agricultural technology and best production practices
High Value Chain Cluster
IDO6/ Capacity to innovate - Progress

## Slide 63: IDO6/ Capacity to innovate - Progress
Guidelines for facilitating the institutionalization of innovation platforms, with common understanding among scientists and partners documented and utilized- in progress;
Analysis of farm advisory services, in order to understand potential avenues available for enhancing adoption, adaptation and broad uptake of technologies and best production practices
Development of a compendium of technologies, best production practices, approaches, social and institutional innovations for each action site:
Innovation Platforms

## Slide 64: IDO6/ Capacity to innovate – Bio-economic modeling

## Slide 65
Country | ALS | Progress to date | Challenges | Expected impact
Jordan | Tree-crop-livestock | Draft literature review on bio-economic modeling produced Conceptual/theoretical model developed; Data needed for calibrating (APSIM) being collected Algebraic model being developed | Funding continues to be a problem. The model requires large amounts of panel data which are often not available. Suitable livestock simulation model not yet found | Potential impacts of technologies, and policy, institutional and market innovations determined and awareness of researchers, policy makers and extension agents raised.
Morocco | Irrigated | Draft report on Biophysical Modeling in agricultural research: Review and perspectives for Morocco produced | Signing of MoA for collaboration with IAMM-CEHEAM delayed due to funding problems | 
Objective: Develop bio-economic models to assess potential impacts and out-scaling opportunities for different technologies and policy, institutional and market innovations

## Slide 66
IDO6/ Capacity to innovate – Post-harvest & market access
Morocco
Potatoes and Onion
Egypt
New Land-Nubaria: Citrus (Oranges), Buffalo milk
Old Land – Sharkia: Tomatoes, Buffalo milk
Salt-Land – Port-Said: Buffalo milk
Jordan
Erak: Olive trees
El Khrishet Village: Livestock and livestock products
Tunisia
Sidi Bouzid: Lamb
Beni-Khdeche: Olive trees

## Slide 67
IDO6/ Capacity to innovate – Post-harvest & market access/ Progress
Diagnostic and selection of the relevant stakeholders in the value chain of the selected crops: Producers, input providers, traders, agro-processing, regulators, quality, wholesalers, retailers, and consumers.
Mapping the challenges for smallholder market access: Review of literature on institutional arrangements in collective marketing.
Marketing survey, supply chain mapping and post-harvest management (on-going)

## Slide 68: Overview on capacity development
A total of 1248 men and 388 women benefit from short-term training. Twenty four (24) men and 15 women benefit from long term training (MSc and PhD).
Few examples in addition to already indicated:
  A Tunisian WLI Stakeholders Meeting was conducted (Dec 2013) involving policy makers, farmers, local NGO’s to gather community needs before implementing land and water conservation practices in Tunisia.
  Policy adoption workshops in Beni Khedache, Tunisia and Meknes, Morocco (Dec 2013) to analyze current policies and constraints to agricultural development.
  Three women based CBOs were equipped with business management skills that will allow them to initiate and mange small businesses. It is anticipated that increasing off-farm income thereby reducing dependence on on-farm income, and pressure on a fragile eco-system (land and water).
  Irrigation water management for olive growing, March 10-14, and June 16-20, 2013, Daraa, Syria, funded by CFC and OFID (11 females; 18 males)

## Slide 69: Suggestions…
Nice pieces of work are being implemented that need to be “better cemented” together through:
  More focus on system research
  Consolidate the community approach
  More focus on bio-economic modeling
  Working mechanisms (clustering activities and get organized around IDOs instead of activities)
Bilateral projects are not well integrated (especially in reporting)
Bring other CG centers in the region
Need to involve more ARI (CIRAD, Wageningen, CSIRO, etc)

## Slide 70: The inception phase
Bringing together the foremost scientists from a multitude of disciplines in order to assess needs and formulate hypothesis, outcomes and activities
Inception Regional Workshops
Regional Launch Meeting & Kick-off meetings by site
Plan of Work and Budget
2011
2013
ICARDA scientists & management
NARS scientists & decision makers
Assumption: Communities/farmers “opinion” is reflected through ICARDA and NARS scientists and other resource persons

## Slide 71: On-going validation using ICARDA community participatory approach within IPs

## Slide 72: Establishing IPs through Community development plan & learning alliance
Phase 1. Characterization of the community
Phase 2. Participatory diagnosis and planning
Phase 3. Participatory programming
Phase 4. Promoting local CBOs
Phase 5. Implementation of community development plan and Monitoring and evaluation.
Fostering integration between different disciplines, actors, etc.
Stimulating farmers and communities participation in steering their own development process.
Facilitating technology transfer through a participatory technology development.
Promoting collective action on the basis of a shared consensus.

## Slide 73: Main phases of the community participatory approach and community development plan (CDP) (Nefzaoui et al., 2007)

## Slide 74
A. Nefzaoui et al. 2006
A. Nefzaoui et al. 2006
Improved knowledge of the communities to better work together
Phase I: Community characterization
D ?
M&E

## Slide 76
A. Nefzaoui et al. 2006
Phase I & II: Participatory diagnosis and planning, and initiation of CBO

## Slide 77: Need to work with focus groups

## Slide 78
Long-term vision development map

## Slide 79
A. Nefzaoui et al. 2006
Phase I & II: Participatory diagnosis and planning, and initiation of CBO

## Slide 80
A. Nefzaoui et al. 2006
Phase IV: Participatory programming

## Slide 81
Development
vision map
Development
vision map
Development
vision map
Community
knowledge book
Community
Data base
Community
knowledge book
Community
Data base
Community
Data base
Community
knowledge book
Community
Data base
Community
Community
knowledge book
Community
Data base
Community
Data base
Phase I: Community characterization
Participatory diagnosis and planning
Development vision map
Formalizing CBO
Primary CDP
Technical feasibility analysis
(technical itinerary, details of operation, implementing capacity, costs, ect)
Multiannual CDP
Output 1
MOU between project & CBO
Output 3
Implementation agreement (project & CBO)
Output 2
Annual budget program