Water and labour saving technologies by micro-irrigation and machineries, selection of farmers and appraisal of potato cultivation in system :  In a meeting with stakeholders at Maan Sagar, the project aims such as advantages of adopting potato cultivation in cropping system in rotation with cereal, use of micro-irrigation to save water, improved production technologies such as paired row planting, machineries to save labour and get higher productivity, introduce high yielding heat and drought tolerant potato varieties suitable for arid ecology, bringing private sectors to introduce contract farming for easy availability of quality seed, inputs and provide  platform for marketing their produce at remunerative prices were discussed.  The farmers had lot of queries and were keen to know when and how they can be part of the project. Orders have been given for two paired row potato planters and two diggers from Deesa, Gujarat for planting and harvesting potato at 25 farmer’s fields in Maan Sagar and 5 farmers field in Jaisalmer. The purpose of buying the modern machines is to improve water use efficiency, productivity and quality of potato, reduce dependency and cost on manual labour for field operations. The local government officials of Horticulture and Agriculture Departments (Director, Additional Director, Joint Director, Deputy Director) were contacted in Jaipur and Jodhpur and appraised about the potato project and its role in improving livelihood of farmers in Rajasthan and involve them as active project partners to implement project activities successfully. The information about the policies and subsidies on the micro-irrigation (sprinkler and drip) installation at selected project farmers’ field was discussed. On their suggestion, local supplier of the drip and sprinklers were contacted. Since the new guidelines from government for the micro-irrigations are in the process and therefore installation process will take some more time. In another meeting in Maan Sagar, twenty five farmers were selected in the village on the basis of water sources and capabilities to take the challenge of growing the highly sensitive income generating potato crop in the system.  These farmers will receive seeds and inputs before potato planting in November 2015. The farmers who will get the sprinkler/drip irrigation installed on their own before planting season will only get the inputs including seed. They were briefed about the timings of field operations, the practices to be followed for potato cultivation, the tentative time for fields to be free for potato cultivation. Lists of the farmers given below -

| S.No. | Name | Father's name | Contact No. |
| --- | --- | --- | --- |
| 1 | Babu Singh | Bishan Singh Rathore | 9166804093 |
| 2 | Bhanwar Singh | Kaan Singh Rathore | 9928475828 |
| 3 | Kaan Singh | Bhojraj Singh Rathore | 9166996487 |
| 4 | Shyaam Singh | Tej Singh Rathore | 9950492134 |
| 5 | Jethu Singh | Chen Singh Rathore | 9166931700 |
| 6 | Dhirendra Singh | Jabar Singh | 9680602551 |
| 7 | Chotu Singh | Sajjan Singh | 9784610308 |
| 8 | Pappu Ram | Jora Ram | 8107481130 |
| 9 | Ram Niwas | Jora Ram | 9929826199 |
| 10 | Ramrakh Niwas | Kanaram | 9660798989 |
| 11 | Jaala Ram | Kanaram | 9929153981 |
| 12 | Shankara Ram | Pularam | 9602084940 |
| 13 | Mohan Ram | Heeraram | 8003112186 |
| 14 | Ana Ram | Heeraram | 9571387817 |
| 15 | Aanshu Ram | Kherajram | 9636942214 |
| 16 | Mohan Ram | Butaram | 8890757279 |
| 17 | Jagmal Ram | Khegaarram | 8107157202 |
| 18 | Babu Ram | Khegaarram | 9587622940 |
| 19 | Rampal | Bhiyaram | 9636996273 |
| 20 | Shakta Ram | Gorakhram | 9251314629 |
| 21 | Sardarmal | Madal Lal | 8107390515 |
| 22 | Gopal Singh | Chandra Singh | 9784440403 |
| 23 | Raghunath Singh | Tej Singh | 9784828409 |
| 24 | Kana Ram | Narayan Ram | 9602011878 |
| 25 | Manohar Singh | Hiyat Singh | 9950282272 |

Hiring of local staff: CIP has hired three local field staff to be based at project site in Maan Sagar area particularly for communicating with project target farmers in implementing the activities timely and successfully. The staff includes two young energetic youth one male and one female and third a mature farmer who are well acquainted with the potentials and problems of the area and new technologies.