## Milestone Reporting
2021 CRP RTB Milestones
The list of milestones presented are results planned for 2021 and not accomplished from previous reporting cycles.
FP | RTB 2022 Outcome | Milestone | Cluster (COA) Contributing | Expected Year | Status (Completed or Canceled) | Summary progress (200 words max) | Evidence (MEL ID or DOI/handle) | Brief summary of main achievements for specific cross-cutting marker (100 words max by marker)
[8 empty] | Gender | Youth | CapDev Activities | Climate Change
1 | Outcome 1.2: Across RTB crops, average 25% reduction of time needed for traits discovery and incorporation into breeding pipelines | Platforms for high-throughput phenotyping under implementation for at least 4 RTB crops | 1.1; 1.2 | 2020 | Extended
1 | Outcome 1.4: At least 20% of newly developed RTB breeding populations with enhanced resilience to climatic shocks available for testing in FP2 | Platforms for high-throughput phenotyping for climate resilience under implementation for at least 3 RTB crops | 1.2 | 2021
1 | Outcome 1.1: For each RTB crop, populations with at least 3 end-users preferred traits and adapted to 2 targeted regions are available (For more details please refer to Table FP1.4) | Gene-edited RTB crops with enhanced traits for breeding and / or direct release | 1.3 | 2021
1 | Outcome 1.1: For each RTB crop, populations with at least 3 end-users preferred traits and adapted to 2 targeted regions are available (For more details please refer to Table FP1.4) | Enhanced insitutional capacities in regulation and stewardship of RTB crops with game-changing traits | 1.3 | 2021
2 | Outcome 2.4: Annual production of at least one nutrient-rich RTB crop increased by 5-10% in 10 targeted countries | Clones of nutrient-rich potatoes and cassava evaluated in 5 countries. | 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 | 2018 | Extended
2 | Outcome 2.3: Targeted breeding programs increased by 10% the diversity of the genetic base used (e.g. number of banana wild species used as parental lines) | Traditional knowledge of the landraces and wild relatives for banana in 5 countries documented for traits of importance, traditional uses, and other cultural and socio-economic aspects | 2.1; 2.2; 2.3; 2.4; 2.5; 2.6; 2.7; 1.4 | 2021
2 | Outcome 2.7: Regulatory frameworks for seed production and seed quality control (including QDS) under implementation in10 countries | RTB included in national food security related policies and initiatives in at least 10 countries | 2.1; 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 | 2021
2 | Outcome 2.2: At least 5,000,000 HH increased their annual RTB yield by at least 10% | Increased number of farmer HH adopting improved varieties | 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 | 2021
2 | Outcome 2.2: At least 5,000,000 HH increased their annual RTB yield by at least 10% | Increased number of farmer HH adopting improved post-harvest techniques including adapted storage facilities, especially for on-farm seed management | 2.1 | 2021
2 | Outcome 2.7: Regulatory frameworks for seed production and seed quality control (including QDS) under implementation in10 countries | Benefit-sharing mechanisms protecting custodian farmers’ rights and facilitating the exchange of Musa genetic resources piloted in 3 countries and recommendations formulated | 2.1; 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 | 2021
2 | Outcome 2.6: At least 35% increase in number of female and young beneficiaries of at least 500,000 HH perceive to have better control over assets and resources | At least 25% of HH adopting improved varieties/seeds are female headed households | 2.1; 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 | 2021
2 | Outcome 2.1: 20,000,000 people (4,000,000 HH), of which 50% are women, increased their annual income by increasing RTB sales and diversifying market strategies | 5,000 profitable decentralized seed business created, of which 30% are run by women and young people | 2.1; 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 | 2021
2 | Outcome 2.4: Annual production of at least one nutrient-rich RTB crop increased by 5-10% in 10 targeted countries | 3,500,000 households, of which at least 25% are female headed, adopting nutritious varieties | 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 | 2021
2 | Outcome 2.8: Every year, 8,000 R&D stakeholders (50% female) trained through short term programs on designing and implementing smallholder-oriented breeding programs and sustainable seed systems | 150 individuals (50% female) trained through long term programs (e.g. MSc and PhD students) | 2.1; 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 | 2021
2 | Outcome 2.2: At least 5,000,000 HH increased their annual RTB yield by at least 10% | Increased number of HH (at least 2,500,000) adopting improved agronomic practices for RTB ware and seed production | 2.1; 2.2; 2.3; 2.4; 2.5; 2.6; 2.7 | 2022
3 | Outcome 3.2: 1,800,000 ha of current RTB production area converted to sustainable cropping systems | Results provided by prediction models used for developing or updating national and regional strategies | 3.1; 3.2; 3.3; 3.4; 3.5; 3.6 | 2021
3 | Outcome 3.1: In areas affected by pests and diseases, RTB yield restored to previous infection conditions by at least 1,500,000 farmer HH, of which at least 25% are female headed households | Individual and community strategies for IPM equally adopted by male and female farmers in 1,200,000 HH | 3.1; 3.3; 3.4; 3.5; 3.6 | 2021
3 | Outcome 3.2: 1,800,000 ha of current RTB production area converted to sustainable cropping systems | Gender-sensitive, context -specific agronomic practices adopted in 1,200,000 HH, of which at least 25% are female headed households | 3.2 | 2021
3 | Outcome 3.3: Capacity to deal with climate risks and extremes increased for at least 1,000,000 HH | At least 60% of developed IPM/ICM management strategies assessed in terms of adaptation to future climates | 3.1; 3.2; 3.3; 3.4; 3.5; 3.6 | 2021
3 | Outcome 3.3: Capacity to deal with climate risks and extremes increased for at least 1,000,000 HH | At least 50% of developed IPM/ICM management strategies contribute in strengthening male and female farmers' adaptation capacity to climate change | 3.1; 3.2; 3.3; 3.4; 3.5; 3.6 | 2022
4 | Outcome 4.6: Food-based nutrition programs/ initiatives promoting RTB crops under implementation in at least 10 countries | RTB crops included in at least 5 medium to large scale nutrition programs/ initiatives developed and/or implemented during the period 2017-2020 | 4.3; 4.4 | 2020 | Extended
4 | Outcome 4.4: Diet quality indices increased by 20% for at least 2,000,000 farmer households and urban/rural consumers | Techniques for inclusion of sweetpotato as an ingredient in commercially processed baked products (bread, cakes, other local wheat based products) documented and training material for small scale processors of commercially viable OFSP based products produced | 4.4 | 2018 | Extended
4 | Outcome 4.6: Food-based nutrition programs/ initiatives promoting RTB crops under implementation in at least 10 countries | RTB crops and products actively promoted by mainstream national nutrition programs in at least 10 countries, with commercial sector investments in highly nutritious RTB foods in at least 2 countries | 4.3; 4.4 | 2021
4 | Outcome 4.1: 700,000 households, 25% of which are female headed, have increased their income by 15-20% by increasing and diversifying RTB sales (food, feed, industrial raw material and seeds) | Increased RTB sales and employment, of which 33% directly benefit women and young people, created in RTB value chains (measured at intervention site level for selected countries) | 4.1; 4.2; 4.3; 4.4 | 2021
4 | Outcome 4.7: 60 development-focused organizations, including women's networks and alliances, having increased their capacity for innovation (e.g. enhanced human capital and improved collaboration network in relevant domains) to scale up fuller utilization of RTB | At least 60 organizations and businesses in 10 countries invested in human resources (at least 33% female beneficiaries) and organizational development to scale up production and dissemination of nutritious RTB foods and value-added products | 4.1; 4.2; 4.3; 4.4 | 2021
4 | Outcome 4.4: Diet quality indices increased by 20% for at least 2,000,000 farmer households and urban/rural consumers | Diet quality, including diet diversity, improved for 50% of women of reproductive age and children under 5 years of age in at least 2,000,000 HH | 4.3; 4.4 | 2022
5 | Outcome 5.2: Whole-farm productivity increased by 25% for at least 1,000,000 HH | Whole-farm productivity approaches included in national/regional policies and development initiatives in at least 10 countries | 5.2 | 2021
5 | Outcome 5.10: At least 5 partnerships and scaling models tested in a minimum of 5 target countries and adjusted to be fit for purpose | Performance of at least 5 partnerships and scaling models in a minimum of 5 target countries assessed, and cross-country experiences shared | 5.4 | 2021
5 | Outcome 5.1: Income increased by 20% for at least 550,000 HH | Multistakeholder partnerships in at least 10 landscapes (region/district administrative level) promoted system intensification and diversification options in RTB-based farming | 5.2 | 2021
5 | Outcome 5.3: Diet quality indices increased by 20% for at least 300,000 farmer households | Multistakeholder initiative implemented at regional/district for whole-diets improvements in at least 10 countries | 5.2 | 2021
5 | Outcome 5.6: At least 35% increase in number of female and young beneficiaries of at least 200,000 HH perceive to have better control over assets and resources | Equitable SDI options for market-driven household income improvement under implementation in at least 5 countries | 5.3 | 2021
5 | Outcome 5.8: At least 66 cases where RTB crops/technologies are newly included in policies or programs executed by government agencies, NGOs, and/or private sector | At least 44 bi-annual stakeholder meetings held across target countries for co-design of impact pathways and M&EL around implementation, including needs assessment and customized product development | 5.4 | 2021
5 | Outcome 5.9: At least 1,500 research/development staff in RTB and in mixed-type partner organizations across prime target countries with strengthened research and innovation capacities including gender-responsive and transformative research | At least 1,500 users of RTB knowledge sharing mechanisms with strengthened capacity for designing, implementing and assessing RTB research | 5.1; 5.2; 5.3; 5.4 | 2021
5 | Outcome 5.10: At least 5 partnerships and scaling models tested in a minimum of 5 target countries and adjusted to be fit for purpose | At least 5 large-scale and rigorous impact studies conducted | 5.1 | 2022

## Outcome Reporting
2021 CRP RTB High-Level Outcomes
The list of outcomes presented belongs to the milestones planned for 2021 and not accomplished from previous reporting cycles.
FP | RTB 2022 Outcome | Summary Progress (200 words max)
1 | Outcome 1.1: For each RTB crop, populations with at least 3 end-users preferred traits and adapted to 2 targeted regions are available (For more details please refer to Table FP1.4)
1 | Outcome 1.2: Across RTB crops, average 25% reduction of time needed for traits discovery and incorporation into breeding pipelines
1 | Outcome 1.4: At least 20% of newly developed RTB breeding populations with enhanced resilience to climatic shocks available for testing in FP2
2 | Outcome 2.1: 20,000,000 people (4,000,000 HH), of which 50% are women, increased their annual income by increasing RTB sales and diversifying market strategies
2 | Outcome 2.2: At least 5,000,000 HH increased their annual RTB yield by at least 10%
2 | Outcome 2.3: Targeted breeding programs increased by 10% the diversity of the genetic base used (e.g. number of banana wild species used as parental lines)
2 | Outcome 2.4: Annual production of at least one nutrient-rich RTB crop increased by 5-10% in 10 targeted countries
2 | Outcome 2.6: At least 35% increase in number of female and young beneficiaries of at least 500,000 HH perceive to have better control over assets and resources
2 | Outcome 2.7: Regulatory frameworks for seed production and seed quality control (including QDS) under implementation in10 countries
2 | Outcome 2.8: Every year, 8,000 R&D stakeholders (50% female) trained through short term programs on designing and implementing smallholder-oriented breeding programs and sustainable seed systems
3 | Outcome 3.1: In areas affected by pests and diseases, RTB yield restored to previous infection conditions by at least 1,500,000 farmer HH, of which at least 25% are female headed households
3 | Outcome 3.2: 1,800,000 ha of current RTB production area converted to sustainable cropping systems
3 | Outcome 3.3: Capacity to deal with climate risks and extremes increased for at least 1,000,000 HH
4 | Outcome 4.1: 700,000 households, 25% of which are female headed, have increased their income by 15-20% by increasing and diversifying RTB sales (food, feed, industrial raw material and seeds)
4 | Outcome 4.4: Diet quality indices increased by 20% for at least 2,000,000 farmer households and urban/rural consumers
4 | Outcome 4.6: Food-based nutrition programs/ initiatives promoting RTB crops under implementation in at least 10 countries
4 | Outcome 4.7: 60 development-focused organizations, including women's networks and alliances, having increased their capacity for innovation (e.g. enhanced human capital and improved collaboration network in relevant domains) to scale up fuller utilization of RTB
5 | Outcome 5.1: Income increased by 20% for at least 550,000 HH
5 | Outcome 5.10: At least 5 partnerships and scaling models tested in a minimum of 5 target countries and adjusted to be fit for purpose
5 | Outcome 5.2: Whole-farm productivity increased by 25% for at least 1,000,000 HH
5 | Outcome 5.3: Diet quality indices increased by 20% for at least 300,000 farmer households
5 | Outcome 5.6: At least 35% increase in number of female and young beneficiaries of at least 200,000 HH perceive to have better control over assets and resources
5 | Outcome 5.8: At least 66 cases where RTB crops/technologies are newly included in policies or programs executed by government agencies, NGOs, and/or private sector
5 | Outcome 5.9: At least 1,500 research/development staff in RTB and in mixed-type partner organizations across prime target countries with strengthened research and innovation capacities including gender-responsive and transformative research