## Workplan 2020 (2)
Annual Work Plan and Budget (AWPB) for twelve (12) month period (January 1 2020 - 31 December 2020)
Effective date of the agreement: 8 June 2018
Project completion date: 30 June 2022
Project implementation period: 8 June 2018 - 30 June 2022
Project team members: AK=Akmal Akramkhanov, EB=Enrico Bonaiuti, BM=Bastian Mueller, VG=Valerio Graziano, EV=Emilie Vansant, MS=Murat Sartas
Ouctome | Activity | Description of Activity | 2020 |  |  |  | Responsibility | Partners | Outputs/indicators | Measn of Verification | Geographical Coverage |  |  |  | Budget 2020 | Budget to Partners | Who? | Co-funding | Who? | YEAR 2: Jan 2020 - Jun 2020 | [5 empty] | YEAR 2: Jun 2020 - Dec 2020 | [5 empty] | Narrative
|  |  | Q1 | Q2 | Q3 | Q4 | [5 empty] | Target for Planned Year (2020) | Target for Entire Project (2018-2022) | Progress in the previous reporting Period (2018-2019) | [5 empty] | Total costs | Salaries and Allowances | Consultancies | Goods and Services | Workshops | Operating Costs | Total costs | Salaries and Allowances | Consultancies | Goods and Services | Workshops | Operating Costs | Narrative
Component 0: Project management (coordination, M&E, steering committee)
Project management | 0.1 | Project coordination |  |  |  |  | AA |  | Planning and implementation of project activities, technical and financial reporting (#2), development and follow-up of agreements with co-implementing partners (#3) and national partners (#4) in focus countries | Project implementation (reports, workplans, budget, ToR, MoAs) | All Counties | 7 | 17 | 4 | 40463.095 |  |  |  |  | 12138.9285 | 8862.0285 | 0 | 0 | 0 | 3276.9 | 28324.1665 | 20678.0665 | 0 | 0 | 0 | 7646.1 | Overall target: New, sub-activity is added from AWPB 2020, separated project management as Component 0. To ensure AWPB, AR, Agreements are implemented in accordance with the proposal and corrective measurements are in place and adapting to the situation (e.g. COVID-19) Progress: Developed workplans, financial reports, MoA, progress reports, liaison with stakeholders. The activity follows the scheduled plan and during Q1/2020 has assessed the impact of COVID-19 on project activities. Plan 2020: Finalize AWPB 2020, annual report, overal coordination, liaison with stakeholders, organize events. COVID-19 Impact: The activity has been planned with 25% Coordinator time as expected activities in March (Sudan) and June ( Moldova) are postponed and most probably a face-to-face training in Morocco will be postponed. Budget utilization is expected to be implemented as proposed.
| 0.2 | Monitoring and evaluation / financial audit |  |  |  |  | EB, EV | country representatives, co-implementing partners | Annual workplan and budget review and planning, M&E plan (#1), Mid-term evaluation: TOR (#1), Selection and Implementation (#1) | AWPBs, Technical Reports | All Counties | 2 | 5 | 1 | 30000 |  |  | 15000 | ICARDA | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 24000 | 0 | 4000 | 2000 | Overall target: New, sub-activity is added from AWPB 2020, separated project management as Component 0. To implement project M&E acivities in accordance with IFAD Evaluation Framework. Progress: The project team developed and published the Mid-term evaluation TOR. Project management related outputs are extracted here: Impact pathway of the project; M&E plan; AWPB 2018-2019. Plan 2020: Detailed M&E plan with indicators to measure progress; Screening Mid-term evaluation applicants in March-April and schedule mid-term evaluation during the last quarter of 2020; AWPB 2020. COVID-19 Impact: The mid-term evaluation may be post-poned to Q1/2021 in case several activities under component 2 will be delayed. This will impact on the consultancy and workshop budget. The staff time from EB (10%) is provided in-kind. | Funds to carry to 2021 - 19,000 USD 15,000 USD mid-term evaluation 4,000 USD workshop cost to switch to consultancy to support evaluator by local specialist | 19000
| 0.3 | Steering Committee |  |  |  |  | AA | country representatives, co-implementing partners | Regular virtual meetings and email correspondance to review project progress, contribute inputs into project activities and decision making. Annual Face-to-Face Meeting (#1) | Reviewed AWPBs, Reports | All Counties. SC Meeting in Moldova | 1 | 5 | 2 | 24000 |  |  | 3250 | CIHEAM | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 24000 | 0 | Overall target: New, sub-activity is added from AWPB 2020, separated project management as Component 0. Partners provide inputs into the project decisions. Progress: Formed Steering Committee (SC); developed ToRs for national committees to establish and support by the project; conducted SC meeting in 2019. Plan 2020: SC committee meeting, virtual review AWPB on a quarterly basis. Finalize engagement of national focal point to support CoP actions (Activity 1.4). Focal points will support coordination at national level for Symposia in 3.2. AA time is included in activity 0.1. COVID-19 Impact: Steering Committee is expected to take place in November (Moldova) and we dont expect delay due to COVID-19. The Steering Committee may however organized in a country without restrictions or virtually. Staff time for the activity is provided in-kind by project partners. | Funds to carry to 2021 - 24,000 USD. Since travel restricted, consider: Option 1: Develop various e-learning courses (requires budget line change from workshop to Goods and Services); Option 2: Organize regional workshop in 2021 (no budget line change) | 24000
Component 1: KM capacity assessment for enhanced formulation of learning needs
1. Improved understanding of KM capacities of the key rural institutions in 3 (+2) target countries in NEN region | 1.1 | Assessment of available knowledge, identification of knowledge management capacity gaps and prioritizing learning needs |  |  |  |  | EV | country representatives, co-implementing partners | 1) Reports on institutions committed to the project detailing baseline in KM including capacity assessment and options/responses to address identified gaps /. 2) Report detailing organizational overview and active projects. 3) Report on IFAD Projects x countries with Knowledge Entry point. | Technical Reports | All Counties | 3 | 5 | 2 | 14400 |  |  |  |  | 7200 | 7200 | 0 | 0 | 0 | 0 | 7200 | 7200 | 0 | 0 | 0 | 0 | Overall target: Assessment of KM in target organizations: institutional KM mapping to identify key partners; inventory of current practices, capacity gaps and learning needs. Progress: Stakeholder selection; Capacity Needs Assessment (CNA) of stakeholders in focus countries completed. Plan 2020: Reports from institutions committing to integration of KM, active projects. EV has planned 100% time in this activity. COVID-19 Impact: No impact is expected on this activity. However Emilie Vansant will start a PhD in June and we have initiated a recruitment for a dedicated research fellow to continue the support for this activty and 1.4.
| 1.2 | Approach Paper on knowledge management and communication strategy |  |  |  |  | MS | Virginia Tech, Community of Practice members, consultants | Finalized Approach Paper. | Working Paper | All Counties | 1 | 1 | 0 | 23775 | 0 | VIRGINIA TECH |  |  | 4500 | 0 | 4500 | 0 | 0 | 0 | 19275 | 0 | 18000 | 1275 | 0 | 0 | Overall target: Paper based on a combination of consultations, desktop studies and field visits. Progress: Elements of Approach Paper identified, consultations on formulating the document completed. Plan 2020: Finalized Approach Paper; develop manuscript to submit to international journal for publication. MS time is estimated at 20%. COVID-19 Impact: No impact is expected on this activity.
2. Effective learning systems established and embedded across organizational processes with strengthened human and institutional capacities to manage the systematization of good practices | 1.3 | Development of capacity development and innovation plans for the target countries |  |  |  |  | VG, EV | ICARDA | Documents uploaded online (access to developed innovation plans). | Technical Reports | All Counties | 0 | 3 | 3 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overall target: Jointly develop innovation plan for a capacity development, KM and communication strategies to enhance in-country institutional capacity. Progress: 3-writeshops conducted to discuss and develop innovation plans. KM strategy, KM and communication plans developed. Plan 2020: No major activities. Upload and access to finalized and formatted documents online. No time is estimated for this activity. COVID-19 Impact: No impact is expected on this activity.
| 1.4 | Regional workshop to kick-start implementation plans and Community of Practice establishment |  |  |  |  | MS | Virginia Tech, Community of Practice members, consultants | ToR and Action Plans (#3) for CoPs (or innovation platforms); National working meetings (#1) in country to evaluate institutional knowledge "value" | Technical Reports | All countries, Sudan | 4 | 5 | 1 | 44820 | 34320 | VIRGINIA TECH + National Partners | 2500 | VIRGINIA TECH | 9500 | 0 | 9500 | 0 | 0 | 0 | 35320 | 0 | 25000 | 4320 | 6000 | 0 | Overall target: Regional workshop to introduce implementation plans and to establish CoPs. Progress: Cross-country CoP regional workshop in Rabat, November 2020. Three CoPs established. Plan 2020: Develop ToR for CoPs to operationalize by National Partners, define roles and responsibilities, coordination. Implement CoPs under unified knowledge (innovation) platform. Assess and demonstrate the "value" of knowledge to decision makers, implemented by VTech. MS and VTech time is estimated at 2.5% while National Focal points will be dedicated full time starting from June. COVID-19 Impact: The field visit scheduled in Sudan during March has been postponed to September. We expect national partners to conduct initial COP facilitation as long as the situation (lock-down) improves between June and December. | Funds to carry to 2021 - 16,000 USD 6,000 USD workshop/travel 10,000 USD partner funds | 16000
Component 2: Capacity development and knowledge systematization
2. Effective learning systems established and embedded across organizational processes with strengthened human and institutional capacities to manage the systematization of good practices | 2.1 | Delivery of on-demand training courses in knowledge management and capacity development best practice |  |  |  |  | AA, MS | CIHEAM, Consultants | One training course organized (at least 20 participants; >=80% satisfaction/effectiveness rate) + 1 MOODLE module; Develop curriculum for on-demand training course on KM. | Technical Reports | Moldova + 1 Moodle | 2 | 8 | 1 | 41750 | 0 | CIHEAM |  |  | 5000 | 0 | 5000 | 0 | 0 | 0 | 36750 | 0 | 0 | 36750 | 0 | 0 | Overall target: Series of tailored capacity development training courses and materials, provided as face to face and online (Moodle). Progress: Training course on BigData in Rabat on December 10-14, 2018 to assess existing portals and capacities at national level. Plan 2020: One training course in 2020 by CIHEAM-Bari in Moldova. In addition, develop curriculum for on-demand training course on KM. MS time is estimated at 2.5%, AA time is part of activity 0.1 coordination while CIHEAM will dedicate full time team during the implementation period (preparation, implementation and reporting). COVID-19 Impact: We had scheduled one Traning course in Sudan with VT and two courses with CHIEAM in Moldova and Morocco. We have rescheduled two in 2021 and maitained one in Moldova after the summer period.
| 2.2 | Organization of at least 3 learning routes in the target countries |  |  |  |  | AA | PROCASUR | Number of learning routes organized (target=1; at least 25 participants, >=80% satisfaction/ effectiveness rate) | Technical Report | Sudan | 1 | 3 | 0 | 112531.7117 | 45000 | PROCASUR | 10000 | PROCASUR | 50012.045 | 3659.045 | 0 | 45000 | 0 | 1353 | 62519.6667 | 0 | 0 | 15000 | 46166.6667 | 1353 | Overall target: Screening and selection of best practices and organization of three Learning Routes in target countries. Handbook material of learning objectives of selected case studies. Progress: Discussion and formulation of agreement with PROCASUR. Plan 2020: Identification of priority-needs based best practices (in 3 countries); Systematization in country Source Book/ Case Studies; Design and implementation of Learning Route; Coaching, follow up of action/ Innovation Plans. AA time is part of activity 0.1 coordination while PROCASUR will dedicate full time team during implementation phase. COVID-19 Impact: The Systematization phase was scheduled for March 2020 but will be postponed during June-August in order to achieve the implementation of the learning route within 2020. | Funds to carry to 2021 - 40,000 USD (travel restrictions) Option 1: consider 6,000 USD for video instruction development of LR methodology in 2020 (requires budget line change from workshop to Goods and Services); Option 2: consider 40,000 USD to develop organizational/country KM Strategy in 2021 (requires budget line change from workshop to Goods and Services) (additionally to brainstorm further on what and how) | 40000
Component 3: Enhanced regional knowledge exchange.
3. Improved knowledge exchanges among stakeholders based on increased adoption of good practices | 3.1 | Set-up and regular maintenance of online portal that builds upon previous tools and capacities |  |  |  |  | VG | Community of Practice members, consultants | Frequency of use of knowledge products (target = 600 downloads per year and 3,000 visits per year) | Portal usage analytic summary | All Counties | 1 | 1 | 0 | 35041.2944 |  |  |  |  | 18675 | 0 | 8675 | 0 | 0 | 10000 | 16366.2944 | 0 | 8675 | 7691.2944 | 0 | 0 | Overall target: Develop KM online portal, ensure info-sharing. Link with Rural Solutions Portal and WOCAT. Progress: Project website created while portal is launched. Portal concept developed, designed and launched with interoperable repository. Plan 2020: Fine-tune, maintenance and integration of tools, populate with knowledge products, increase the use frequency. VG time is estimated at 50%. COVID-19 Impact: No impact is expected on this activity. | Funds to carry to 2021 - 4,000 USD (operating costs) | 4000
| 3.2 | Roll-out of five knowledge symposia |  |  |  |  | AA | Community of Practice members, suppliers | At least one national symposia organized by national partners. | Technical Report | Modova or Sudan | 1 | 5 | 2 | 15691.2944 | 0 | National Partners |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15691.2944 | 0 | 0 | 7691.2944 | 8000 | 0 | Overall target: Series of events, symposia, to share best practices on topics related to KM and specificied three project areas. Progress: Two symposium organized (in Morocco and Moldova in 2019) on different topics related to project areas. Plan 2020: At least one national symposia organized by national partners. AA time is part of activity 0.1 coordination. COVID-19 Impact: No impact is expected on this activity.
| 3.3 | Development and dissemination of knowledge products |  |  |  |  | AA | Community of Practice members, suppliers | Communication material including briefs, videos, print materials, visualizations of developed knowledge products. Newsletters. | Knowledge products | All Counties | 7 | 30 | 7 | 25091.2944 | 2200 | National Partners |  |  | 2200 | 0 | 0 | 0 | 0 | 2200 | 22891.2944 | 0 | 0 | 7691.2944 | 13000 | 2200 | Overall target: Packaging stakeholder knowledge into accessible products: infographics, booklets, short promo video-infographics, courses. Progress: Total of 7 key products generated by ICARDA and implementing partners out of 62 created overall, including reports, presentations, information and communication products. Plan 2020: Newsletters; at least 7 communication products originating from stakeholder knowledge base. AA time is part of activity 0.1 coordination. COVID-19 Impact: No impact is expected on this activity.
[12 empty] | Subtotal direct cost |  |  | 407563.69 | 81520 |  | 30750 |  | 109225.9735 | 19721.0735 | 27675 | 45000 | 0 | 16829.9 | 298337.7165 | 27878.0665 | 75675 | 80418.8833 | 101166.6667 | 13199.1
[12 empty] | Programme suport cost (8%) |  |  | 32605.0952 |  |  |  |  | 8738.0779 | 1577.6859 | 2214 | 3600 | 0 | 1346.392 | 23867.0173 | 2230.2453 | 6054 | 6433.5107 | 8093.3333 | 1055.928
[12 empty] | 2% CSP |  |  | 8979.4432 |  |  |  |  | 2406.4666 | 434.4947 | 609.7356 | 991.44 | 0 | 370.7964 | 6572.9766 | 614.2096 | 1667.2716 | 1771.7888 | 2228.904 | 290.8026
[12 empty] | Total |  |  | 449148.2284 |  |  |  |  | 120370.518 | 21733.2541 | 30498.7356 | 49591.44 | 0 | 18547.0884 | 328777.7104 | 30722.5214 | 83396.2716 | 88624.1828 | 111488.904 | 14545.8306
[12 empty] | Budget potentially affected by COVID-19 |  |  | 160804.836 |  |  | 35.8% | [15 empty] | 103000
22.93%