## Operation plan 2014
Operational Work Plan for Valuation of Ecosystem Services for Improving Agricultural Water Management in Kazakhstan, year 2014
# | Activities | Outputs | Coordination | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Resources /Staff/Support
I | Baseline assessment | Data Base (GIZ/RS and MS Excel), stakeholder maps, inputs to SWAT model | Iskandar Abdullaev | [12 empty] | Field coordinator, MSc students, travel, interviews | bar: 6 to 12
I.1 | Agricultural assessment | crop yields, inputs, productivities | Anna Inozemtseva | bar: 7 to 8
I.2 | Irrigation assessment | water application, efficiency, irrigation, irrigation methods, inflow, out flow | bar: 7 to 8
I.3 | Biophysical assessment | soils, water quality, ET and other bio-physical inputs to the SWAT model | bar: 7 to 8; 11
I.4 | Drivers of water use | Positive/perverse incentives, regulations and other features affecting land and water uses | Iskandar Abdullaev | bar: 7 to 8; 11
I.5 | Socio-economic assessment | stakeholder maps, demographic information, industries, gender | Ludmilla Kiktenko | bar: 8
I.6 | Environmental assessment | state of the environment, indicators, environmental services | Simon Charre | [12 empty] | Field coordinator (data), MSc student on ES, interviews | bar: 6 to 8; 11
I.7 | Data Base for SWAT and CAREC Knowledge | data collected and systematized for further use and application | Alexey Kobzev | [12 empty] | Coordination with other staff systemization of data in SWAT-compatible formats | bar: 11 to 12
II | Stakeholders and Gender | Stakeholder maps, gender aspects of water and environmental management, institutional arrangements for stakeholder involvement | Ludmilla Kiktenko | bar: 7 to 11
II.1 | Stakeholder mapping, roles and types, institutional arrangements for stakeholder participation | stakeholder map and events with stakeholders | Ludmilla Kiktenko | bar: 7 to 8
II.2 | Gender component in water and environmental management | Concept on inclusion of gender issues into the water, environmental management | Ludmilla Kiktenko | bar: 8; 11
III | Capacity Building and Education |  | Iskandar Abdullaev | bar: 7 to 12
III.1 | Training for CAREC staff | Training on GIS/RS and SWAT modeling | Iskandar Abdullaev
III.2 | MSc research | 2 MSc studies | Iskandar Abdullaev | bar: 7 to 8; 11 to 12
IV | Overall Project Coordination |  | Simon Charre | bar: 6 to 12

## Operation Plan 2015
Operational Work Plan for Valuation of Ecosystem Services for Improving Agricultural Water Management in Kazakhstan, year 2014
# | Activities | Outputs | Coordination | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Resources /Staff/Support
I | Baseline assessment | Data Base (GIZ/RS and MS Excel), stakeholder maps, inputs to SWAT model | Iskandar Abdullaev | [12 empty] | Field coordinator, MSc students, travel, interviews | bar: 1 to 8
I.1 | Agricultural assessment | crop yields, inputs, productivities | Anna Inozemtseva | bar: 1 to 5
I.2 | Irrigation assessment | water application, efficiency, irrigation, irrigation methods, inflow, out flow | bar: 1 to 5
I.3 | Biophysical assessment | soils, water quality, ET and other bio-physical inputs to the SWAT model | bar: 1 to 3
I.4 | Drivers of water use | Positive/perverse incentives, regulations and other features affecting land and water uses | Iskandar Abdullaev | bar: 1 to 5
I.5 | Socio-economic assessment | stakeholder maps, demographic information, industries, gender | Ludmilla Kiktenko | bar: 1 to 5
I.6 | Environmental assessment | state of the environment, indicators, environmental services | Simon Charre | [12 empty] | Field coordinator (data), MSc student on ES, interviews | bar: 1 to 5
I.7 | Creation of the SWAT database | data collected and systematized for further use and application | Alexey Kobzev | [12 empty] | Coordination with other staff systemization of data in SWAT-compatible formats | bar: 1 to 5
I.8 | Creation of the InVEST database | data collected and systematized for further use and application | Alexey Kobzev | bar: 1 to 8
II | Stakeholders and Gender | Stakeholder mapping, gender aspects of water and environmental management, institutional arrangements for stakeholder involvement | Ludmilla Kiktenko | bar: 1 to 8
II.1 | Stakeholder mapping, roles and types, institutional arrangements for stakeholder participation | stakeholder mapping and events with stakeholders | Ludmilla Kiktenko | bar: 1 to 5
II.2 | Gender component in water and environmental management | Concept on inclusion of gender issues into the water, environmental management | Ludmilla Kiktenko | bar: 1 to 8
III | Capacity Building and Education |  | Iskandar Abdullaev
III.1 | Training for CAREC staff | Training on InVEST modeling | Iskandar Abdullaev | bar: 2
III.2 | MSc research | 2 MSc studies | Iskandar Abdullaev
IV | SWAT and InVEST modeling and scenarios | modeling of water use scenarios, environmental services, climate impact | Simon Charre | bar: 3 to 9
IV.1 | Development of water use scenarios | different water scenarios | Iskandar Abdullaev, Simon Charre | [12 empty] | staff time, field visits, data base, MSc students, farmer days | bar: 3 to 8
IV.2 | Environmental services under different water management and climate change scenarios | Impact of different water management + climate change scenarios on ES | Simon Charre, Anna Inozemtseva | bar: 3 to 9
V | Improving Water Management and Environmental Services | Policy options, technologies and learning for improved water management and ES | Simon Charre and Iskandar Abdullaev | bar: 4 to 11
V.1 | Enhancing role of women in water and environmental management | institutional, organizational options and incentives for woman's participation in water and environmental management | Ludmilla Kiktenko | [12 empty] | Include demonstration days | bar: 4 to 10
V.2 | Water saving, water productivity improvements in irrigated agriculture | technologies, methods for water saving, improving irrigation methods, water use efficiency and irrigation planning and crop management in irrigated agriculture | Anna Inozemtseva | [12 empty] | Include demonstration days | bar: 4 to 10
V.3 | Incentive based mechanisms for ES | economic, financial and management options to improve types, accessibility, sustainability of environmental services in rural areas | Simon Charre | bar: 9 to 11
VI | Improved Policy Making, up scaling and synergies with other projects | policy messages, up scaling road map, synergies and cooperation with other projects | Simon Charre and Iskandar Abdullaev
IV.2 | Development of a policy brief on water and land management for increasing ecosystem services provision | political support and will for the project findings and uptakes | Iskandar Abdullaev, Anna Inozemtseva, Simon Charre | bar: 10 to 12
VI.3 | Finalization of project results, planning of next steps |  | Simon Charre and Iskandar Abdullaev | bar: 11 to 12