## Sheet1
IFAD-ICARDA Project: Annual Work Plan, 2016 (Year-1) (May 2016 - Aug 2017)
Project Title:
Enhancing food and nutritional security, and improved livelihoods through intensification of rice-fallow system with pulse crops in South Asia
Program Countries: Bangladesh. India and Nepal
Project Duration: 48 months (May 2016 to May 2020)
Overall Goal:
To establish a sustainable integrated pulse production system in rice fallows to enhance pulse production and farm income directly of nearly 15,000 farmers in India, Nepal and Bangladesh resulting in food and nutritional security of more than 75,000 farm families
Specific Objective:
Development and testing of cropping systems and agro-technologies for improved production and productivity of lentil, grasspea and chickpea as second crop in rice- fallows for improved food and nutrition security, farm income and soil health
Output-1: Germplasm identification
Output-2: Out-scaling of technologies
# | Activities and sub-activities | ('000$)
1 | Project launching workshop involving stakeholders and donor; Inception report
i. | Project launching workshop; Inception report (detailing project partner wise activities and responsibility planning), finalization and approval of annual work plan | 25
2 | Develop Crop suitability maps using new GIS technologies
i. | Geo-informatics (very high resolution imaging) applications for characterization of rice fallows; mapping of crop suitability, soil type and fertility, soil moisture retention after rice harvest and other bio-physical parameters; feasibility plans for crop intensification in rice fallows; interface tool for national actors/policy makers/farmers to measure technology adoption | 28
3 | Conduct Baseline studies, PRA, selection of districts, blocks, villages and farmers, and End line
i. | Partner level assessment and final selection of districts, blocks, villages, farmers | 18
ii. | PRA, Baseline study and Pulses value chain (project indicator and gender disaggregated study) | 27
iii. | Endline assessment (last quarter in last year) | 0
4 | Cluster demonstrations in selected villages through IPs
i. | Establishment of innovation platforms (3 IPs in Bangladesh (Rajshahi, Satkhira, Khulna); 2 in Nepal (Banke, Badia) and 3 in India (Raipur, Birbhum, Jajpur) [validate and disseminate improved varieties and production technologies; information exchange hub] | 216
ii. | Farmer participatory cluster demonstration (8-10 ha) for varieties and technologies in IP's and farmers' fields (varieties, improved crop production technologies and mechanization- demonstrated in compact clusters of 8-10 hectares mostly in IP's) | 94
5 | Selection of genetic materials, introgression, and multi-location trials
i. | Genotype mapping of Lentil, grasspea and chickpea (available and wild cultivars/varieties); | 27
ii. | Performance evaluation of available and wild cultivars (existing/new varieties involving wild, local elites, and varieties of state dept., university, ICARDA etc.) for selection of 5-6 suitable early maturing germplasm each of lentil, chickpea and grasspea for screening and genetic fixing at ICARDA RP | 45
iii. | Climate adaptation modeling and screening of suitable new early maturing germplasm of lentil, chickpea and grasspea through initial selection at ICARDA Research Platform at Amlaha (India) (through conventional and molecular breeding approaches, Trait specific (early maturing, disease and pest resistance, drought tolerance, suitability to mechanical harvest, herbicide tolerance) germplasms will be identified through FIGS) | 30
iv. | Seed multiplication of selected germplasms (supply seeds of these newly constructed genotypes for local adaptation trials in multi-location project sites by project partners to select appropriate cultivars) | 40
v. | Improved varieties of lentil, chickpea and grasspea varieties trial in small-holder farmers in rice- fallow cropping systems | 60
6 | Training of Trainers, Farmers, Women and Youths, Workshops, Policy Advocacy
i. | Training and capacity building of farmers, youths and women on various project aspects (pulse production technology, value addition, post-harvest, market linkage) | 45
ii. | Workshop on sharing findings with NARS and other partners on genotypic expression and performance in multi-location trials | 15
iii. | Seed System, up-scaling/ out-scaling of varieties and technologies - sharing with policy makers and NARS partners (involving department/ degree scholars/ NGOs) | 13
iv. | Post-graduate degree programs for orientation in the program processes (at least 35% female students) | 25
v. | Exposure visits for farmers, women, youth and other policy makers | 28
7 | VBSE development and pulses seed multiplication
i. | Establishment of VBSEs (80-100 VBSE formation, handholding and support) and seed multiplication of farmers' preferred varieties | 70
8 | Publication of posters/ Flyers/ Booklets in English and local languages
i. | Publication of posters/flyers/booklets in English and local languages; research publications | 8
9 | Annual evaluation, review workshops & steering committee meeting
i. | Monitoring of project activities by the Steering Committee (SC) (project goal, project activities, project outputs, scaling out and outcomes/impact as depicted in Project Impact Pathway) | 25
ii. | Half yearly and annual evaluation, review and planning meeting | 27
iii. | Project management and support | 24
iv. | Mid-term evaluation (first quarter of second year) | 0
v. | Independent final evaluation (last year) | 0
10 | Adoption and Impact studies
i. | Assessing utility and profitability of weed control through herbicides and mechanical harvesting of legumes and their implications on reducing drudgery of women | 10
ii. | Assessments of technology impacts differentiated by gender; and women farmers and women headed households | 22
Total |  | 922