PROGRESS REPORT

Enhanced small-holder wheat-legume cropping systems to improve food security under changing climate in the drylands of West Asia and North Africa

Grant Number: COFIN-ECG-56-ICARDA

Period: 1 January 2011 - March 2013

| Algeria | Egypt | Jordan | Lebanon | Morocco | Sudan | Tunisia | Turkey |
| --- | --- | --- | --- | --- | --- | --- | --- |

March 2013

#### Acknowledgements

ICARDA is grateful to the European Union and the International Fund for Agricultural Development for the generous financial support and technical backstopping provided to this project.

Gratitude is also expressed to the NARS’ Management, National Coordinators, and all scientists and technicians for the dedication and the painstaking work they provided during the last months. This ensured a good start for the dissemination activities targeting mainly small-holder farmers. The support and help of the ICARDA Management, Programs, Units, scientists, and technicians has been crucial, instrumental in the successes to date, and highly appreciated.

Contents

Executive summary	4

1.Introduction and grant background	11

2. Grant goal, objectives, and target groups	11

3. Changes in the grant implementation context and grant design which have occurred during the reporting period	11

4. NARS institutions executing the project	12

5. Sites selection and description	12

6.Progress and performance by component	23

7. Progress towards component objectives	62

8. Use of communication tools and innovative approaches	63

9. Participatory development and evaluation of best-bet technology options	64

10. Links, if any, with other IFAD-supported activities and/or other partners	65

11. Lessons learned and knowledge shared	65

12. Dissemination activities and farmer’s involvement	66

13. Gender mainstreaming	66

14. Publications	67

15. Backstopping to the countries	67

16. Meetings	67

17. Shortcomings and problems encountered in grant implementation and actions suggested	68

18. Other events and relevant issues during the reporting period	68

## Executive summary

Food security of the West Asia and North Africa (WANA) region countries is very closely related to cereal and food legume production; the most important annual crops in many countries of the region. Nowadays most of the countries of this region are unable to cover their needs from domestic production and depend, therefore, on food imports to different degrees, making them the most import-dependent countries in the developing world. The potential to increase the yields of staple crops is important, particularly at the level of small-holder farmers, the major contributors to production. Actual farm yields of crops in the region are far below their potential. Adapted varieties and associated technologies, which will enable farmers in the dry areas to take full advantage of the cereal-food legume rotations to increase productivity and sustain their wheat-based production systems and adapt to climate change and variability, are being developed. However, most of these technologies are not well known or widely used.

The overall goal of the project is to contribute to food security in the WANA region in an environment of increasing climate variability by improving the productivity and production of wheat-legume based cropping systems. These improvements can be achieved by

- Promoting proven and tested technologies for wheat-legume rotation systems

- Scaling out existing improved wheat and food legume varieties and their associated production technologies (supplemental irrigation, introduction of new conservation agriculture technologies in wheat-legume rotation systems, and improved seed delivery systems)

Concurrently identifying and testing appropriate new technologies to sustainably improve productivity and production constitute the first specific objective of the project. The second specific objective is related to further development and demonstration of new varieties that are higher yielding and better adapted to both biotic and abiotic stresses. This second objective includes integrated pest management (IPM) of key diseases, insect pests, and parasitic weeds which have a demonstrated wide range of hosts in farmers’ fields. Also included is improved crop and soil water management, including the use of supplemental irrigation, in order to respond to such new challenges and constraints as climate changes. The use of geographic information systems (GIS) and geo-statistics for the spatial analysis of disease and pest distributions is considered.

Implementation of on-farm activities with the National Agricultural Research Systems (NARS) could not start before the 2012/13 cropping season because of a delay in signing the grant contract (signed only in July 2012) and the disbursement of the funds. The on-farm demonstrations started in the 2012/13 cropping season in eight countries.

The NARS institutions involved in the dissemination of the research results and the implementation of the project activities are ITGC (Algeria), ARC/FCRI (Egypt), NCARE (Jordan), LARI (Lebanon), INRA (Morocco), ARCo (Sudan), INRAT (Tunisia) and GAP ARI Sanliurfa Institute (Turkey). In the latter two countries other institutions are also involved.

In Morocco the project activities are implemented in the Rabat-Salé-Zemmour-Zaer region and in Lebanon they are implemented in the Beqaa plain. In the others countries the activities are distributed in more than one region to ensure rapid diffusion of the technologies developed.

The project areas are extremely diverse as regards climate and soil structure, annual rainfall averages from almost none to more than 700 mm, and there are high variations in temperature.

The first objective concerns promotion of proven and tested technologies for wheat-legume rotation systems, by scaling out existing improved wheat and food legume varieties and their associated production technologies. Various outcomes have to be mentioned as regards the testing the new varieties of wheat and food legumes. Indeed several varieties of wheat (durum and bread) and food legumes (faba bean, chickpea, and lentil) were released during the last period in the countries involved in the project. Forty two varieties of wheat and food legumes, originating from the National Programs and CGIAR centers (ICARDA and CIMMYT), have been released and forty three varieties have been submitted for release in Algeria, Egypt, Lebanon, Morocco, Tunisia, and Turkey during the period 2010-2012. Most of the released varieties (88%) are wheat and chickpea. The main characteristics of these varieties are that they have high yield potential and resistance or tolerance to one or more biotic and abiotic stresses prevailing in the WANA region that cause important yield losses. More emphasis should be given to the release of faba bean and lentil varieties. Some countries (Turkey, Lebanon, and Algeria) have been more active in releasing varieties during the last three years. Most of the varieties released carry different resistance/tolerance and are high yielding.

Although the involvement of the NARS in the project started after some delay, several activities have been undertaken with farmers, such as popularization of the new wheat and food legume varieties and testing conservation agriculture, supplemental irrigation, and IPM in farmers’ fields.

Since the 2012/13 cropping season is not completed in most countries – only in Egypt and Sudan – it is possible only to have an idea about the expected performance of the packages tested.

In Egypt, the superiority of the introduced Orobanche tolerant varieties (Misr 3 and Giza 843) is clearly visible mainly in fields infested with Orobanche; farmers using these varieties have experienced increased yields as compared to neighboring farmers using susceptible varieties. The high demand to test the new resistant genotypes confirmed the regeneration of interest in growing faba bean in Orobanche infested regions. Participants in the field day organized in Zakazik district (Sharkia Governorate) on 5 March 2013, in the presence of members of the Steering Committee, noticed the high performance of Giza 843. While this had been sowed at low density (75 kg/ha) the yield was expected to be higher than 4.5 t/ha. By reducing the seeding rate, the variety can be disseminated more rapidly and therefore can reach the maximum number of farmers in fewer years. The low seeding density and early sowing (late October or early November) of other improved varieties (Misr 3, Nubaria 2, Nubaria 3, and Sakha 4) resulted in good performances in other regions.

Similar activities to popularize recently released varieties of wheat and food legumes were conducted also in Algeria, Jordan, Lebanon, Sudan, Tunisia, and Turkey. It is expected that through the on-farm demonstrations, field days, and media coverage farmers will be made aware of the latest achievements of the new varieties and their associated production technologies.

The project is supporting the seed increase of the recently released varieties to facilitate their development and consolidate the national efforts in the diffusion of new technologies. Figures from some of the countries involved in the project show increases in demand for the seed of these varieties. Farmers want to replace the old varieties and thus contribute to improving the food security status of the region.

Other initiatives (mainly on wheat) in other countries are also contributing in the development of new varieties through the support of national funds or regional projects (for example the ‘Enhanced food security in Arab countries’ project). These initiatives will thus increase the use of the different wheat varieties (for example, Maali and Nasr in Tunisia and Mikki3 and Icarasha in Lebanon).

Furthermore the project has considered the involvement of farmers in the process of evaluating promising lines with breeders to select and propose the best ones for release, facilitating the later adoption of the varieties.

The project is facilitating discussion involving all stakeholders to identify the major constraints to the adoption by farmers of the improved technologies identified and obtain feedback relating to technology development and the adaptive research program. ICARDA and the NARS scientists have done surveys and collected data to help identify the emergent problems that farmers are facing (both technical and socioeconomic). Seed production chains for some crops in Morocco and other North Africa countries show weakness that are not helping farmers to benefit from the important achievements in variety development. An important need for capacity development for seed production and technology has been identified; mainly in the characterization and maintenance of the varieties and breeding. Therefore, courses on wheat breeding using classical and molecular tools, food legume breeding courses, seed science and technology, and variety maintenance have been or will be held in 2013. Scientists from the NARS participating in these courses are called upon and encouraged to conduct in-country courses for their farmers, primarily on seed production and maintenance.

The national coordinators are starting to identify groups of farmers willing to develop an informal seed production system for a small community and help them improve the quality of the seeds being used. The project will help by acquiring small units for seed cleaning and treatment for a small organized group.

Conservation agriculture (CA) constitutes one of the technologies that should be promoted to address the effect of climate changes and improve the fertility of the soil. Nowadays, this technology is becoming widespread in many of the countries involved in the project. In Morocco, progress has been achieved in using direct seeding for lentil crops during the 2012/13 cropping season; 500 ha are under cultivation in the Rabat-Salé-Zemmour-Zaer region. In Tunisia, the area under CA is estimated to be 12,000 ha and this potentially can be increased. In Egypt, CA also has potential to contribute to minimizing the infestations of Orobanche on faba bean sowed after rice. Two on-farm demonstrations were undertaken in 2012/13 with faba bean. The reduced costs – mainly a result of direct seeding machines being made available at lower prices – and the increase in fuel prices in many non-producer oil countries have encouraged policy makers in the region to pay more attention to this technique, particularly following the encouraging results achieve in the different trials on different crops. During the 2012/13 cropping season, Algeria, Egypt, Jordan, Lebanon, Morocco, and Tunisia conducted on-farm demonstrations of CA for wheat, faba bean, chickpea, and/or lentil. Field days are planned across the cropping season in the different countries to highlight the beneficial effect of CA. Collaboration with other projects operating in the region – these would be primarily the International Fund for Agricultural Development (IFAD) and International Center for Interdisciplinary and Advanced Research (ICIAR) projects operating in some countries of the region – is encouraged in order to organize joint dissemination activities.

Supplemental irrigation is one of the technologies that contribute to stabilizing the production of wheat. It has been implemented in several trials and on-farm demonstrations with wheat in 2012/13 in some of the countries involved in the project.

The preliminary investigation from the wheat and food legumes baseline and variety adoption surveys and constraints analyses conducted during the 2011/12 season in Morocco, indicated that the food security strategy in Morocco is based on pragmatic policies that promote self-reliance agriculture and permit food imports to compensate for structural deficits. However, two main challenges are facing food security in Morocco – the needs of a rapidly growing population and alleviation of climate change impacts.

Cereals are a strategic food in Morocco where per capita consumption is 210 kg. The national production covers, on average, less than 70% of the population’s needs. Wheat production remained unchanged during the 1960s and 1970s and increased in the 1980s as a result of the release of new improved bread and durum wheat cultivars. The release of these cultivars improved yields and triggered a series of policy actions from the government. The most important ones were related to the evaluation of the breeding programs, the upgrade of seed processing activities, and promotion of large-scale demonstrations of new cultivars. However, the breeding efforts alone have not been sufficient to bridge the gap between the actual production and the potentialities of the country.

Gender analysis was initiated in Morocco in 2012 and in Egypt in 2013 using national collaborators. The lack of sufficient gender integration in local community development initiatives is a design flaw which could result in the failure of such initiatives. This research focused on the level of men’s and women’s participation in social research using participatory research tools and the way they see the usefulness of the results generated by participatory research. The questions raised were concerned with how men and women reacted to the participatory research tools used, what was the level of difficulties they experienced, and how did they assess the usefulness of the results generated by the participatory tools.

Concerning gender inequality in the context of climate change, the research addresses gender and vulnerability to climate change impacts on water availability in north-east Morocco. This arid and semi-arid region has already experienced several droughts and erratic rainfall in the past, leading not only to environmental degradation – including soil erosion – but also social and economic impacts affecting local livelihoods. The research provides a detailed description of the gender division of roles and tasks in this remote conservative rural society.

Examination of the effects of changes in climate and water resources on gender inequality resulted in an attempt, using a case studies approach, to analyze why women are more vulnerable to environmental risks to agriculture and livelihoods and how these affect gender relations. The case studies provided powerful empirical evidence that represent how gender roles are perceived and practiced in the target areas.

This work documents the call that for any agricultural effort seeking to benefit both men and women in Morocco; gender equality is a precondition and it needs to be understood in its complex, real, and dynamic life situations.

The ripple effects of the social and gender analysis research process was also studied, together with a review of reflections on participatory gender research carried out in Morocco. The results recognize that participatory research is the start of a change process.

A socioeconomic analysis of productivity trends and gaps in wheat and food legume based systems in Morocco, showed that the high international commodity prices of recent years (especially for wheat) and their negative impact on trade balances have created a strong incentive for Moroccan policy decision-makers to enhance food security in order to reduce dependency on imported commodities.

Under the second objective, concerning the development of new germplasm and production technologies to cope with climate change, several expected outputs/outcomes have been developed.

New wheat and food legume genotypes, better adapted to climate variability and change, have to be developed. Therefore, the breeding programs conducted at ICARDA continue to introduce all available sources of resistance or tolerance to the main identified biotic and abiotic stresses and grain quality traits into high yielding genetic backgrounds through hybridization to select and develop high yielding multiple stress-tolerant/resistant lines with higher quality. A major effort was undertaken to screen new collection of wheat and food legumes (cultivated and wild relatives) to identify new sources of resistance and tolerance to different biotic and abiotic stresses for the purpose of broadening the genetic basis of resistance. Many new sources of resistance, either in the cultivated species or in wild relatives, have been identified for different biotic and abiotic stresses. More than 2000 new crosses are done annually in the wheat breeding program and more than 600 in the food legume breeding program.

Each year, ICARDA is proposing to the NARS hundreds of new improved high yielding lines of wheat (bread and durum) and food legumes (faba bean, chickpea, and lentil) carrying resistance to more than one pathogen/pest and tolerating drought, cold, and salinity. The proposed material was selected and tested in different environments through the collaboration that the Center has established with its NARS partners. The advanced lines proposed in the different nurseries distributed to the NARS will allow an increase in the number of released varieties in the region. These new releases will have a better performance than those already grown and it is expected their rate of adoption, to replace the old generation varieties still grown widely in the region, will increase. Farmers in the region will take advantage of this material to reduce their costs of production and reduce the risk of losing their harvests to the different stresses that they are facing.

Several collaborators in the project region benefit from the ICARDA’s nurseries for wheat and food legumes. In the 11 countries (Algeria, Egypt, Iraq, Jordan, Lebanon, Libya, Morocco, Syria, Sudan, Tunisia, and Turkey) involved in the project there were 45 collaborators in 2011 and 39 in 2012.

Consolidate the interaction between ICARDA and NARS breeders and associate farmers in the process of final evaluation will help in identifying superior and desirable genotypes and improve the adoption of the released varieties. The project is encouraging and supporting this interaction through activities implemented in the different countries, mainly those conducted in farmers’ fields. In 2012/13, the wheat program sowed large plots of many advanced and promising lines in Merchouch (Morocco), Sids (Egypt), and Terbol (Lebanon) for the purpose of participatory selection by national breeders and farmers.

The project is consolidating the presence of food legumes in the rotation and developing a sustainable wheat-legume rotation system. For that, the project is conducting on-farm demonstrations to highlight the beneficial effects of introducing legume crops into the cropping system. The Tunisian team chose to demonstrate the positive effects of growing faba bean in the wheat system to farmers in the Kef region. Farmers in this region either grow a monoculture of cereals (wheat), wheat-barley or oat, or wheat after fallow. The use of the faba bean variety Bachaar in this semi-arid region is appropriate since it can tolerate drought better than others.

In Egypt, a national campaign to reintroduce faba bean into the cropping system in the traditional faba bean growing area is enhanced in 2012/13. The new package is based on the use of faba bean varieties tolerant to Orobanche. A low dose of glyphosate and planting at a low seed density allows farmers to minimize the yield losses arising from Orobanche and foliar diseases and improve the profitability of the crop. Many farmers requested seeds of the tolerant varieties to adopt this package and reintroduce the faba bean into the cropping system. In Jordan, the wheat-chickpea rotation is promoted through the project. In Algeria, lentil and chickpea crops are introduced into a cereal monoculture system and in wheat-fallow to improve the productivity of wheat and the soil fertility. Support is given to the use of certified seeds of grain legumes.

Several IPM packages conducted in different countries at on-farm demonstrations in the 2012/13 cropping season consolidate the wheat-legume rotation for a sustainable crop production and improved food security. The IPM are designed to control Ascochyta blight on chickpea and faba bean, Orobanche on faba bean, Fusarium wilt on chickpea, root rot on chickpea, foot rot on durum wheat, and weeds on wheat.

Surveys of wheat and food legume diseases were undertaken in Morocco during the 2011/12 cropping season and disease and insect suitability maps were developed. The incidence of chocolate spot on faba bean varied from low to high incidence in different areas of Morocco.

The work on GIS and remote sensing will focus on the area of Marchouch (Morocco) and Fernana (Tunisia) in 2012/13 for disease and pest assessment and yield prediction.

The capacity building targets the reinforcement of the national programs in the breeding of wheat and food legumes using either classical methods or molecular tools, including production of doubled haploid and marker assisted selection. Seed production and variety description and maintenance are considered thoroughly in the capacity development program.

A plan to train young scientists and technicians has been established with the NARS and is being executed. The gender issue is considered in this training.

Progress in the work plan can be seen in the better genetic material proposed to the NARS for the different crops to address resistance to disease and pests, tolerance to heat, cold, drought, and salinity, and grain quality. The multiple stress resistant/tolerant varieties developed will allow small-holder farmers to grow wheat and food legumes with lower costs and improve their incomes through better yields; thus contributing to an improvement in the food security status in the region and the world, and preserving the environment. Also significant progress has been achieved in variety releases, mainly for wheat (durum and bread). However the process of releasing food legumes is still slow and few varieties have been released in many countries involved in the project. The reason for this could be a lack of human resources working on food legume breeding in the NARS institutions and a lack of adaptation of the proposed materials to the different growth conditions. Food legume researchers at ICARDA are working to establish a close collaboration with some NARS food legume breeding programs to select and develop more preferred and adapted lines and solve the many constraints facing food legume crops in the Central and West Asia and North Africa (CWANA) region.

The implementation of on-farm activities (i.e. variety popularization, CA, supplemental irrigation, IPM) specific to the project in the countries involved and also of the activities associated with the NARS (baseline studies, seed sector studies, and so on) started only in the 2012/13 cropping season because of the long time taken to sign the project grant.

Farmers have access to information about wheat and food legumes crops through different channels. In some countries the telecommunication tools (such as internet and SMS) are routinely being used to access information, but this is generally confined to medium- or large-scale farmers. Traditional extension with direct contact between farmers and extension agents is still operational in most of the countries. Some countries invested more in communication with farmer by developing agriculture TV channels (Egypt) or newspapers specializing in agriculture. These can be used to promote the new technologies in the wheat-food legume system. SMS is well used in Tunisia and Turkey to communicate awareness messages to farmers.

The NARS are disseminating the information through field days and farmers’ field schools.

This project has established links with the ‘Enhancing food security in Arab countries’ project in the countries where both are conducting activities. This is particularly so, in Egypt, Jordan, and Tunisia where some of the on-farm activities are conducted at the same sites. The regional coordinator of the ‘Enhancing food legume in Arab countries’ project participated in the coordination meeting of the EU-IFAD project, held in Amman (Jordan), 12-13 December 2012. Furthermore, the project is connected to the CGIAR Funds programs, particularly CRP3.1 (Wheat) and CRP3.5 (Grain legumes).

During the last Steering Committee meeting held in Egypt on 4 March 2013, the Director Generals of the NARS and the ICARDA management agreed to request a no-cost extension for 20 months to ensure three cropping seasons of work with farmers for better impact and to ensure the success of the project.

# Introduction and grant background

Cereals and food legumes are the most important annual crops in the WANA region. Both are considered basic elements for population nutrition. The WANA countries’ food security depends on their capacity to produce cereals and food legumes. Nowadays most of the countries of this region are not able to cover their needs from domestic production and depend therefore on food imports to different degrees. This makes them the most import-dependent countries in the developing world. The potential to increase the yields of staple crops is important mainly at the level of small-holder farmers, the major contributors to production. Actual farm yields of crops in the region are far below their potential. ICARDA and its partners in WANA are developing adapted varieties and associated technologies that will enable farmers in the dry areas to take full advantage of cereal-food legume rotations to increase productivity, sustain their wheat-based production systems, and adapt to climate change and variability; however, most of these technologies are misused.

# 2. Grant goal, objectives, and target groups

The overall goal of the project is to contribute to food security in the WANA region in an environment of increasing climate variability by improving the productivity and production of wheat-legume based cropping systems.

The specific objectives are summarized below.

Specific Objective 1: Promotion of proven and tested technologies for wheat-legume rotation systems by scaling out existing improved wheat and food legume varieties and their associated production technologies (supplemental irrigation, introduction of new CA technologies in wheat-legume rotation systems, and improved seed delivery systems). Concurrently, appropriate new technologies to sustainably improve productivity and production are being identified and tested.

Specific Objective 2: In response to new challenges and constraints, such as climate change, further development and demonstration of new varieties, which are higher yielding and adapted to both biotic and abiotic stresses, are required. The use of these new varieties will be combined with IPM for key diseases, insect pests, and parasitic weeds which have a wide range of hosts in farmers’ fields. Improved crop and soil water management, including the use of supplemental irrigation, GIS, and geo-statistics will be used for a spatial analysis of the distribution of diseases and pests. The economic impacts of diseases will be evaluated.

The intended beneficiaries are wheat and legume producers throughout the region. Farmers and communities in the program’s target locations and on-farm testing sites are expected to make immediate use of the new technologies. In the lowland coastal areas of WANA, the target lead NARS include Egypt, Morocco, Tunisia, Syria, and Sudan. For the continental areas of the region, the target NARS include Algeria, Lebanon, Morocco, Syria, and Turkey. For the high-altitude areas, the target NARS are Iraq, Jordan, Libya, and countries of the Arabian Peninsula, such as Yemen.

# 3. Changes in the grant implementation context and grant design which have occurred during the reporting period

Implementation of the on-farm activities with the NARS could not start before the cropping season 2012/13 because of the delay in signing the grant contract (signed in July 2012) and in the disbursement of funds by the donor. The on-farm demonstrations started in the 2012/13 cropping season in eight of the 12 countries mentioned in the document of the project.

Some countries used the project as an opportunity to promote recently released varieties of all the three food legume species (faba bean, chickpea, and lentil) and the appropriate technologies associated with their cultivation. Others focused on one or two legumes species.

# 4. NARS institutions executing the project

ICARDA executes the project with the direct involvement of the NARS institutions of eight countries (Algeria, Egypt, Jordan, Lebanon, Morocco, Sudan, Tunisia, and Turkey). The different national institutions involved in the project are presented in Table 1.

Table 1. List of national institutions and national coordinators responsible for the execution of the project

| Countries | Institutions coordinating the activities |
| --- | --- |
| Algeria | ITGC (Institut Techniques des Grandes Cultures) |
| Egypt | ARC (Agricultural Research Center) |
| Jordan | NCARE (National Center for Agricultural Research and Extension) |
| Lebanon | LARI (Lebanese Agricultural Research Institute) |
| Morocco | INRA (Institut National Recherche Agronomique) |
| Sudan | ARCo (Agricultural Research Corporation) |
| Tunisia | INRAT (Institut National Recherche Agronomique de Tunisie) |
| Turkey | GAP ARI (Southeastern Anatolia Regional Agricultural Research Institue, Sanliurfa) |

The lists of members of the steering committee, national coordinators, and NARS scientists and technicians involved in the project are shown in Annex B.

# 5. Sites selection and description

During the 2012/13 cropping season, activities under the direct responsibility of NARS were conducted in several regions of the eight countries involved (Algeria, Egypt, Jordan, Lebanon, Morocco, Sudan, Tunisia, and Turkey). Most of the countries chose to extend their field activities to cover the main production areas of wheat and food legumes. The following section presents a brief description of the most important selected sites and their main characteristics.

- Algeria

In the 2012/13 cropping season, the on-farm demonstrations were implemented in nine governorates (Constantine, two districts; Setif, two districts; Mila, three districts; Tiaret, two districts; Tissemsilt Blida, one district; Tlemcen, one district; Oum El Bouaghi, one district; and Ain Defla, one district). The main constraints to crop production are reported as low access to mechanization, low use of fertilizers because of their high cost, poor crop management, frost in the highlands, and an insufficient and irregular rainfall. The regions where the project is conducting on-farm activities can be described as follows:

Constantine Governorate, Didouche Mourad district: (Latitude 36°26'54.07"N, longitude 6°38'2.18"E; altitude 658 m; average rainfall 526 mm): The major cropping systems in the region are wheat (durum/bread)-food legume (chickpea, lentil, and faba bean), wheat-fallow, and wheat-wheat. The difference between potential and actual wheat yields is important – at ITGC the yield is 5.5 t/ha, while the farmers’ yields are 2.3 t/ha. The most frequently grown varieties are GTA dur and Cirta (durum wheat), HD 1220, and Ain Abid (bread wheat), Ghab 4 (chickpea), and Syrie 229 (lentil).

Constantine Governorate, Ain Smara district: (Latitude: 36°15'60.0"N, longitude: 6°30'0.0"E; altitude 684 m, average rainfall 526 mm): The major cropping systems in the region are wheat (durum/bread)-food legume (chickpea, lentil, and faba bean), wheat-fallow, and wheat-wheat. The difference between the potential wheat yield and farmers’ actual yields is almost the same as that in Didouche Mourad district. Also the same varieties are grown.

Setif Governorate, Guellal district: (Latitude 36° 2'42.93"N, longitude 5°19'40.43"E; altitude 1026 m; average rainfall 395 mm). The most common cropping system is wheat-fallow-horticulture. The difference between the potential wheat yield at ITGC (3.5 t/ha) and the farmers’ actual yields (1.3 t/ha) is also important. The most frequently grown varieties are GTA dur, Boussalem, and Waha (durum wheat), HD 1220 and Wifak (bread wheat), and Dahra (lentil).

Setif Governorate, Ain Amat district: (Latitude 36°10'60.00"N, longitude 5°18'60.00"E; altitude 1014 m; average rainfall 395 mm). The most common cropping system is wheat-fallow. The difference between the potential yield at ITGC and the farmers’ actual yields is the same as for the previous region. The most frequently grown varieties are also the same.

Mila Governorate, Ferdjioua district: (Latitude 36°24'26.46"N, longitude 5°57'5.54"E; altitude 863 m; average rainfall 514 mm). The commonest cropping systems in the region are wheat (durum/bread)-food legume (chickpea, lentil, and faba bean), wheat-fallow, and wheat-wheat. The difference between the potential wheat yield at ITGC (4.5 t/ha) and the farmers’ actual yields (1.9 t/ha) is important. The most frequently grown varieties are Vitron and Waha (durum wheat), Arz and Anza (bread wheat), Ghab 4 (chickpea), and Idleb 2 and Syrie 229 (lentil).

Mila Governorate, Sidi Khalifa district: (Latitude 36°21'36.00"N, longitude 6°17'24.00"E; altitude 960 m; average rainfall 526 mm). The most common cropping systems in the region are wheat (durum/bread)-food and feed legume (chickpea, lentil, faba bean, and vetch), wheat-fallow, and wheat-wheat. The difference between the potential yield at ITGC and farmers’ actual yields is the same as for the previous region. Also the same varieties are grown.

Mila Governorate, Mila district: (Latitude 36°27'1.00"N, longitude 6°15'52.00"E; altitude 476 m; average rainfall 526 mm). The most common cropping systems in the region are wheat (durum/bread)-food legume (chickpea, lentil, faba bean, and vetch), wheat-fallow, and wheat-wheat. The difference between the potential yield and farmers’ average yields is still important.

Tiaret Governorate, Mellakou district: (Latitude 36°24'26.46"N, longitude 5°57'5.54"E; altitude 858 m; average rainfall 333 mm). The most common cropping system in the region is wheat (durum/bread)-food legume-vegetables. The difference between the potential yield of wheat at ITGC (3.7 t/ha) and the farmers’ actual yields (1.5 t/ha) is important. The most frequently grown varieties are Vitron, Boussalem and Simeto (durum wheat), HD1220 and Ain Abid (bread wheat), FLIP84-92C (chickpea), and Syrie 229 (lentil).

Tiaret Governorate, Sebaine district: (Latitude 35°27'28.88"N, longitude 1°36'7.32"E; altitude 899 m; average rainfall 333 mm). The most common cropping system in the region is wheat (durum/bread)-food legume-vegetables (potatoes). The same varieties are grown as in the previous district.

Tissemsilt Governorate, Ammari district: (Latitude 35°34'21.32"N, longitude 1°44'3.77"E; altitude 916 m; average rainfall 364 mm). The most common cropping system in the region is wheat (durum/bread)-fallow/food legume-vegetables. The difference between the potential yield of wheat at ITGC (2.8 t/ha) and the farmers’ actual yields (1.5 t/ha) is quite important. The most frequently grown varieties are Ofanto, Simeto, and Vitron (durum wheat), HD1220 and Ain Abid (bread wheat), Ghab 4 (chickpea), and Syrie 229 (lentil).

Blida Governorate, Mouzaia district: (Latitude 36°28'0.00"N, longitude 2°40'60.00"E; altitude 115 m; average rainfall 608 mm). The most common cropping system in the region is wheat (durum/bread)-vegetables. The difference between the potential wheat yield at ITGC (4.3 t/ha) and the farmers’ actual yields (2.6 t/ha) is quite important. The most commonly grown varieties are Vitron (durum wheat), HD1220 (bread wheat), Ghab4 (chickpea), and Syrie 229 (lentil).

Tlemcen Governorate, Saf-Saf district: (Latitude 34°53'57"N, longitude 1°16'34"W; altitude 730 m; average rainfall 320 mm). The most common cropping system in the region is cereal-legume-vegetables. The difference between the potential yield of wheat at ITGC (2.6 t/ha) and farmers’ actual yields (1.3 t/ha) is quite important. The most frequently grown varieties are Ofanto, Vitron, and Waha (durum wheat), HD1220 and Arz (bread wheat), Flip84-92C and Ghab4 (chickpea), and Syrie 229 (lentil).

Oum El Bouaghi Governorate, Beriche district: (Latitude 35°54'60.00"N, longitude 7°22'60.00"E; altitude 893 m; average rainfall 351 mm). The most common cropping system in the region is wheat-barley. The difference between the potential yield of wheat at ITGC (2.2 t/ha) and farmers’ actual yields (1.2 t/ha) is quite important. The most frequently grown varieties are Waha and Boussalem (durum wheat) and Arz (bread wheat).

Ain Defla Governorate, Ain El Amra district: (Latitude 36°18'18.00"N, longitude 1°50'49.20"E; altitude 251 m; average rainfall 732 mm). The most common cropping system in the region is wheat (durum/bread)-vegetables (potatoes, lettuce/food legumes [pea and faba bean]). The difference between the potential yield of wheat at ITGC (4.3 t/ha) and farmers’ actual yields (2.8 t/ha) is quite important. The most frequently grown varieties are Ofanto, Simeto, Vitron, and Mexicali (durum wheat) and Aid Abid and Arz (bread wheat).

ITGC also conducted activities on the demonstration and seed production farms of ITGC (Oued Smar, El Khroub, Setif, Guelma, Tiaret, Sidi Bel Abbes, and Ain El Hjar). The activities were mainly those related to seed increase of newly released varieties and promising lines of wheat and food legumes, and verification trials.

- Egypt

In Egypt, five governorates were chosen to host the on-farm demonstrations of recently released faba bean varieties and IPM packages. The demonstration fields were located in Al-Sharkeia, Kafr-Al-Sheikh, Assiut, Dakahlia, and Beheira governorates.

Al-Sharkeia Governorate is one of the governorates of East Delta and extends between latitudes 30°10’ and 31°19’N and between longitudes 32°15’ and 32°25’E. The geographical location gives it a feature-rich environment, fertile soil, and mild weather which help the growth and quality of crops. It has various soil types – clay, silty, and sandy. Rainfall is concentrated in the winter and the annual average is no more than 50 mm. The cropping system at Al-Sharkeia is as follows:

    - Winter field crops are wheat, barley, forage crop; Egyptian clover (berseem), faba bean, lentil, chickpea, and green beans

- Summer field crops are maize, rice, cotton, peanut, sesame, and soybean

- Vegetables crops are tomatoes, watermelon, squash, cucumbers, eggplants, and peppers

- Fruits crops are mango, citrus, and grapes.

During the 2012/13 season the area cultivated with faba bean is 9781 feddan (4100 ha) and the average yield in this governorate ranged from 10-12 ardab/feddan (3.9-4.43 t/ha).

The main faba bean varieties in this governorate are Giza 843, Misr 1, Misr 3, Sakha 1, and Giza 3.

Kafr-Al-Sheikh Governorate is characterized by its unique geographical location. It lies in the northern part of the country. Its western boundary follows the western branch of the Nile in the Nile Delta and its northern boundary is the Mediterranean. The governorate experiences a Mediterranean climate. Average annual rainfall varies between 140 mm to 250 mm. Clay, silty, and sandy soils are found in Kafr-Al-Sheikh governorate.

The cropping system at Kafr Al-Sheikh is:

•	Winter field crops are wheat, barley, and sugar beet and the forage crops are Egyptian clover (berseem) and faba bean

•	Summer field crops are rice, maize, cotton, peanut, sesame, and soybean.

During the 2012/13 season the area cultivated with faba bean is 18683 feddan (7847 ha), with an average yield of 9-10 ardab/feddan (3.3-3.7 t/ha).

The main faba bean varieties grown in this governorate are Sakha 1, Sakha 2, Sakha 4, Giza 716, and Giza 843.

Assiut Governorate: is located at latitude 13°27’N and longitude 14°30’E. The climate is continental – cold in winter, hot in summer. The governorate is bordered to the north by Minya Governorate, to the south by Sohag Governorate, too the west by New Valley Governorate, and to the east by the Red Sea Governorate. The distance from Cairo is 375 km.

The cropping system at Assiut is:

•	Winter field crops are wheat, barley, and sugar beet, and forage crop are Egyptian clover (berseem) and faba bean

•	Summer field crops are sugar cane, maize, cotton, sorghum, peanut, sesame, and soybean.

The rainfall is very limited and the amount received is almost zero. The soil is clay to yellow to light sandy.

During the 2012/13 season the area cultivated with faba bean is 5193 feddan (2181 ha) and the average yield is 8.2 ardab/feddan (3.0 t/ha).

The main faba bean varieties in this governorate are Giza 843, Giza 3, Sakha 1, and Misr 1.

Dakahlia Governorate: is located in the northeast of the Delta, between latitudes 30°5’ and 31°5’N and at longitude 30°32’E. The annual average rainfall is 60 mm. The soil in this region is heavy clay to light sandy.

The cropping system at Dakahlia is:

•	Winter field crops are wheat, barley, and sugar beet and the forage crops are Egyptian clover (berseem), lentil, chickpea, and faba bean.

•	Summer field crops are maize, cotton, sorghum, peanut, sesame, and soybean.

During the 2012/13 season the area cultivated with faba bean is 7540 feddan (3167 ha) and the average yield is 9-10 ardab/feddan (3.3-3.7 t/ha).

The main faba bean varieties grown in this governorate are Giza 843, Giza 716, Giza 3, Sakha 1, and Sakha 3.

Beheira Governorate is located on the western side of the republic. It is bordered to the west by Alexandria and Matruh Governorates, to the south by Giza Governorate and Sadat City, and to the east by Kafr El-Sheikh, Gharbia, and Monufia Governorates. The soils are newly reclaimed desert areas (calcareous and sandy soils) and fertility is very poor because of the low levels of macro- and micronutrients and organic matter. Sprinkler and drip irrigation systems are used to irrigate field crops, vegetables, and fruit trees. The principal source of irrigation water for the whole area is the Nubaria canal. The annual average rainfall is between 120 and 200 mm.

The area allocated for faba bean is 22343 feddan (9384 ha) and the average yield is 13.4 ardab/feddan (4.9 t/ha).The main faba bean varieties grown in this governorate are Giza 716, Nubaria 1, Nubaria 2, Nubaria 3, Sakha 1, Misr 1, Misr 3, and Giza 843.

- Jordan

On-farm demonstrations were implemented during the 2012/13 cropping season in Irbid, Ma’daba, and Karak Directorates.

Irbid Directorate is located in the northern part of Jordan. The area is characterized as a typical semi-arid Mediterranean climate with an annual rainfall ranging from 250 to 500 mm, with a long-term average of about 450 mm. The rainy season starts around November and ends in April. The summer period is completely dry. The cropping systems in the area are wheat based and barley based in the drier part. Wheat is rotated with legumes and summer vegetables. Wheat-fallow, barley-fallow, and barley-barley rotations are common in the drier part of the region as we go from west to east. This area used to be a major legumes production area, but, the planted areas decreased because of the low yields of the local varieties that were planted in the spring. The plants encountered water and temperature stresses at the end of the growing season. Also, production costs were high.

Maru research station is about 20 km north of Irbid city in north Jordan. The elevation of the station is 620 m above sea level. The climatic conditions are characterized by cold winters and hot summers. The long-term average annual rainfall (20 years) is 414 mm. The soil at Maru station is heavy clay.

Madaba Directorate lies 40 km to the south of Amman. The area experiences a semi-arid Mediterranean climate with an annual rainfall ranging from 250 to 400 mm, with a long-term average of about 300 mm. The rainy season starts around November and ends in April. The summer period is completely dry. The cropping systems in the area are wheat based and barley based in the drier part. Wheat is rotated with legumes and summer vegetables. Wheat-fallow, barley-fallow, and barley-barley rotations are common in the drier part of the region.

Mushager regional research center was established in 1988 in Madaba Directorate. It is located 28 km southwest of Amman on an area of 121.2 ha. The elevation of the station is 800 m above sea level. The climatic conditions are characterized by cold winters and hot summers. The long-term average annual rainfall is 350 mm. The soil is heavy clay.

Karak Directorate lies 140 km to the south of Amman. The area is a semi-arid Mediterranean climate with annual rainfall ranging from 250 to 350 mm, with a long-term average of about 300 mm. The rainy season starts around November and ends in April. The summer period is completely dry. The total cultivated area is 49135 ha, of which 6873 ha is cultivated with olive and fruit trees, 6200 ha with vegetables, and 20564 ha with field crops. The cropping systems in the area are wheat based and barley based in the drier part. Wheat is rotated with legumes and summer vegetables. Wheat-fallow, barley-fallow, and barley-barley rotations are common in the drier part of the region.

Rabba regional research center was established in 1988. It is located in Karak Directorate. It is 120 km south of Amman. The elevation of the station is 870 m above sea level. The climatic conditions are characterized by cold winters and hot summers. The long-term average annual rainfall is 330 mm. The soil is heavy clay.

Farmers participating in the on-farm demonstrations were small-scale ones, their fields being less than 4 ha. The main constraints that they face include

- Climatic conditions, including reduced rainfall and changes in its distribution in addition to increases in temperature

- Availability of proper zero till machines

- Mechanically harvested chickpea varieties combined with increased labor costs have resulted in a reduction in the  area planted to chickpea (food legumes in general)

- Seed production and distribution systems

- Continuous land fragmentation which reduces the ability of farmers to apply modern technologies.

These constraints are common to all the three governorates.

- Lebanon

In Lebanon, the on-farm demonstrations for 2012/2013 were implemented in Bekaa Governorate and distributed over seven sites located in three ‘Kazas’ or districts (Hermel, Baalbeck, and Zahle). Chickpea seed multiplication was conducted at LARI's Kferdan station.

Al Kaa, Hermel district (two sites) is: located in north Bekaa Governorate.

Al Kaa 1: Latitude 34°34’13.5’’N, longitude 36°46’29.0’’E; altitude 668 m.

Al Kaa 2: Latitude 34°33’03.7’’N, longitude 36°46’79.3’’E; altitude 674 m.

The Al Kaa region is a typical semi-arid zone, characterized by cold winters and dry summers, with a maximum annual rainfall of 250 mm. The major winter cropping systems in the area are barley and wheat rotated with some legumes and vegetables. The planted areas have decreased because of the low yields of the local varieties of wheat and barley and climate change (drier spring). This latter has also affected some winter legumes, especially the varieties of chickpea that are cultivated in the spring. Another factor causing a reduction in the planted is the high cost of irrigation.

Deir El Ahmar, Baalbeck district is located in north Bekaa Governorate. Latitude 34°07'66.5’’N, longitude: 36°13’69.1’’E; altitude 996 m. The average annual rainfall ranges between 400 and 450 mm. Wheat is the major winter crop in this area rotated with summer crops, especially potato and corn and sometimes tobacco. The new varieties of cereals and legumes which produce higher yields and have high tolerances to drought and low temperatures should be promoted.

Majdaloun, Baalbeck district is located in north Bekaa Governorate. Latitude 34°99'07.4’’N, longitude 36°10’21.0’’E; altitude 1003 m. The average annual rainfall ranges between 400 and 450 mm. Wheat is the major winter crop in this area rotated with summer crops, especially potato and corn and sometimes tobacco. The new varieties of cereals and legumes which produce higher yields and have high tolerances to drought and low temperatures should be popularized.

Zahle (2 sites), Zahle district is located in central Bekaa Governorate.

Zahle 1: Latitude 33°80’70.2’’N, longitude 35°93’86.8’’E; altitude 885 m. It is used to compare CA technology practices and conventional practices for growing the same variety of wheat.

Zahle 2: Latitude 33°81’ 34.2’’N, longitude 35°94’ 98.6’ E; altitude 890 m.

The average annual rainfall in the area is between 600 and 650 mm. Wheat is the major winter crop in this area rotated with summer crops, especially potato and corn, vegetables, and legumes. New varieties of cereals and legumes which have higher yield potentials and tolerance to drought and low temperatures will be promoted.

Taanayel, Zahle district is located in central Bekaa Governorate. Latitude 33°79’47.5’’N, longitude 35°87’30.3’’E; altitude 901 m. Annual rainfall is between 650 and 680 mm. Wheat is the major winter crop in this area rotated with summer crops, especially corn, vegetables, and legumes. The new varieties of cereals and legumes which produce higher yields and have high tolerance to drought and low temperatures should be popularized.

Kferdan, Baalbek district. This is a LARI and ICARDA research station with a maximum rainfall of 450 mm. Barley and wheat are the major winter crops on this station rotated with some legumes. The chickpea varieties are increased here.

- Morocco

In Morocco, the main activities of the project were conducted in the Rabat-Salé-Zemmour-Zaer region, in particular at Marchouch, Brachwa, and Had Ait Mimoun during the 2012/13 cropping season. This region covers about 442700 ha of agricultural land where 75% of the farms are less than 5 ha in size. Most of farmers are poor. Cereals are the main cultivated crops, occupying more than 284500 ha, about 64 % of the agricultural land. These are followed by food legumes occupying 30100 ha (7 % of the agricultural land). The involvement of women in farm activities is low.

Marchouch and Brachwa (Zaer district) are located 70 km south of Rabat. The soil is loamy clay with an average rainfall of 400 mm. Cereals are generally grown in rotation with legumes. The difference between potential and farmers’ yields is important. For cereals this difference is about 3 t/ha for faba bean, 2 t/ha for lentil, and between 1 and 1.5 t/ha for chickpea.

The main technical constraints are the limited range of varieties, low weed control, diseases and pests, inappropriate seeding rate, and low level of mechanization. The most important varieties grown in the Zaer region are Achtar and Marchouch (bread wheat) and Karim and Merzak (durum wheat), local populations of faba bean (Farihane, Zahour, and Rizki), chickpea and Bakria, the local population of lentil. The varieties that should be promoted in the region are Arrihane and Kharrouba for bread wheat, Faraj and Louiza for durum. The chickpea varieties Arifi, Rizki, and Zahour, the lentil varieties Chekkouf, Zaaria, and Bakria, and the faba bean variety Aguadulce are recommended for this region.

Had Ait Mimoun (Zemmour district) is located 30 km north of Meknes. The soil is loamy clay with an average rainfall about 600 mm. Cereals are grown in rotation with legumes, in general. The differences between potential yields and farmers’ actual yields are about 3 t/ha for cereals and 2 t/ha for faba bean. The main technical constraints are the limited number of varieties, weed infestation, inappropriate seeding rate, and diseases.

The most commonly grown varieties are Achtar and Amal (bread wheat), and Karim (durum wheat). For faba bean farmers use mainly the cv. Aguadulce. For this region the varieties Arrihane, Kharrouba, and HI 50 (bread wheat) and Faraj and Louiza (durum wheat) should be promoted. The chickpea varieties Farihane, Arifi, Rizki, and Zahour, the lentil varieties Chekkouf, Zaaria, and Bakria, and the faba bean variety Aguadulce are recommended for this region.

- Sudan

In Sudan during the 2012/13 cropping season, the on-farm demonstrations were implemented in three states, River Nile State, Gezira State, and Northern State. The activities during this season included on-farm and on-station demonstrations of promising lines, seed increase, and dissemination of information through field days and farmer field schools (FFS).

The River Nile State is located between latitudes 16-22°N and longitudes 32-35°S. It has a trace amount of rain and a mean annual temperature of about 30°C. The soil is generally flat with few depressions. There are three types of soil, Riverian (highly fertile), Karu (moderately fertile), and high terrace (poor).

The state consists of six localities and is inhabited by 950000 citizens with over 80% practicing agriculture (farming and herding) for their livelihoods. Major cultivated lands are located around the River Nile and Atbara banks. Farmers grow staple crops (sorghum and fodders) as well as economic crops (vegetables). In Sudan, winter represents the main agricultural season and is characterized by being short and warm. However, the River Nile State has relatively cold and long winters. This makes the state an ideal area for winter crops, such as wheat and legumes. Drought, climate change, land degradation, and river bank erosion are the main causes of natural resources shrinkage. The area given over to faba bean, is 11870 ha, that to chickpea is 2940 ha, and that to wheat is 13890 ha.

The Northern State is located in northern Sudan and receives a trace amount of rain and a mean annual temperature of about 30°C. There are three types of soil, Riverian (highly fertile), Karu (moderately fertile), and high terrace (poor). Farmers grow economic crops (vegetables and fodders) and depend mainly on date palm. Winter, which is long (November to March), is the main agricultural season. Drought, climate change, land degradation, and river bank erosion are the main causes of natural resources shrinkage. The area given to faba bean is 13400 ha and that to wheat is 19000 ha.

The Gezira scheme is the largest irrigated project in Sudan, covering an area of about 900000 ha. The scheme is located in the arid and semi-arid climatic zone (between latitudes 15˚15' and 14˚15'N and longitudes 33˚30' and 32˚30'E). The annual rain fall ranges between 230 and 400 mm and the mean annual temperature is about 28°C. The soil of the scheme is part of the central clay plain of Sudan. It is generally flat with a few depressions. The dominant soil is vertisol, deep clay in texture, and moderately well drained. The soil is non-saline and slightly sodic with a high cation exchange capacity. It is characterized by its dark brown color and has cracks extending to more than 50 cm. The cropping systems in the scheme are wheat and sorghum based rotated with winter legume (chickpea), summer legume (groundnut), and vegetable. Chickpea was recently introduced into the scheme and its cultivation is faced with many constraints. The main problems are that the farmers use seeds from unknown sources – there is no systems of seed production and distribution – and the temperature is high, particularly towards the end of the season. Viral, wilt, and root diseases are considered the major constraints to the crop production. There are high fluctuations in, and less sustainability of, crop productivity because of these and other factors.

- Tunisia

In Tunisia, the fields chosen for the on-farm demonstrations during the 2012/13 cropping season were mainly located in the north of Tunisia in six governorates (Jendouba, Beja, Kef, Siliana, Bizerte, and Zaghouan). Three legume crops (faba bean, chickpea, and lentil) and durum and bread wheat are demonstrated in these fields.

Fernana is situated in the northwest of Tunisia (180 km from Tunis and 23 km from Jendouba). Fernana is located in a sub-humid zone (mean annual rainfall 700 mm). Yields under rain fed conditions are very low (1.3 t/ha for cereals and around 1.26 t/ha for faba bean) compared to the potential yields (4-5 t/ha for wheat and 2.5-3.0 t/ha for faba bean). In the 2010/11 cropping season, the improved faba bean variety cv. Bachaar yielded 1.91 t/ha and cv. Badi yielded 2.02 t/ha. In comparison, the farmers produced only 1.08 t/ha, a large difference (food security in Arab Country, progress report 2011). The soil in the region is fertile black clay. The main cropping system is wheat-faba bean. About 50% of the farmers are small-holders (farms less than 10 ha). Farmers have less access to new technologies compared to other regions and use minimum inputs for crop production. Food legumes are grown on about 18% of the agriculture land and cereals on about 47%. This is an area which is very suitable for CA and it will be used as a case study for GIS and remote sensing.

Kef Governorate is located in north-west Tunisia. It is a semi-arid region with an average annual rainfall ranging between 300 and 450 mm. The fertility of the soil is variable. The cropping system is basically wheat and barley with fallow although sometimes other crops, such as oats or legumes, are grown. Small-, intermediate- or large-scale farmers can be found in Kef. The farmers’ yields are low – around 1.5 t/ha – a large difference compared to the potential yield at the research station which is at least two to three times higher. The most frequently grown varieties are Karim (durum wheat), Utique (bread wheat), Beja 1 (chickpea), and Kef (lentil).

Beja Governorate is located in central north Tunisia and is considered the most important wheat growing region in the country. Annual rainfall ranges between 400 and 700 mm, but most of the agriculture area receives an average annual rainfall of between 500 and 600 mm. The soil is mostly fertile. The main constraints for these crops are foliar diseases (for wheat, Septoria tritici, rust, and Fusarium; for grain legumes, Ascochyta blight, chocolate spot, rust, Fusarium wilt, and others) and parasitic plants, mainly Orobanche on faba bean and Cuscuta on chickpea. The most popular cropping systems in the region are wheat (durum/bread)-food legume (faba bean, chickpea or fenugreek), or sunflower/garlic.

Three small-scale farmers are involved in the EU-IFAD project. The farmers’ fields are situated in the southern-western zone of Beja Governorate.

Hammam Sayala is located 8 km from Beja city and 108 km from the capital, Tunis (latitude 36°39'18.36"N, longitude 9°08'20.33"E). The field is infested with Orobanche foetida.

Sidi Shili is located 11 km from Beja city and 111 km from Tunis, (latitude 36°38'18.53"N, longitude 9°09'41.94"E). The field is situated in an irrigated area (suitable for supplemental irrigation).

Sidi Ismaïl is located 20 km from Beja city and 120 km from Tunis, (latitude 36°34'46.73"N, longitude 9°08'26.94"E). The field is suitable for CA.

Kairouan, Chebika district is located at 160 km south of Tunis and about 16 km from Kairouan (latitude 35°37’33’’N, longitude 9°55’43’’E). The average rain fall is low – 300 mm. Most of the irrigated wheat area is located in this region. The farm associations and the farm equipment which exist at the ‘Institut National des Grandes Cultures’ (INGC), Tunisia experimental station could lead to the dissemination of new technologies to farmers.

Bizerte Governorate, Mateur district is located 60 km north of Tunis. The average rainfall in the region is around 600 mm. The most common rotations are wheat (durum/bread)-legume (chickpea, faba bean, and bean), wheat (durum/bread)-sunflower, and wheat-oat. Many farmers practice a monoculture of wheat-wheat and as a consequence problems of root diseases and Fusarium are becoming frequently observed in the region. There is a large difference between potential yields for wheat at the experimental station (5.5 t/ha) and the farmers yields (2.7 t/ha). The most frequently grown varieties are Karim (durum wheat), Utique (bread wheat), Beja 1 (chickpea), Badi and land races (faba bean), and landraces (sunflower).

Zaghouan Governorate, El Fahs district is a semi-arid region. The annual rainfall is normally between 350 and 400 mm. The cropping systems in the region are wheat (durum/bread)-legume (faba bean), wheat (durum/bread)-fallow, wheat/barley, wheat-oat, or wheat-wheat. The most commonly grown varieties are Karim (durum wheat), Utique (bread wheat), Beja 1 (chickpea), and Rihane (barley).

Siliana Governorate is located in a semi-arid region with an annual rainfall ranging from 300 to 400 mm, in general. The cropping systems in the region are wheat (durum/bread)-legume (chickpea and lentil), wheat (durum/bread)-fallow, wheat-wheat, wheat-barley, and barley-legume (chickpea and lentil). The most commonly grown varieties are Karim (durum wheat), Utique (bread wheat), Beja 1 (chickpea), Siliana (lentil), and Rihane (barley).

- Turkey

Activities are being conducted in four provinces during the 2012/13 cropping season:

Sanliurfa Province, Siverek district, latitude 37°0'N, longitude 39°01'E; altitude 666 m. It is a medium arid area. Annual rainfall averages around 440 mm. Precipitation falls mainly in the winter and spring seasons. The main rotation applied is wheat-lentil-barley. The major problems for wheat are yellow rust and drought. The potential yield for wheat is about 3.5 t/ha and for lentil is 1.4 t/ha. Most of farmers have an average economic situation.

Sanliurfa Province, Viransehir district, latitude 37°09'N, longitude 38°54'E; altitude 500 m. It is a medium arid area. Annual rainfall averages around 440 mm. Precipitation falls mainly in the winter and spring seasons. The main rotation is wheat-lentil. The main constraints for wheat are yellow rust and drought. Yield potentials are about 3.0 t/ha for wheat and 1.1 t/ha for lentil. Most of the farmers are poor.

Kahramanmaras Province, Araban district, latitude 37°32'N, longitude 36° 28'E; altitude 2800 m. The soil structure of Araban district is clay-sandy loam. On average, the annual precipitation is 460 mm. Water decreases in the spring and summer months and the land becomes increasingly dry as the temperature increases. Most of the precipitation falls in the winter. No rain is generally received during the summer season. The main rotation is barley-wheat-chickpea. The main constraint for wheat is yellow rust and for chickpea, Ascochyta blight. Yield potentials are about 3.5 t/ha for wheat and 1.8 t/ha for chickpea. Most of farmers have an average economic situation.

Kahramanmaras Province, Yavuzeli district, latitude 37°19'N, longitude 36° 34'E; altitude 2700 m. The Soil structure of Yavuzeli district is clay-loam. The average annual precipitation for Yavuzeli district is 400 mm. Water decreases in the spring and summer months and the land becomes increasingly dry as the temperature increases. The main rotation is barley-wheat-chickpea. The main constraints for wheat are yellow rust, Septoria, and Sunn pest, and for chickpea the constraint is Ascochyta blight. Yield potentials are about 4 t/ha for wheat and 1.5 t/ha for chickpea. Most of the farmers are poor.

Eskisehir Province, Hamidiye district. The demonstration site is located at latitude 39°34’6’’N, longitude: 30°55’20”E; the altitude is 907 m. The average rainfall is 300 mm. The main rotation is barley-sunflower-wheat-chickpea. The main constraints for wheat are drought, yellow rust, and Sunn pest, and for chickpea the constraint is Ascochyta blight. Yield potentials are 2.5-3.0 t/ha for wheat and 0.8-0.9 t/ha for chickpea. Most of the farmers are poor.

Usuk Province, Ulubey district. The demonstration site is located at latitude 38°25’17’’N, longitude 29°17’28”E. The altitude is 737 m and the average rainfall is 400 mm. The main rotation is barley-wheat-chickpea. The main constraints for wheat are drought, yellow rust, and Sunn pest, and for chickpea the constraint is Ascochyta blight. Yield potentials are 3.0-3.5 t/ha for wheat and 1.1 t/ha for chickpea. Most of farmers have an average economic situation.

# Progress and performance by component

  - Progress based on outcomes

Objective 1: Promotion of proven and tested technologies for wheat-legume rotation systems, by scaling out existing improved wheat and food legume varieties and associated production technologies, while concurrently identifying and testing appropriate new technologies to sustainably improve productivity and production; expected outputs and outcomes include the following:

- High yielding and stress tolerant wheat and food legume germplasm and associated technologies tested and adapted to farmers’ production environments and end-user requirements

Several varieties of wheat (durum and bread) and food legumes (faba bean, chickpea, and lentil) were released to the countries involved in the project during the last period. The main characteristics of these varieties were that they had the characteristics of a high yield potential and resistance or tolerance to one or more of the biotic and abiotic stresses prevalent in the WANA region that cause important yield losses.

Tables 2 presents the varieties of faba bean, chickpea, lentil, and durum and bread wheat released during the period 2010-2012 while Table 3 lists the number of varieties submitted for release in the same period.

Table 2: Varieties of faba bean, chickpea, lentil, and durum and bread wheat released by National Programs during the period 2010-2012

| Countries | Faba bean | Chickpea | Lentil | Durum wheat | Bread wheat | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Algeria | 0 | 0 | 0 | 8 (Ammar1, Ammar6, Setifis, Megress, Wahbi, Saoura, Mansoura, Massinissa) | 4 (El Wifak, R’mada, Djanet, Djemila) | 12 |
| Egypt | 4 (Nubaria2, Nubaria3, Sakha4, Misr3) | 0 | 0 | 2 (Benysuif5, Benysuif6) | 3 (Gemmiza11, Sids12, Sohag1) | 9 |
| Jordan | 0 | 0 | 0 | 0 | 0 | 0 |
| Lebanon | 0 | 1 (Ghab5) | 0 | 4 (Tal Ammara1, Miki3, Asghar, Icarasha) | 1 (Tal Amara2) | 6 |
| Morocco | 0 | 0 | 0 | 1 (Louiza) | 2 (Kharrouba, HI50) | 3 |
| Sudan | 0 | 0 | 0 | 0 | 0 | 0 |
| Tunisia | 0 | 1 (Nour) | 1 (Boulifa) | 0 | 0 | 2 |
| Turkey | 0 | 5 (Azkan, Hisar, Cakır, Aksu, Diyar) | 0 | 3 (Alibaba, Gundas, Icajoudy) | 2 (Mufitbey, Nacibey) | 10 |
| Total | 4 | 7 | 1 | 16 | 14 | 42 |

Table 3: Number of varieties of faba bean, chickpea, lentil, and durum and bread wheat submitted for release by National Programs during the period 2010-2012

| Countries | Faba bean | Chickpea | Lentil | Durum wheat | Bread wheat | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Algeria | 0 | 2 | 3 | 3 | 3 | 11 |
| Egypt | 0 | 0 | 0 | 0 | 0 | 0 |
| Jordan | 0 | 0 | 0 | 0 | 0 | 0 |
| Lebanon | 1 | 1 | 0 | 3 | 1 | 6 |
| Morocco | 0 | 3 | 1 | 5 | 2 | 11 |
| Sudan | 0 | 0 | 0 | 0 | 0 | 0 |
| Tunisia | 1 | 0 | 0 | 0 | 0 | 1 |
| Turkey | 0 | 6 | 0 | 4 | 4 | 14 |
| Total | 2 | 12 | 4 | 15 | 10 | 43 |

It can be seen from Tables 2 and 3 that most of the released varieties are wheat (durum and bread). The food legume varieties are still limited in number, particularly for faba bean and lentil. More emphasis is needed on the development and release of food legume varieties in the WANA region. During the past three years, some countries have been more active in releasing varieties (Turkey, Algeria, and Lebanon) while others are less so (Sudan, Jordan, and Tunisia).

Although the involvement of the NARS in the project started after some delay, several activities have been undertaken with farmers. These include popularization of the new wheat and food legume varieties and working with farmers to test CA, supplemental irrigation, and IPM in their fields. Table 4 shows the number of farmers associated with the different activities undertaken in the 2012/13 cropping season. Most of them are involved in the popularization of the new varieties of wheat and food legumes.

Table 4. Number of farmers involved in the different field demonstration activities presented during the 2012/13 cropping season

| Activity | Country |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Algeria | Egypt | Jordan | Lebanon | Morocco | Sudan | Tunisia | Turkey |
| Variety popularization (including verification trials) | 11 | 35 | 4 | 7 |  | 16 | 19 | 6 |
| Conservation agriculture | 3 | 2 | 6 | 1 | 2 |  | 3 |  |
| Supplemental irrigation | 5 | 35 |  |  |  |  | 3 |  |
| IPM |  | 20 |  |  | 8 |  | 6 |  |

Since the 2012/13 cropping season is not completed in most countries, only in Egypt and Sudan, it is possible only to have an idea about the expected performance of the packages tested.

In Egypt, the superiority of the Orobanche tolerant varieties (Misr 3 and Giza 843) which were introduced is clearly visible, mainly in fields infested with Orobanche. For example, in Al-Ghar (Zakazik, Al-Sharkia Governorate), farmers using Giza 843 with appropriate agronomic practices (low seed density, only one irrigation, appropriate crop rotation, and reasonable fungicide protection) can expect a yield of between 4.5 and 5 t/ha. However, in a neighboring farmer’s field showing a high infestation with Orobanche, where the susceptible variety Sakha 1 was used, the expected yield is not likely to reach 1 t/ha. The approximately 150 farmers participating in the field day organized on 5 March 2013 appreciated the differences between both fields and most of them asked to test the variety Giza 843 with the recommended package in the 2013/14 cropping season. The field day organized at Zakazik benefited from extensive media coverage. Indeed at least six daily newspapers published articles about the field day as well as it being presented on the specialized Egyptian TV channel, (Misr AlZera3eya). These articles highlighted the importance of the action and the success in reintroducing a faba bean crop in the region by using the new variety Giza 843 and an appropriate management package (Annex G).

It is expected that faba bean production will increase in the neighboring area of Al-Ghar, where farmers abandoned a faba bean crop during the last decade because of the Orobanche problem and competition from other crops. The low seeding density applied with this variety (75-80 kg/ha) produces important ramifications, improves pod setting and reduces risk of chocolate spot development because of the lower vegetative growth. Furthermore, low seed density improves water use efficiency; only one or two irrigations are needed in northern Egypt. Farmers used to grow faba bean with almost double the amount of seed per ha, which increased costs. By reducing the seeding rate, the variety can be disseminated more rapidly and, therefore, can reach the maximum number of farmers in fewer years. With a low seeding density and early sowing (late October or early November) other improved varieties (Misr 3, Nubaria 2, Nubaria 3, and Sakha 4) performed well in other regions.

The strategy of developing the faba bean growing area in Egypt by inter cropping with young fruit trees in reclaimed desert areas gave important results that will contribute to an increase in faba bean production and improve soil fertility and structure. This will have a positive effect on fruit production. Intercropping is used by sowing generally two faba bean rows between young fruit trees or sowing faba bean on the fruit tree rows. Irrigation is generally done by a drip system.

In Egypt, the ARC is supporting the increased use of improved faba bean varieties by producing foundation seeds (in 2012, the ARC produces 140.6 tonne of faba bean foundation seed). Around 60% of the amount produced is recuperated by the Central Administration (national seed company) and other private seed companies licensed to produce certified seeds. The faba bean varieties most produced over the last five years were Sakha 1, Giza 716, Giza 843, Misr 1, Sakha 4, Nubaria 1, and Giza 3. In 2012, the Field Crop Research Institute of the ARC started to produce foundation seed of the recently released faba bean varieties Nubaria 2, Nubaria 3, Wadi 1, and Misr 3 (Table 5). The varieties most produced are still Sakha 1 and Giza 843. It is expected in the coming seasons that the Orobanche resistant variety Misr 3, which has better Orobanche tolerance than Giza 843; and the foliar diseases resistant varieties, Nubaria 2 and Nubaria 3, will make rapid gains in the area. It is important to give special attention to the maintenance of the faba bean varieties to avoid any mixing and, therefore, any loss of the characteristics of the variety.

Table 5. Production of faba bean foundation seed (in tonne) during 2011 and 2012 in Egypt

| Faba bean variety | 2011 | 2012 |
| --- | --- | --- |
| Sakha1 | 26.100 | 39.690 |
| Giza 843 | 13.675 | 35.340 |
| Sakha 2 | 2.475 | 4.800 |
| Giza 3 (improved) | 8.175 | 12.300 |
| Sakha 3 | 8.25 | 7.800 |
| Misr 1 | 1.000 | 4.800 |
| Nubaria 1 | 3.860 | 4.000 |
| Sakha 4 | 3.400 | 13.65 |
| Giza 716 |  | 13.500 |
| Nubaria 2 |  | 1.200 |
| Nubaria 3 |  | 1.500 |
| Misr 3 |  | 0.390 |
| Wadi 1 |  | 1.625 |
| Total | 66.935 | 140.595 |

The breeder and foundation seeds of newly released faba bean varieties (Misr 3, Sakha 4, Nubaria 2, and Nubaria 3) were developed in two research stations (Nubaria and Sakha). Table 6 shows the area and expected production for breeder and foundation seed for each faba bean variety.

Table 6. Allocated area (in ha) and expected production (in tonne) of breeder and foundation seed for each variety in 2013

| Cultivar | Sites | Breeder seed area | Expected production of breeder seed* | Foundation seed area | Expected production of foundation seed* |
| --- | --- | --- | --- | --- | --- |
| Nubaria 2 | Nubaria | 0.105 | 0.42 | 1.47 | 5.88 |
| Nubaria 3 | Nubaria | 0.105 | 0.42 | 1.05 | 4.2 |
| Misr 3 | Nubaria | 0.105 | 0.42 | 1.68 | 6.72 |
| Sakha 4 | Sakha | 0.420 | 1.68 | 4.2 | 16.8 |
| Giza 843 | Sakha | 0.420 | 1.68 | 4.2 | 16.8 |

* Production estimated on the basis of an expected yield of 4 t/ha

As Table 6 shows, it is expected to generate 4.2 tonne of Nubaria 3, 5.9 tonne of Nubaria 2, 6.7 tonne of Misr 3, and 16.8 tonne each of Sakha 4 and Giza 843. Each tonne produced can be used to sow 12-13 ha. The foundation seed will serve to produce certified seeds. The grown area for foundation seed of the variety Misr 3 (the most Orobanche resistant faba bean variety) is expected in 2013/14 to show a twentyfold increase over that of 2012/13. The grown area for Nubaria 2 will be expected to increase fivefold and for Nubaria 3, threefold (Tables 5 and 6). It is expected that by 2014, the production of the first generation of certified seed of Misr 3 will be more than 30 tonne, sufficient to sow more than 400 ha.

In the 2012/13 cropping season Egypt started a national campaign promoting faba bean production which consolidates the efforts of the project team to reduce the discrepancy between national production and national need and improve the food security status in respect of faba bean, one of the most important agriculture products in the diet of the Egyptian population.

In Sudan, on-farm demonstrations of recently released varieties of faba bean and chickpea have been carried out by the ARCo during the 2012/13 cropping season in the Gezira, River Nile, and Northern States using recommended agronomic packages.

In River Nile State, the program of the 2012/13 cropping season was executed at the Ed-Damer locality (Hudeiba and Aliab), Lower Atbara (Gersi), and Shendi locality (Bagrawia). The released faba bean cultivars used were Ed-Damer and BB7 and the chickpea cultivars were Atmour and Shendi. Eleven demonstration plots were implemented and four field days were organized. A considerable amount of seed was produced this season which can be used next season for on-farm demonstrations.

In Northern State, in the 2012/13 cropping season, the program was executed at Elselaim Basin, Dongola, and Merowe research stations and sought to spread the improved food legume varieties.

In the Gezira scheme, the on–farm demonstrations of the chickpea varieties released in the Sudan (eight varieties) were implemented in three locations to evaluate their performance under the Gezira conditions. Chickpea has been recently introduced into the scheme and its cultivation faces many constraints (farmers use uncontrolled seed, the high temperature, and viral and wilt diseases). Three demonstration plots and three field days were executed with 65 farmers participating.

In total, eight field days have been organized (River Nile State four, Gezira State three, and Northern State one) with 198 farmers participating. About 8.7 tonne of faba bean seeds of the improved varieties have been retained for the next crop season’s demonstration fields. Other amounts of chickpea and lentil seeds will be retained for conducting on-farm demonstrations in 2013/14.

In Sudan, ICARDA, in collaboration with the ARCo, is carrying out a selection program for faba bean tolerant to high temperature and the main diseases. The identified tolerant varieties could be promoted in the coming years.

In Tunisia, a decision was taken by the Ministry of Agriculture during a previous year to promote a faba bean (small seed) grown area. Production was encouraged by giving a 30% subsidy on the faba bean seed price which allow improved varieties released in 2003 – Badi and Bachaar – and entered in commercial use in 2007 to spread rapidly. By this means the ministry hoped to rapidly expand the area sowed to faba bean and also to improve faba bean yield and production in the country. In October 2012 all the stocks of faba bean seeds at COSEM (a seed company commercializing the improved varieties) were sold. Sixty tonne of the seeds of the faba bean variety Bachaar were distributed in autumn 2012 to farmers of the northern governorates of Tunisia (Table 7). An effort should be made to educate farmers on the appropriate agronomic practices to improve productivity in the new area of production. Therefore most of the faba bean seed for the on-farm demonstrations implemented during the 2012/13 cropping season were located in Kef Governorate where faba bean is not commonly grown. Farmers in Kef Governorate received 20 tonne of faba bean seeds of the cv. Bachaar at a price subsidized by 30%. The variety promoted in this region (Bachaar) is known for its high adaptation, particularly to dry areas and its partial resistance to rust and to stem nematode. It is expected that through this action the grown area in the region (around 1000 ha) will rapidly increase (it is expected double after two to three years of working closely with the farmers). It is also expected to have a favorable effect on wheat productivity in the coming seasons through the improvement of soil fertility. The multidisciplinary research team involved in the project consolidates its efforts to ensure technical backstopping of the joint activities conducted within the ‘Food security project in Arab countries’ in Fernana region, in particular.

Table 7. Amounts of faba bean – small seeds of improved varieties (Bachaar and Badi) – distributed in Tunisia to farmers with 30% subsidy on the price (tonne)

| Crop season | Total faba bean seeds distributed | Faba bean seeds distributed in Kef Governorate |
| --- | --- | --- |
| 2009/10 | 77.0 | 0 |
| 2010/11 | 95.0 | 6.6 |
| 2011/12 | 96.8 | 8.0 |
| 2012/13 | 60.0 | 20.0 |

The area planted to the durum wheat variety Maali, released in 2007, is rapidly increasing and all the certified seeds of this variety which were produced were sold. The amounts of certified seed of the durum wheat varieties Maali and Nasr sold in 2011 and 2012 are presented in Table 8. It appears from the statistics that between 2011 and 2012 sales of Maali seed increased by about 223%. The rapid extension of the variety is a result of the activities undertaken within the ‘Enhancing food security in Arab countries’ project which conducted many on-farm demonstrations with the variety Maali (progress reports of the project 2011 and 2012). The variety Maali is high yielding with tolerance to drought and Septoria. Farmers rapidly adopted the variety because it responds to all environments and to supplemental irrigation. Maali has been commercially available since 2010/11 and is occupying between 15 and 20% of the area given over to durum wheat. The only limitation on its further extension is the limited capacity of the seed company COSEM which is exclusively producing the seed commercially. In long-term testing trials done by INRAT it was found that this variety gives, on average, 0.5 t/ha more than the most commonly grown variety, Karim (M.S. Gharbi, personal communication). Another variety of durum wheat (cv. Salim) released by INRAT in 2009, but not yet commercialized, produces a similar level of yield to Maali and has better resistance to leaf rust besides the resistance to Septoria. This variety is included in on-farm demonstrations to promote its use mainly in areas with high disease pressure. This project, in collaboration with the project ‘Enhancing food security in Arab countries’ and national institutions, will continue to spread the use of the variety Nasr, released in 2004 and commercially available since 2006. This variety is the one most resistant to Septoria (the main biotic constraint for durum wheat in north Tunisia), but it needs particular attention because of its susceptibility to lodging. Nasr is the appropriate variety for small-holder farmers who apply low fertilizer inputs and have no access to fungicides to control Septoria because of their high cost. Nasr is grown on 10-15% of the area cultivated with improved varieties of durum wheat. The adoption rate for Maali is around 95% and for Nasr is between 50 and 60% (M.S. Gharbi, durum wheat breeder at INRAT, personal communication).

Table 8: Progression in commercialization of durum wheat varieties Maali and Nasr in Tunisia

| Durum wheat varieties | 2011 (tonne) | 2012 (tonne) | Progression (%) |
| --- | --- | --- | --- |
| Maali1 | 1,665.0 | 3,707.5 | 223 |
| Nasr2 | 1,114.8 | 2,123.4 | 196 |

1 Commercialized by COSEM; 2 Commercialized by COSEM and CCSPS

The program of variety popularization is followed by several institutions: ‘Institut National de la Recherche Agronomique de Tunisie’ (INRAT), ‘Centre Régional des Recherches en Grandes Culture de Béja’ (CRRGC), ‘Institut National des Grandes Cultures de Boussalem’ (INGC), ‘Pole Regional de Recherche et de Développement Agricole du Nord-Ouest du Kef’ (PRRDANO), et ‘Office de l’Elevage et des Pâturages’ (OEP)

In Morocco, great effort has been made by the national program at INRA during the last decade to select high yielding varieties with tolerance to the main abiotic and biotic stresses for bread and durum wheat. In particular attention has been given to resistance to Hessian fly which causes serious losses, particularly in dry areas or during dry years. Unfortunately most of the varieties released did not reach the farmers although INRA concluded contracts with seed companies for their commercialization. The seed companies found that importing foundation seeds of foreign old varieties was more economic than using locally improved varieties where to increase they would need to start from the early generation at their expense (only G0 and G1 are produced by INRA, Morocco). To conduct on-farm demonstrations during the 2012/13 cropping season, the project was faced with a shortage of seeds of the recently released wheat and legume varieties. Consequently, a special program to increase bread and durum wheat and food legume varieties was conducted at the research stations for use in on-farm demonstrations in the 2013/14 cropping season. The project is helping in increasing the early generations, mainly of the recently released varieties like the durum wheat Louiza and the bread wheat Kharouba and HI50 and some other varieties of food legumes and wheat released earlier, but which did not reach the farmers.

The Moroccan industries prefer to use imported wheat (bread and durum) for processing. They argue that the Moroccan products are poor in quality. The varieties Louiza and Kharouba are of good quality and we expect that they will be developed and adopted rapidly.

In Lebanon, LARI plays an important role in the production and dissemination of newly released varieties of cereals and food legumes, meeting almost 100% of the needs of farmers for wheat seeds. Several varieties, mainly of durum wheat, have been released (Tal Ammara1, Miki3, Asghar, and Icarasha) or submitted for release during the period 2010-2012 (see Tables 2 and 3). LARI is increasing the seeds to make them available soon to farmers in order to replace the old varieties still being used extensively (i.e. Lahn2). These varieties are expected to result in substantial increases in the production of wheat and food legumes since in addition to their high yield potential they carry resistance or tolerance to different stresses.

In Algeria, eight varieties of durum wheat (Ammar 1, Ammar 6, Setifis, Megress, Wahbi, Saoura, Mansoura, and Massinissa) and four of bread wheat (El Wifak, R’mada, Djanet, and Djemila) were released during the period 2010-2012 and have been promoted in different regions of the country through the project. Furthermore, four other durum wheat varieties (Sigus, Beni Mestina, Tedjdid, and Mawna) and five bread wheat (Boumerzoug, Massine, Tidis, Akhamoukh, and Ain Lahma) were submitted for release during the period 2010-2012. It is expected that the areas under those varieties will rapidly increase as they have a high yield potential and carry resistance/tolerance to different stresses. The large number of wheat varieties released or submitted for release should satisfy the needs of farmers in the different cropping areas where variability of climate is significant. They should replace the old generation varieties which are still frequently used despite being highly susceptible to diseases.

Where food legumes are concerned, two chickpea varieties (Ghab 4 and Ghab 5) and three lentil varieties (Ebla 1, Idleb 2, and Idleb 3) were submitted for release during the period 2010-2012 and these will be promoted by the project.

The program of foundation seed production for 2012/13 took into consideration the desire of the Ministry of Agriculture to improve the rate of certified seed use to 50% for both cereals and food legumes (25% for chickpea and 75% for lentil). These are the fixed objectives for certified seed production at the national level in 2012/13 and 2013/14. For the 2012/13 cropping season, ITGC is increasing the seed of eight lentil, six chickpea, one faba bean small, one faba bean large, 14 durum wheat, and seven bread wheat varieties. Some of these varieties are newly released. The lentil varieties represent more than 50% of the food legume seed increase program.

In Turkey, five chickpea, three durum wheat, and two bread wheat varieties were released during the period 2010-2012 (Table 2). These need to be promoted and increased to reach, before long, a large number of farmers who will take advantage of the characteristics that they are carrying. Though there were some varieties released at earlier dates, they were not promoted sufficiently to farmers for them to be widely disseminated. They occupy a smaller acreage in farmers’ fields than expected given that they are high yielding, have good quality characteristics, and are tolerant to one or more biotic and abiotic stresses. So, those cultivars have also been included in the demonstration and on-farm trials in order to present them to the farmers in their own fields and not solely in the fields of the research institutes. As the main yield limiting factor for chickpea in most of the chickpea growing areas of Turkey is Ascochyta, farmers tend to plant chickpea at later dates in order to escape Ascochyta epidemics. This strategy results in the chickpea growing in warmer and drier conditions and the farmers end up with a lower yield than the cultivars’ potential. Most of the old cultivars do not have sufficient resistance/tolerance to Ascochyta to allow farmers to plant earlier in the Central Anatolian Plateau (CAP) of Turkey or in the spring or the winter planting in the southeastern part of Turkey. The new cultivars, which are now in the demonstration and on-farm trials, have been planted at the recommended dates (early spring planting in CAP or winter planting in southeastern Anatolia). This will demonstrate that these new cultivars not only have high yield potential, but are also disease resistant/tolerant. Six other varieties of chickpea, four bread wheat and four durum wheat were submitted for release during the same period (Table 3). Three institutes (Southeastern Anatolia Regional Agricultural Research Institute (GAPARI) Sanliurfa, Transitional Zone Agricultural Research Institute (TZARI) Eskişehir, and TZARI Kahramanmaraş) are conducting on-farm activities during the 2012/13 cropping season to promote the use of recently released varieties. In coming years, the cultivars released, or in the pipe line for release, will be included in the demonstrations and on-farm trials.

- Preferred genotypes identified in participatory varietal selection trials and submitted by the national programs for varietal release in targeted production areas

Most of NARS programs’ associate farmers are in the process of evaluating selected material, at least in on-farm verification trials. During the 2012/13 cropping season, several improved lines of legume and wheat underwent verification trials or yield trials in farmers’ fields. These would allow the farmers to appreciate the performances of the genotypes under farm conditions. Field visits to evaluate the improved lines have been, or will be, organized at the appropriate time. So far, the material selected will be promoted for large-scale testing and submitted for release during the coming seasons. The process of selection by farmers will help in the variety being adopted since the farmers know, better than any others, the requirement of the market and their needs.

In Tunisia, several of ICARDAs trials and national trials of faba bean and chickpea were sowed in farmers’ fields and/or on station for participatory evaluation in 2012/13 (Annex A. Work plan for Tunisia).

In Turkey, on-farm verification trials are planned for durum wheat (in Siverek), for bread wheat (in Eskisehir-Hamidiye, and Usak), and for chickpea (in Araban, Yavuzeli, Eskisehir-Hamidiye, and Usak) (Annex A. Work plan for Turkey). Field days for the participatory evaluation of the advanced lines tested on-farm will be organized in spring 2013.

In Egypt, several on-farm verification trials in Lower Egypt (Sakha, Behira, and Nubaria), in Middle Egypt (Minia, Mallawy, and Sids), and in Upper Egypt (Mataana, Assiut, and New Valley) have been planned for 2012/13. In each region, farmers will have an opportunity to appreciate the behavior of three promising faba bean lines (Annex A. Work plan for Egypt). Furthermore, at the Sids research station, ICARDA and ARC have sowed a large number of improved wheat lines for appreciation and selection by the national breeders in the region who are participating in the course on classical and molecular wheat breeding from 10-21 March 2013.

In Algeria, several promising lines of bread and durum wheat were tested on-farm at Didouche Mourad (two durum and four bread), Benifouda (one durum), and Ain Abessa (one durum) for final evaluation by farmers in 2012/13 (Annex A. Work plan for Algeria).

In Morocco, breeders and farmers will appraise and select the best wheat and legumes lines implemented at the INRA research station, Marchouch during the 2012/13 cropping season (Annex A. Work plan for Morocco).

- New and emerging constraints to adoption by farmers of identified improved technologies and the feedback provided on the technology development and adaptive research program

A meeting to initiate discussion about the seed sector for cereals and food legumes in Morocco was organized at INRA, Morocco on 31 January 2013. The participants were stakeholders in the seed sector.

Workshops including all stakeholders will be organized by NARS institutions during 2013 to identify the main constraints that farmers are facing to improving their yields, producing wheat and food legumes, and adopting new technologies.

In 2012, surveys were conducted in some countries to assess the importance of some diseases and pests and their effect on grain yields. We can mention:

- Survey of faba bean viruses in Sudan. A survey to identify virus diseases affecting the faba bean crop in the major production areas (Dongola, Korti, Karima, Marawe, Berber, Atbarar, Ed-Damer, Shendi, and Khartoum) in Sudan was conducted during 22 January-2 February 2012. The survey covered 60 randomly selected faba bean fields and 1130 samples were analyzed for 10 legume viruses at ICARDA. The incidence of virus disease was between 1 and 10% in Dongola, Korti, Karima, and Marawe and between 1 and 2% in Berber, Atbarar, Ed-Damer, and Shendi. Serological tests indicated that bean yellow mosaic virus (BYMV) was the most common in the faba bean fields. This was followed by broad bean stain virus (BBSV) and Luteoviruses (e.g. bean leaf roll virus). This survey is important in order to recommend the suitable area for faba bean seed increase.

- Survey of faba bean viruses in Tunisia. Field surveys were conducted in Tunisia during three growing seasons to identify viruses which produce yellowing, reddening, and/or stunting symptoms in chickpea, faba bean, and pea crops. A total of 1100 samples were collected from 56 fields in the northeastern regions (Bizerte, Menzel Bourguiba, and Cap Bon – Menzel Bouzalfa, and Menzel Temime) and the northwestern regions (Kef, Jendouba, Beja, and Boussalem). The samples were tested by tissue blot immunoassay using 10 virus antisera. The laboratory results showed that chickpea chlorotic stunt virus (CpCSV) was the most common, (average 44%), followed by faba bean necrotic yellows virus (FBNYV) (average 8.9%), bean leaf roll virus (BLRV) (average 3.9%), and beet western yellows virus (BWYV) (average 3.8%).

For the 2012/13 cropping season, during November and December 2012, virologists from ICARDA and INRAT collaborated in a field survey in the Bizerte and Cap Bon regions in Tunisia. They collected Tunisian virus isolates of the most economically significant legume and cereal viruses in the Central and West Asia and North Africa region together with their aphid vectors. These virus isolates and aphid species will be used later to screen for virus resistance under Tunisian conditions. The virus isolates identified were barley yellow dwarf virus-PAV (BYDV-PAV) and its aphid vector Rhopalosiphum padi; beet western yellows virus (BWYV) and its aphid vector Myzus persicae, chickpea chlorotic stunt virus (CpCSV) and its aphid vector Aphis craccivora, faba bean necrotic yellows virus (FBNYV) and its aphid vector Acyrthosiphon pisum, cucumber mosaic virus (CMV), and alfalfa mosaic virus (AMV).

- Survey of faba bean foliar diseases in Morocco in 2012. This survey allowed mapping the botrytis high spot infestation area.

- National seed systems strengthened through technical training and advisory services

One of the constraints in the field crop sector in the WANA region is the weakness of the seed system, particularly for food and feed legumes that have not played an important role in the dissemination of new improved varieties. Investment in training young engineers and technicians on seed production technology and varietal maintenance, mainly in food legumes, is crucial for ensuring a better quality product and maintaining the characteristic of the varieties, particularly for allogamous crops, such as faba bean. Maintenance of varieties is very important for a crop such as faba bean which presents a high rate of outcrossing (between 50 and 70%).

It is planned to conduct a training course on seed science and technology and variety maintenance during 2013 (June in Turkey) one participant attending from each of the 12 countries. The trainees will conduct in their country national courses for farmers’ groups on seed production, conservation, and variety maintenance and storage.

The Seed Unit specialists visited the North African countries (Algeria, Morocco, and Tunisia) to make a first diagnosis of the situation and meet the stakeholders of the seed sector and provide advisory services.

- Financially viable community- or farm-based seed production enterprises, capable of producing quality-assured seed, established on pilot sites

The Seed Unit, in collaboration with the Socioeconomic Policy Research Program (SEPRP) has developed a framework for the analysis of wheat and faba bean seed systems. Key research questions have been identified and a questionnaire and check list, for use along the seed value chain, has been prepared by the team. An exploratory mission was made to Morocco (28-31 January 2013) and preparation is underway to conduct the household survey to understand the determinants of the wheat and faba bean seed market. Additional questionnaires will be developed and surveys conducted on policy and regulatory issues, variety release mechanisms, seed production, and quality assurance. In addition, seed specialists visited Algeria and Tunisia to investigate the possibility of developing an informal seed production system for crops not of interest to seed companies.

It was decided during the Steering Committee meeting held 4 March 2013 in Egypt to support one small farmer group in each participating country by supplying them with the equipment necessary to produce quality-assured seed. The countries will send their needs for specific equipment to support the establishment of a small informal seed producer group.

Different scenarios could be imagined to implement this activity. It could be done through any group of farmers willing to take responsibility for ensuring the services for the farming community in a particular region for crops not of interest to the seed companies and not generating sufficient benefits for the private sector to warrant its investment. If that is not possible, the NARS involved will have to install a small unit, with the support of the project, for seed cleaning and dressing for farmers requesting free services. It needs farmers to be sufficiently aware about the services offered by the institutions.

It is planned that during 2013, the small units wishing to develop this activity will be functional in most of the countries involved in the project.

- New conservation agriculture-based wheat-legume rotation systems developed and tested in farmers’ fields

Nowadays, CA is becoming widespread in many of the countries involved in the project. During the 2012/13 cropping season, Morocco, for example, plans to grow 500 ha of lentil under CA in the Rabat-Salé-Zemmour-Zaer region. In Tunisia, the area under CA is estimated to be 12,000 ha and potentially can be quickly increased. In Lebanon the area under CA is increase very fast from 20 ha in 2007/08 to more than 1700 ha in 2011/12 cropping season. In Egypt, CA also has the potential to minimize the infestation of Orobanche on faba bean sowed after rice. The availability of cheaper direct seeding machines and the increase in fuel price in many non-producer oil countries have encouraged policy makers in the region to pay more attention to this technique, given the relevant results generated from the different trials on different crops. During the 2012/13 cropping season, Algeria, Egypt, Jordan, Lebanon, Morocco, and Tunisia conducted on-farm demonstrations of CA for wheat, faba bean, chickpea, and/or lentil (Annex A. countries’ work plans). Field days are planned across the cropping season in the different countries to highlight the beneficial effect of CA. Collaboration with other projects operating in the region is encouraged. This collaboration would be primarily with IFAD and ICIAR projects operating in the countries of the region in order to organize joint dissemination activities.

- Integrated supplemental irrigation and crop management packages that conserve water and maximize crop productivity developed and tested in the target areas

On-farm demonstrations of supplemental irrigation were conducted in Tunisia, Algeria, Lebanon, and Turkey during the 2012/13 cropping season. The demonstrations are done mainly for wheat in these countries (Annex A. countries’ work plans).

- Results from the wheat and food legumes baseline and variety adoption surveys and constraints analysis communicated to users, including research, extension, development agencies, and policy decision-makers

Results on the preliminary investigation on wheat production, which were obtained during the 2011/12 season in Morocco, indicated that the food security strategy in Morocco is based on pragmatic policies that promote self-reliance agriculture and permit food imports to compensate for structural deficits. However, two main challenges are facing food security in Morocco – the needs of a rapidly growing population and alleviation of the effects of climate change.

With a consumption of 210 kg per capita, cereals are a strategic food in Morocco. The national production covers, on the average, less than 70% of the population’s needs. Wheat production remained unchanged during the 1960s and 1970s and increased in the 1980s with the release of new improved bread and durum wheat cultivars. The release of these cultivars improved the yield and triggered a series of policy actions from the government. The most important of these were related to the evaluation of the breeding programs, to the upgrade of the seed processing activities, and to the promotion of large-scale demonstrations of new cultivars. However, the breeding efforts alone have not been sufficient to bridge the gap between actual production and the needs of the country.

Water resources are entirely dependent on precipitation and most of the arable land is located in arid or semi-arid areas where the average annual rainfall varies from 200 to 400 mm. Technologies that improve water use efficiency have been developed in Morocco through a research network covering the different regions of the country. As a result, supplemental irrigation and integrated crop management practices were promoted in a participatory manner with farmer playing an important role.

The investigation indicated that an irrigated farming system is characterized by highly fragmented farms and the dominance of small farms. Small-holder farmers represent 65% of the total farmers in the region, but they have control over only 25% of the total area. Medium-holder farmers represent 32% of the total households and have control over 42% of the total area. Large farms control 33% the total area, but represents only 3% of farmers. This system is based on the production of a broad range of food and cash crops. The cropping pattern is dominated by cereals (38%), alfalfa (17%), fruit (20%), sugar beet (13%), and vegetables (12%).

According to the typical technical management for wheat, summer’s deep plowing in some situations and offset disking and drilling are the dominant techniques used in a cereal-cereal rotation. However, the choice of the techniques and tools for soil preparation is related to the preceding crop. Super-phosphate is incorporated into the soil during its preparation in fall at a rate of 150-200 kg/ha. Urea is broadcast once during the tillering stage at a rate of 200-300 kg/ha when the soil is wet. The rate of seeding is 200-250 kg/ha. Only 70 % of farmers practice chemical weed control. Some farmers apply this chemical early and others late. No fungicide is used. The number of irrigations varies from one to five depending on the availability of water (rainfall). Salama, Radia, Achtar, Amal, and Arrihane are the varieties most used for bread wheat and carioca, Karim, Merzak, and Vitron, for durum wheat. The rotations used are wheat-alfalfa and wheat-sugar beet. Average yields range between 3 and 5 t/ha, depending on many factors, such as farm size, rainfall/precipitation, variety planted, input used, and crop management.

In a rainfed farming system, the production system is based on crop and livestock integration. The average farm size is relatively small, about 9.2 ha of cultivated land. The dominant land tenure is private ownership. Sharecrop farming and renting modes represent only 12% of the cultivated land. The cropping system is largely dominated by cereals (especially wheat and bread) because of the semi-arid climate; in fact 84% of the area is covered by cereals. Fodder (barley, oats, corn, and peas) are grown on 6% of the area. Pulses, mainly bean, faba bean, lentil, chickpea, and pea occupy 4.5% of the area. The fruit trees are dominated by olive trees. The main growing season is November to May and the main rotation is cereals-food legumes. The main rotations practiced in the rainfed farming system are wheat-food legumes, wheat–barley-food legumes, wheat-onion, wheat-corn, and wheat-fallow. Recently, some farmers have replaced the wheat-food legume rotation by continuous wheat because of the scarcity of hired labor needed for food legume management and harvesting. In general, farmers use a low proportion of certified seed (20%). The main varieties grown by farmers in the region, listed in order of importance, are:

- Bread wheat: Achtar, Salama, Radia, Amal, Arrihane

- Durum wheat: Carioca, Karim, Marzak, Vitron

- Barley: local varieties

- Chickpea: Clavansa

- Lentil: Bakria.

Where cereal is a preceding crop, the first tillage is done with the stubble-plow in September. This is followed, towards the end of October or early November, by a cross pass with the disc harrow (cover crop). In the case of fallow, the initial work is done at the beginning of March using a stubble-plow. In some cases, chemical treatment precedes the pass of the stubble-plow. With the arrival of autumn, a cross pass of a ‘cover crop’ is usually done before sowing towards the end of October. Very few farmers use soil analysis for crop fertilization purposes and the main fertilizers used for wheat and their basic respective doses are DAP (18-46-0), 150 to 200 kg/ha and ammonium sulfate (21%), 50 to 75 kg/ha. Cover fertilizers are decided according to the rainfall conditions during the agricultural season. Thus, in rainy years, 50 to 75 kg/ha of urea are added. Seeding is made after the first autumn rains. They start in late October/early November for barley and in mid-November for wheat. In case of late rains, the seeding period can be extended till the end of December. Seed rates for wheat vary from 160 to 200 kg/ha in the case of drill sowing, and 200 to 250 kg/ha with broadcast seeding. The crop management of wheat by farmers, in general, is limited to weed control. In most cases, herbicide treatments are performed after the emergence of weeds. The average wheat yield obtained by farmers in a normal year is about 2 t/ha.

The main problems reported by farmers in the irrigated wheat-based farming system are:

- Irrigation water deficit

- Low water use efficiency

- Limited use of water use efficiency techniques

- Wheat yields obtained by farmers are low compared to the potential

- Increase in using cereal-cereal rotations

In a rainfed farming system, the main constraints identified by farmers for a wheat-based farming system are:

-	Irregular and low rainfall in recent years

-	Decreasing area for food legumes

-	Limited use of inputs

-	Low mechanization

-	Low use of certified seeds

-	Problems in accessing loans (only 18% of farmers have access to bank loans).

- Gender analysis, including differentiating the constraints that men and women face in accessing technologies, information, and markets and communicating this to relevant stakeholders, including research, extension development organizations, and policy decision-makers

The following gender research activities were completed in Morocco with national collaborators:

- Results from gender and access to market for medicinal plants surveys in Morocco

The research summarizes the case where a large development project in Morocco had limited success because of a failure to sufficiently integrate gender into its design. The development project in Morocco was designed to implement the sustainable use of herbal and medicinal plants for community income generation. However, although the project supported women’s groups, the project, for reasons not fully explained, did not fully integrate gender into the implementation of its major development initiative. The dichotomy of supporting women’s groups, but not fully integrating them into the major development initiative was surprising. The research documents the importance and role of women in the field of herbal and medicinal plants, and demonstrated that women play major roles in using and maintaining knowledge of herbal and medical plants. The results illustrate that lack of sufficient gender integration in local community development initiatives is a design flaw which could result in the failure of such initiatives.

- Methodological research on gender and its use

This research focused on the level of men’s and women’s participation in social research using participatory research tools, and the way they see the usefulness of the results generated by participatory research. The questions raised were how men and women reacted to the participatory research tools used, what was the level of difficulties they experienced, and how did they assess the usefulness of the results generated by the participatory tools. The analyses showed that, during the application of participatory research methods, men and women have different capacities for participation given their levels of education, exposure to external ideas, and their ability to express their thoughts. Women had greater difficulty in applying some tools. This analysis showed that when designing the implementation of participatory research tools, factors that may affect the level of participation of both men and women should be considered and steps should be taken to avoid incomplete participation. This study also examined the extent to which local participants found the results generated by the participatory process useful. This raised the point that one should not use participatory tools only for extractive purpose, but also for transformative purposes. Opportunities should be provided for the participants to reflect and think about making changes on their own, while considering the possible socioeconomic factors and gender differences in the level of participation.

- Gender inequality in the context of climate change

This research addresses gender and vulnerability to climate change impacts on water availability in north-east Morocco. This arid and semi-arid region has already experienced several droughts and erratic rainfall in the past, leading not only to environmental degradation including soil erosion, but also to social and economic impacts affecting local livelihoods. The research provides a detailed description of the gender division of roles and tasks in this remote conservative rural society. The vulnerability and effects of climate-related events (droughts, water shortages, floods, and landslides) by gender, and particularly on women’s workloads, are analyzed. The analysis provides insights into how environmental factors can further exacerbate gender inequality, making rural women particularly more vulnerable, and thus calls for redoubled efforts in regions that are more vulnerable to climate variability. This research shows how men and women farmers cope with climate variability and explores how coping strategies are shaped by the gender dimensions of power relations and the decision-making processes.

- The effects of changes in climate and water resources on gender inequality

The research, using a case study approach, examines why women are more vulnerable to environmental risks in agriculture and livelihoods and how these affect gender relations. The case studies provided powerful empirical evidence which showed how gender roles are perceived and practiced in the target areas. The approach is a narrative description of the selected cases to showcase the uniqueness and complexities of the context. The descriptive nature of the investigation attempts to give as much context as possible. Each case is handled as a separate story, treating it as a chronological recounting. Four cases from different socioeconomic categories were analyzed. This work is a document emphasizing the point that for any agricultural effort directed to benefitting both men and women in Morocco, gender equality is a precondition and hence needs to be understood in its complex, real and dynamic life situations.

- The ripple effects of the social and gender analysis research process

This research documents a review of reflections on participatory gender research carried out in Morocco. The basic question addressed is: What are the ripple effects of participatory research on gender dimensions in rural communities? Did the research have an effect on gender sensitive understandings among community participants? The research results recognize that participatory research is the start of a change process. Furthermore, if throwing the pebble is a big act in itself that deserves a solid conceptualization, planning, and action, then the ripples occurring from that act are even more important. They are the resonance of the research process and, therefore, deserve due attention and are certainly worthy of recognition and wide dissemination.

- Analysis of productivity trends and gaps in wheat and food legume based systems made available to relevant institutions and policy decision-makers

Based on the socioeconomic research activities in Morocco, it was found that high commodity prices internationally in recent years, especially for wheat, and their negative impact on the trade balance, have generated a strong incentive in policy decision-makers in Morocco to enhance food security and reduce the dependency on imported commodities.

Research results indicated that the average wheat yields obtained by farmers are 4 t/ha in irrigated farming systems and 2 t/ha under rainfed ones, while well-managed farms are able to produce on average 7 t/ha under irrigation systems and 5 t/ha under rainfed. This large gap is mainly a consequence of insufficient and variable rainfall and the predominantly poor crop management techniques used by most farmers.

To increase and stabilize yields of wheat in these environments, Moroccan scientists have been developing improved and more adaptable techniques since the 1980s. The research results obtained showed the positive contributions of improved varieties and better technical management in reducing the gap between the actual and potentially achievable yields. It was proven that early to semi-early cultivars, early planting, early weed control, optimum nitrogen application, and supplemental irrigation at tillering and heading increased and stabilized the wheat yield. Unreasonable use of fertilizers for wheat production also represents a serious problem. The use of the recommended fertilizer rate, based on soil analysis and plant requirements, could significantly improve nitrogen productivity and reduce production costs.

In order to better manage the risks related to high climate variability and uncertainty, farmers tend to minimize their production costs. The existence of a solid insurance system could encourage farmers to invest in improved crop management. Easy access to loans could also help farmers to use the inputs as recommended. Supplemental irrigation technology could help to reduce climatic risks and encourage farmers to use inputs intensively.

The socioeconomic component of the project focuses on monitoring and assessing the uptake and impact of the technologies and other innovations generated by the program. Understanding the constraints that limit technological change and identifying policy and institutional measures that alleviate these constraints will be a critical part of this component. This component, however, will give greater emphasis to ways of increasing technology adoption to reduce yield gaps and enhance food security. New methods of impact assessment will be used, such as gender analysis, market access of small-holder producers, management of natural resources – particularly water allocation and management – and socioeconomic factors affecting adaptation to climate change. More emphasis will be given to the integration of social and gender analytical frameworks and methodologies across the components of this socioeconomic and policy research and across other ICARDA programs.

During the last coordination meeting (Amman, 12-13 December 2012) it was decided to conduct a baseline gender analysis and a constraints analysis for faba bean in Egypt to understand the reasons for the decline in the faba cropping area and production. The collaborator is Dr. Ragab Hassan Ahmed, a scientist in ARC. The socioeconomic work plan for Egypt during 2013 will focus on faba bean and will include the following activities:

- Reviewing secondary data and analyzing of faba bean productivity trends

- Analyzing the productivity gaps of wheat and food legumes systems

- Monitoring and assessing the technical performance and economic viability of faba bean tested technologies

- Conducting a baseline survey at the national level

- Conducting a gender analysis

- Conducting an ex-ante assessment of potential impact.

- Adoption studies

The activities planned for the adoption studies are:

- Review secondary data

- Carry out a baseline survey

- Conduct an ex-ante assessment of the potential impact for the tested technologies

- Document adoption and impact of improved varieties.

- Analysis of the productivity gaps in wheat and food legume and the determinants of these gaps

This activity will be part of the baseline study that will be conducted in 2013 in Egypt. The other countries are called on to organize national workshops with all stakeholders to identify the main constraints to the wheat-legume system productivity.

- Research capacity of national programs enhanced through training and networking

During 2011 and 2012, a total of 12 trainees (six trainees/year) underwent individual training in the ICARDA-INRA Cooperative Research Project in Morocco. The trainees – two from Egypt, two from Tunisia, one from Algeria and seven from Morocco – are graduate students (PhD, MSc, BS) who did part of their research (between one and three months) at ICARDA. Although the trainees are not directly sponsored by the project, most of them are working in the national program of the institutions involved in the project and the project contributed by covering part of the chemicals and laboratory supplies for the training course.

ICARDA offered training to participants from Iraq and Egypt in ‘Biotechnology Applications in Crop Improvement’ 16-26 September, 2012, in Cairo, Egypt, in cooperation with Agricultural Genetic Engineering Research Institute.

The training of young NARS scientists in new techniques, such as doubled haploid breeding, marker assisted selection, and transformation will continue as a group activity during 2013 and some of the trainees will be supported by the project.

Several regional short-term courses will be organized, mainly in spring 2013, in different countries. These will include:

- Classical and molecular approaches for wheat breeding – Egypt, 10-21 March 2013

- Food legume breeding – Lebanon, 8-19 April 2013

- Integrated pest management in cereal and food legume – Algeria, 21-30 April 2013

- Seed science and technology and variety maintenance – Turkey, June 2013.

Furthermore, it is planned to organize small group training on supplemental irrigation, GIS and remote sensing, and doubled haploid and marker assisted selection. An MSc student will start her research in Jordan on supplemental irrigation of wheat in 2013. Support for PhD and MSc students will be ensured according to need and the availability of sufficient funds.

Sponsorships for other activities (supporting the participation of some scientists involved in the project in international workshops and conferences and on exchanges of visits) will depend on the approval of the Steering Committee and the availability of funds.

A list of beneficiaries of the training on ‘Classical and molecular wheat breeding’ (Egypt, 10-21 March 2013), on ‘Food legume breeding’ (Lebanon, 8-19 April 2013) and on ‘Integrated pest management in cereal and food legume’ (Algeria 21-30 April 2013), supported by the project, constitutes Annex C. Almost half of the participants are female.

Objective 2: Development of new germplasm and production technologies to cope with climate change

Under this objective the expected outputs/outcomes include the following:

- New wheat and food legume genotypes, better adapted to climate variability and change

The breeding programs conducted at ICARDA continue to introduce all available sources of resistance or tolerance to the main identified biotic and abiotic stresses and for grain quality traits into high yielding genetic backgrounds. Hybridization is used to select and develop high yielding multiple stress-tolerant/resistant lines with higher quality. A major effort was undertaken to screen new collections of wheat and food legumes to identify new sources of resistance and tolerance to different biotic and abiotic stresses for the purpose of broadening the genetic basis of the resistance.

Many new sources of resistance, either in the cultivated species or in wild relatives, have been identified for different biotic and abiotic stresses.

Every year ICARDA is proposing to the NARS hundreds of new improved high yielding lines of wheat (bread and durum) and food legumes (faba bean, chickpea, and lentil) carrying resistance to more than one pathogen/pest and tolerating drought, cold, and salinity. The proposed material was selected and tested in different environments through the collaboration that the Center has established with its NARS partners. The advanced lines proposed in the different nurseries distributed to the NARS will increase the number of released varieties in the region. These new lines have better performances than existing ones and they are expected to replace the older varieties that are still grown widely in the region (in North Africa for example, old wheat varieties are still widely grown). Farmers in the region can take advantage of this material to reduce the costs of production and reduce the risk of losing their harvest from the different stresses that they are facing.

Consolidating the interaction between ICARDA and the NARS breeders and associating farmers during final evaluations will help to identify superior and desirable genotypes and improve adoption of the released varieties. The project, through the activities implemented in the different countries – mainly those conducted in farmers’ fields – is encouraging and supporting this interaction. In 2012/13, the wheat program sowed large plots of many advanced and promising lines in Merchouch (Morocco), Sids (Egypt), and Terbol (Lebanon) for the purpose of participatory selection with the national breeders and farmers.

Several collaborators in the project region benefit from ICARDA’s nurseries for wheat and food legumes. In the 11 countries (Algeria, Egypt, Iraq, Jordan, Lebanon, Libya, Morocco, Syria, Sudan, Tunisia, and Turkey) involved in the project there were 45 collaborators in 2011 and 39 in 2012.

When requested, ICARDA is supporting the national programs by providing seeds of early generations (breeder and foundation seed) of the released varieties originating from the Center. This way, farmers can quickly benefit from the advantages of the newly released varieties. In Libya, four durum wheat cultivars were selected and multiplied and 250 kg of seed from each were provided to the Libyan ARC. Beltagy3, Icarasha, and Adnan are the most promising lines.

During the last two years, several ICARDA durum wheat varieties have been released, mainly in Lebanon, Morocco, Algeria, Turkey, and Ethiopia. In Algeria, in addition to the ICARDA line Heider – released as Boussalem-03, and which has a higher yield than the widely grown Waha, Vitron, Ammar1, and Ammar6 – a new cultivar was released as Beni Mestina (Lahn/Cham1-2003) in 2011. In Tunisia, recently released cultivars are Maali, Nasr, and Salim; the latter two are Septoria resistant. In Egypt, breeders have identified Ainzen – released as Bani Suef – which is under multiplication. In Morocco, the IRDEN Hessian fly resistant varieties continue to be adopted by farmers replacing the susceptible ones. An additional advantage of the ICARDA Hessian fly resistant varieties is their tolerance to drought and heat. In favorable seasons with no drought or Hessian fly infestation, the yields of the resistant varieties are similar to or higher than the commercial cvs. Karim and Tomoh (Omrabi 6). One Icamor line Hessian fly resistant is released as Faraj; it also shows resistance to Septoria tritici and to leaf rust in Morocco. Ammar10 has been released also. It has a high yellow pigment value. In Jordan, UmQais (Omrabi 5) has been released and is under multiplication. Further, Lahnhaucan is being grown by farmers. Several lines have been tested in farmers’ fields and show good yields under dryland conditions. The cultivars Lahnhaucan and Younès are the most promising in Jordan. In Syria, the ICARDA originated varieties Douma-1, Bouhouth-7, Bouhouth-9, and Cham5 out-yielded the widely grown cultivars Cham1 and Cham3. The 2010 released Cham9 (Miki3) has been multiplied on a large-scale. It is resistant to all three leaf rusts and tolerant to Septoria tritici. In Lebanon, several varieties have been released or submitted for release. These include Miki3, Icarasha, Lahn, Asghar2, and Lahnhaucan. The Zahlé cv. with a red grain has been multiplied. In 2010 in Turkey, in addition to the early release of Gidara, the ICARDA line Ammar6 was released as Gundus. In Sudan, early and heat tolerant lines have been identified; the most promising genotype is Icajihan22.

The project is helping popularize most of the varieties released for the benefit of the farmers and thus contributing in improving the food security in the project region.

- Sustainable wheat-legume rotation system established at the farm level

In many countries of the region, food legume crops are being replaced by monoculture of wheat or other crops providing more short-term benefits. The project is conducting on-farm demonstrations to highlight the beneficial effect of introducing legume crops into the cropping system. The Tunisian team chose the Kef region to demonstrate to farmers the positive effects of growing faba bean in the wheat system. Farmers in this region either follow cereal monoculture (wheat), wheat-barley or oat, or wheat after fallow rotations. The use of the faba bean variety Bachaar in this semi-arid region is appropriate since it can tolerate drought better than other varieties.

In Egypt, a national campaign to reintroduce faba bean into the cropping system in the traditional faba bean growing area is being enhanced in 2012/13. The new package is based on use of faba bean varieties tolerant to Orobanche, low doses of glyphosate and low seed planting density which allow farmers to minimize the yield losses resulting from Orobanche and foliar diseases and improves the profitability of the crop. Many farmers requested seeds of the tolerant varieties in order to adopt this package and reintroduce faba bean into the cropping system. In Jordan, the wheat-chickpea rotation is promoted by the project. In Algeria, lentil and chickpea crops have been introduced into the cereal monoculture system and in wheat-fallow to improve the productivity of the wheat and the soil fertility. Support has been given for the use of the certified seeds of grain legumes.

The IPM packages conducted in different countries at on-farm trials will consolidate the wheat-legume rotation for a sustainable crop production and improved food security.

- IPM options for key diseases, insect pests, and parasitic weeds with wide effectiveness demonstrated in farmers’ fields

One of the most important elements of IPM is the availability of high yielding and stress-tolerant varieties or any other no costly technology which can improve farmers’ yields substantially with reasonable costs.

IPM trials conducted by ICARDA showed interesting results in minimizing the damage caused by diseases and pests and improving the yield that could be transferred and, therefore, improving farmers’ incomes. The NARS also developed their IPM either for cereals and legumes for which higher yields are possible.

Following are some of the synthesized IPM results obtained at ICARDA which could be transferred and tested on-farm in the region.

- Integrated management of Ascochyta blight of faba bean under northern Syrian condition

Three seasons of trials were conducted on the disease parameters and yields. The conclusions reached were that if improved resistance faba bean varieties were not available to farmers like in Syria, then the integration of planting in November-December with one fungicide foliar spray at the vegetative stage would help reduce the severity of Ascochyta blight and reduce pod and seed infections. This would ensure, therefore, better seed quality.

- Integrated management of Fusarium wilt on chickpea:

Trials were conducted over two cropping seasons. The results led to the conclusion that integrating early planting (January) with genotypes carrying some levels of Fusarium wilt resistance can reduce the impact of Fusarium wilt and increase yield significantly.

- Integrated management for control Orobanche on faba bean:

On-farm demonstrations for the control of Orobanche on faba bean were conducted in 2012/13 in Egypt in 20 fields. In Dakahlia and Assiut in five on-farm demonstrations in each location, fields infested with Orobanche crenata were planted with the faba bean variety Giza 843 and in Sharkia, 10 on-farm demonstration fields were planted with the faba bean varieties Giza 843 and Misr 3 (Annex A. countries work plans). At all sites a low dose of glyphosate was delivered. Preliminarily results showed net control of Orobanche and substantial increases in the yields.

IPM on-farm demonstrations for controlling Orobanche were also undertaken in Tunisia and Morocco during the 2012/13 cropping season (Annex A. countries work plans).

Others IPM on-farm demonstrations are being conducted during the 2012/13 cropping season in different countries involved in the project (Annex A. countries work plans). These IPM on-farm demonstrations are for wheat, faba bean, and chickpea. They are designed particularly to control weeds, foliar diseases, root diseases, and insect pests. The demonstrations included:

- Integrated management of root rot on chickpea and foot rot on durum wheat in Tunisia

- Integrated management of winter and spring chickpea at Marchouch and Had Ait Mimou in Morocco

- Integrated management of foliar diseases on faba bean and chickpea in Tunisia

- Integrated management of weeds on wheat at Marchouch and Had Ait Mimou and grain legumes at Merchouch.

- GIS spatial analysis of dry area farming systems and geo-statistics of crop adaptation and disease/pest prevalence to help target technology interventions

Surveys of wheat and food legume diseases were conducted in Morocco during the 2011/12 cropping season and disease and insect suitability maps were developed by the ICARDA GIS Unit. The incidence of chocolate spot on faba bean varied from low to high in different areas of Morocco.

In 2012/13, the work on GIS and remote sensing will focus on the areas of Marchouch (Morocco) and Fernana (Tunisia) for disease and pest assessment and yield predictions.

- Tools for determining new supplemental irrigation schedules and packages for better adaptation of wheat-legume systems to climate change

In 2013, an MSc student from the Jordan University of Science and Technology will conduct a study on supplemental irrigation schedules and packages for wheat.

- Ex-ante assessments of the potential impacts of improved wheat/legume varieties and associated technologies on crop productivity, household income, and food supply documented for selected countries

In many of the countries involved in the project, farmers still grow the old varieties. For example in Tunisia and in Morocco, the durum wheat variety Karim, released in the 1980s, is still the one most frequently grown. Rust and Septoria resistant wheat varieties released in many countries in the region, will replace old varieties which are characterized by their higher susceptibility, but are still grown extensively in the region. The research results and on-farm testing of recently released varieties showed that some of these give net advantages in production and income over Karim. On-farm demonstrations conducted in 2010/11 within the ‘Enhanced food security in Arab countries’ project in Tunisia, indicated the net advantages of Maali, released in 2007 and commercialized since 2010 (Under irrigation in 2010/11, Maali gave 0.9 t/ha more than Karim and in rainfed conditions it produced 0.35 t/ha more [progress report of the project, October 2011]). The area cultivated under Maali is increasing quickly and it is expected that by 2014 it will be the number one variety of durum in Tunisia. This will have considerable impact on wheat production in the country. In Algeria, most of the durum wheat cropping area is under old varieties – Waha, Vitron, and Ben Bashir. It is expected that, progressively, the newly released varieties will replace the old.

In Morocco, encouragement should be given to increasing foundation seeds of those varieties locally selected to reach the goal fixed by the Morocco Green Plan regarding the use of certified seeds and to help in spreading varieties resistant to Hessian fly and other diseases particularly rust.

However, wheat productivity in the project area is lower than the world average. This difference is mainly because of the insufficient and variable rainfall and predominant poor crop management techniques used by most farmers. The potential for increasing wheat production will depend on the ability to increase productivity by farmers applying the research outcomes and adopting the new wheat technologies. Diffusion of improved cultivars, together with optimal agronomic practices, will assist in overcoming production shortfalls, help ensure continuity of an adequate grain supply, and improve the livelihoods of households in the region. It is necessary to make seed of the improved varieties available to farmers at the right time if wheat productivity is to be improved. Therefore, strengthening national seed systems through increased private sector participation and alternative delivery systems is needed.

For food legumes, the number of released varieties in the region is still insufficient and limited and needs to be augmented. An effort should be made to increase the number of released varieties and make them available to farmers at reasonable prices. Farmers have given up growing some food legumes because of the many constraints they are facing when using traditional varieties susceptible to diseases and pests and also from competition with other crops. The most relevant cases are faba bean in Egypt and Morocco. Faba bean varieties tolerant to Orobanche have been released in Egypt (Giza 843 and Misr 3) and Tunisia (Najeh). Popularization of these varieties in the region and their use with appropriate IPM will contribute to the improvement of households and food supply. Similarly, great progress has been made at ICARDA and the NARS in selecting chickpeas tolerant to Ascochyta blight, the major constraint of chickpea in the region. Those tolerant varieties, which can be used in winter sowings with appropriate IPM, will contribute to the improvement of the supply of this commodity in the region.

An economic surplus model was used to derive summary measures of the ex-ante impacts of faba bean improvement in Morocco. The model was developed by the project under certain reasonable assumptions for the research and benefits accruing from 2014 (when the improved technologies would begin to be adopted) to 2020. Table 9 summarizes the measures of the ex-ante economic, nutritional, and environmental impacts of faba bean research and extension in Morocco.

Table 9. Ex-ante impact assessment for the adoption of faba bean technology in Morocco

| Estimated adoption rate in 2020 (% of farmers using the technology in 2020) | 15 |
| --- | --- |
| Estimated increase in yield (kg/ha) | 1,264 |
| Present value of gross benefit (USD) at a discount rate of 5% | 49,019,472 |
| Average annual increase income (USD) | 6,127,434 |
| Additional food supply (t/year) | 17,958 |
| Additional availability of protein (t/year) | 5,387 |
| Additional N availability in soil (t/year) | 1,446 |

- The impacts of selected crop diseases evaluated and farmers’ perceptions and practices in managing plant diseases analyzed

A study the impact of the main diseases on wheat and food legume production and farmers’ perceptions and practices is planned for 2013. The study will use surveys in some of the countries involved in the project to assess the impact of diseases and pests on crop yields and to study farmers’ awareness, perceptions, and practices. Once the information collected has been analyzed it will be assembled in one document and shared. In Morocco, scientists from the IPM group with INRA’s research team did a survey on wheat and food legume diseases and pest in March 2013.

  - Progress based on activities undertaken

The main activities undertaken under Objective 1: ‘Promotion of proven and tested technologies for wheat–legume rotation systems by scaling out existing improved wheat and food legume varieties and associated production technologies, while concurrently identifying and testing appropriate new technologies to sustainably improve productivity and production‘ are:

- Baseline studies, and gender and constraints analysis

A preliminary baseline study and gender and constraints analyses were initiated in Morocco in 2011/12 as mentioned previously and will be finalized at the end of 2013. The study on the faba bean situation in Egypt was initiated in 2013 and will be finalized at the end of 2013. Furthermore, scientists from the Socio Economic Policy Research Program of ICARDA are helping to develop a questionnaire to be conducted in other countries for better understanding the place of food legumes in the cropping system in the countries involved in the project and to identify the main constraints for the development of legumes in the WANA region.

Surveys were conducted in some countries to improve understanding of the plant health on some food legume crops. Importance of some diseases and pests and their effect on grain yield were determined, including the following:

- Survey of faba bean viruses in Sudan in 2012

- Survey of faba bean viruses in Tunisia in 2011 and 2012

- Survey of foliar diseases of faba bean in Morocco in 2012.

- Survey of diseases and viruses in Sudan in 2013

- Survey of diseases, pests and viruses in Morocco in 2013

- On-farm varietal trials of wheat and legumes

The seed section at ICARDA produced foundation seed of released varieties and promising lines of durum and bread wheat, faba bean, chickpea, and lentil during the 2010/11 and 2011/12 cropping seasons. Most of this seed was distributed to researchers, NARS, and technology transfer projects for variety popularization and demonstration purposes during the 2011/12 cropping season. Produced seed of wheat and food legumes during the 2011/12 cropping season could not be distributed due to the situation in Tel Hadya at this time. The amount of seed produced and distributed in 2011 and 2012 is shown in Tables 10 and 11.

Table 10. Elite seed production and distribution in the 2010/11 cropping season

| Crops | Production (tonne) | Number of varieties/lines | Distribution (tonne) |
| --- | --- | --- | --- |
| Durum wheat | 6.250 | 50 | 5.960 |
| Bread wheat | 17.214 | 267 | 13.828 |
| Sub-total | 23.464 | 317 | 19.788 |
| Faba bean | 0.398 | 24 | 0.398 |
| Chickpea | 26.094 | 1,731 | 2.119 |
| Lentil | 6.350 | 16 | 5.600 |
| Sub-total | 32.842 | 1,771 | 8.117 |
| Total | 56.306 | 2,088 | 27.905 |

Note: For bread wheat and chickpea this includes 240 and 1700 lines of international nurseries, respectively

Table 11. Elite seed production in the 2011/12 cropping season

| Crops | Production (tonne) | Number of varieties/lines | Distribution (tonne) |
| --- | --- | --- | --- |
| Bread wheat | 2.0 | 1 | 0 |
| Durum wheat | 6.0 | 60 | 0 |
| Sub-total | 8.0 | 61 | 0 |
| Faba bean | 0.1 | 28 | 0 |
| Chickpea | 6.0 | 12 | 0 |
| Lentil | 5.0 | 4 | 0 |
| Vetch | 1.0 | 1 | 0 |
| Sub-total | 12.1 | 45 | 0 |
| Total | 20.1 | 106 | 0 |

Seven countries (Algeria, Egypt, Jordan, Lebanon, Sudan, Tunisia, and Turkey) were involved in on-farm demonstrations of high yielding and stress-tolerant varieties of wheat and food legumes during the 2012/13 cropping season (Table 12).

The countries’ work plans and additional information on the on-farm demonstrations and verification trials are given in Annex A.

Table 12. Recently released varieties of bread and durum wheat, faba bean, chickpea, and lentil demonstrated on-farm during the 2012/13 cropping season in countries involved in the project

| Countries | Bread wheat |  | Durum wheat |  | Faba bean |  | Chickpea |  | Lentil |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Varieties | Area (ha) | Varieties | Area (ha) | Varieties | Area (ha) | Varieties | Area (ha) | Varieties | Area (ha) |
| Algeria | Ain Abid, Wifak | 0.566 | Cirta, Bousselam, Setifis, Megress | 0.1025 |  |  | Ghab4, Ghab5, FLIP97-42C, FLIP84-92C, (FLIP88-85C) | 4.0 | Syrie 229, Dahra | 2.05 |
| Egypt |  |  |  |  | Giza 843, Misr 3, Nubaria 2, Nubaria 3, Sakha 4 | 14.4 |  |  |  |  |
| Jordan | Ammon | 0.5 | ACSAD1187 ACSAD1275 | 4.5 |  |  |  |  |  |  |
| Lebanon |  |  | Mikki3, Ikarasha | 1.1 |  |  | FLIP97-706C, FLIP97- 7C | 0.9 |  |  |
| Sudan |  |  |  |  | Ed-Damer, Hudeiba93, SML | 7.9 | Wad Hamid, Shendi, Burgieg, Atmour, Hawata, Jebel Mara | 6.25 |  |  |
| Tunisia | Tahent | 0.0180 | Maali, Nasr, Salim | 4.527 | Bachaar Badi | 30.0 | Beja 1, Nayer, Bouchra | 4.977 | Siliana, Kef | 0.125 |
| Turkey | Altay, Mufitbey, Nacibey, Es-26 | 1.0 | Gundas, Icajoudy | 2.0 |  |  | Aksu, Azkan, Hisar, Cakir, Gökçe, Canitez | 1.5 |  |  |

In Algeria, during the 2012/13 cropping season, on-farm demonstrations of recently released varieties of chickpea, lentil, and durum and bread wheat were conducted in several locations (Didouche Mourad, Guellal, Mellakou, Ferdjioua, Ain Smara, Mouzaia, Saf-Saf, Ammari, and Sidi Khelifa) characterized by their contrasting environments (Annex A work plan of Algeria). The total areas sown in farmers’ fields were 4 ha of chickpea, 2.05 ha of lentil, 0.1025 ha of durum wheat, and 0.566 ha of bread wheat (Table 12).

On-farm verification trials were planted in three locations (Didouche Mourad: two durum and four bread wheat; Benifouda: one durum; and Ain Abessa: one durum). These varieties were compared to some varieties that are widely cultivated in Algeria. Seed increase and maintenance of early generations (breeder and foundation seed) of wheat, chickpea, and lentil recently released varieties and promising lines were done in several ITGC experimental stations (‘Ferme de développement et de production de semences’ - FDPS) at El Khroub, Sétif, Oued Smar, Tiaret, Guelma, and Sidi Bel Abbes. This activity was supported by the project in order to provide sufficient seed to increase the number of demonstrations in the coming seasons, and to contribute to the expansion of the new varieties in Algeria (Annex A work plan of Algeria 2013).

In Egypt, in the 2012/13 cropping season, ARC conducted 15 on-farm demonstrations of recently released faba bean varieties in two regions: Nubaria (10 demonstration fields to promote cvs Nubaria 2 and Nubaria 3) and Kafr Al-Sheikh (five demonstrations to promote cv Sakha 4). One demonstration field in Nubaria was discarded. These on-farm demonstrations were conducted in fields that were not infested by Orobanche. More information about these demonstrations is presented in Annex A (work plan 2013 of Egypt). Another 20 on-farm demonstrations were conducted in Orobanche infested fields using cvs Misr 3 and Giza 84. ARC also carried out on-farm verification trials in North Egypt (Sakha, Behira, and Nubaria), Middle Egypt (Minia, Mallawy, and Sids), and Upper Egypt (Mataana, Assiut, and New Valley) in the 2012/13 cropping season. Information on these demonstration trials is given in Annex A (work plan 2013 of Egypt). Furthermore, on-station seed increase (foundation and breeder seed) and maintenance of recently released varieties were performed in Nubaria and Sakha Research Stations of ARC. Three faba bean varieties (cvs Nubaria 2, Nubaria 3, and Misr 3) were increased in Nubaria, and two (cvs Sakha 4 and Giza 843) in Sakha. The produced seeds will be used for on-farm demonstrations in the 2013/14 cropping season and for delivery to seed companies for production of certified seed. In 2012/13 cropping season, ARC is performing different ICARDA faba bean trials at Gemmiza and Sids Research Stations.

In Jordan, during the 2012/13 cropping season, NCARE conducted on-farm demonstrations of recently released varieties of durum and bread wheat in Irbid (two demonstrations of durum) and in Ma’daba (one demonstration each of durum and bread wheat) (Annex A work plan of Jordan 2013). On-farm and on-station participatory evaluation trials were conducted on durum wheat and chickpea in Maru, Mushager, and Rabba. NCARE also increased and maintained recently released varieties of durum wheat (three varieties), bread wheat (one variety), and chickpea (one variety) on 9 ha in Mushagher Research Station (Annex A work plan of Jordan 2013). The varieties most recently released in Jordan were bread wheat cv Ammon and durum cv Om Quis, registered in 2008. NCARE intends to submit a durum wheat variety for release in 2013.

In Lebanon, LARI carried out on-farm demonstrations with recently released varieties of durum wheat and/or in the process of release for chickpea in Al Qaa in the 2012/13 cropping season (two demonstration fields with durum wheat and chickpea), Deir El Ahmar (one demonstration field with durum wheat and chickpea), Majdaloun (one field with durum wheat and chickpea), Zahlé (two fields with durum wheat and chickpea), and Taanayel (one demonstration field with chickpea). More information is presented in Annex A work plan of Lebanon for 2013. LARI also conducted seed increase and maintenance of two recently released chickpea varieties and two other promising lines at Keferdan Station in the 2012/13 cropping season.

In Morocco, in fields of Marchouch Research Station, INRA conducted seed increase and maintenance of recently released varieties (eight of durum wheat, one bread wheat, four faba bean, four chickpea, and six lentil) during the 2012/13 cropping season (Annex A work plan of Morocco for 2013). Three promising lines of the faba bean minor-type, and three of the major type, were increased in Marchouch; and 96 lines of bread wheat with resistance to Hessian fly were increased at Jmaat Shim and Sidi Aidi Research Stations.

In Sudan, during the 2012/13 cropping season, ARCo conducted 13 on-farm demonstrations of faba bean in Nile River State, Lower Atbara, and Northern State and three of chickpea in Lower Atbara, Salwa area, and Gezira State (Annex A work plan of Sudan 2013). Several field days were organized and many farmers participated. On-station seed increase and maintenance of recently released varieties were performed in the 2012/13 cropping season in isolated fields at Hudeiba Research Station, where four faba bean (cvs Hudeiba 93, Ed-Damer, BB7, and SML) and three chickpea (cvs Burgieg, Atmour, and Hawata) varieties were increased. ARCo also conducted on-station participatory evaluation trials of faba bean and chickpea in different locations (Hudeiba, Merowe, Shendi, and Medani). ARCo expects to propose two new varieties each of faba bean and chickpea in 2013.

In Tunisia, there were on-farm demonstrations with recently released varieties of faba bean, chickpea, lentil, durum, and bread wheat (17, seven, four, five and one fields, respectively) – covering the main production area of those crops. The on-farm demonstrations focused on promoting the cultivation of faba bean minor-type in Kef region, particularly cv Bachaar. For promising lines of durum there were one on-station and four on-farm verification trials, and for bread wheat one on-station and three on-farm trials. On-farm participatory evaluation trials of faba bean and chickpea were implemented in different locations: Boussalem, Kef, Sidi Ismail, Sidi Shili, and Mateur. The Tunisian program conducted seed increase of faba bean, chickpea, and lentil varieties at the on-farm level in different locations – and of durum and bread wheat, faba bean, chickpea, and lentil in five research stations – in order to provide farmers with sufficient seed for conducting more on-farm demonstrations for the 2013/14 cropping season. During the 2012/13 cropping season, Tunisian institutions involved in the project implemented several faba bean, chickpea, and lentil trials for participatory evaluation in three research stations: Oued Mliz, Beja, and Kef. More information is presented in Annex A work plan of Tunisia 2013.

In Turkey, on-farm demonstrations of recently released varieties were done during the 2012/13 cropping season with bread wheat (two fields at Usak and Eskisehir-Hamidye), durum wheat (two fields at Siverek and Talat Demiroren Koruklu), and chickpea (four fields at Usak, Yavuzeli, Eskisehir-Hamidye and Talat Demiroren Koruklu) as mentioned in Annex A work plan of Turkey in 2013. Furthermore, on-farm verification trials of promising lines were conducted at Siverek for durum wheat; at Eskisehir-Hamidiye and Usak for bread wheat; and at Araban, Usak, and Yavuzeli for chickpea. Most of chickpea will be planted in spring (March–April). On-station demonstrations of promising durum wheat lines were sown in TDO Koruklu Research Station. The national program expects to propose four bread wheat, five durum wheat, and six chickpea varieties in 2013.

- WANA yield trials for wheat and legumes

The cereal (bread and durum wheat) and food legume (faba bean, chickpea, and lentil) breeding programs at ICARDA annually prepare a set of various international nurseries to share with NARS partners. The germplasm is evaluated in partnership with NARS to release superior, adapted, and farmer-preferred varieties for commercialization to increase production and productivity.

Tables 13 and 14 show the number of nurseries distributed to the countries involved in the project in the 2011/12 and 2012/13 cropping seasons, respectively.

Table 13. Number of international nurseries distributed in the 2011/12 cropping season

| Country (collaborators)1 | Crops2 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Bread wheat | Durum wheat | Faba bean | Chickpea | Lentil | Grass pea | Total |
| Algeria (2) | 8 (4) | 5 (1) | 4 (1) | 16 (5) | 13 (4) | 1 (1) | 47 (16) |
| Egypt (8) | 81 (11) | 14 (2) | 17 (6) | 15 (9) | 17 (5) |  | 144 (33) |
| Iraq (2) | 1 (1) | 2 (2) | 2 (1) | 2 (1) | 2 (1) |  | 9 (6) |
| Jordan (2) | 1 (1) | 5 (2) |  | 4 (4) | 5 (3) |  | 15 (10) |
| Lebanon (1) | 1 (1) | 2 (2) |  |  |  |  | 3 (3) |
| Libya (1) |  |  | 5 (5) | 4 (4) | 7 (7) | 3 (3) | 19 (19) |
| Morocco (8) | 54 (13) | 12 (2) | 12 (7) | 17 (9) | 16 (13) | 1 (1) | 112 (45) |
| Sudan (2) | 19 (8) | 1 (1) | 2 (2) | 10 (6) | 5 (5) |  | 37 (22) |
| Syria (1) | 10 (9) | 3 (2) | 22 (7) | 27 (7) | 21 (7) | 25 (5) | 108 (38) |
| Tunisia (3) | 12 (8) | 8 (2) | 16 (7) | 31 (11) | 15 (12) |  | 82 (40) |
| Turkey (15) | 22 (8) | 6 (2) | 5 (5) | 4 (4) | 7 (7) | 3 (3) | 47 (29) |
| Total (45) | 209 (64) | 58 (18) | 85 (41) | 130 (60) | 108 (64) | 33 (13) | 623 (260) |

Note: 1 number of collaborators in each country across all cereal and legume nurseries

2 numbers in brackets represent sets received from a total available set of international nurseries.

Table 14. Number of international nurseries distributed in the 2012/13 cropping season

| Country (collaborators)1 | Crops2 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Bread wheat | Durum wheat | Faba bean | Chickpea | Lentil | Grass pea | Total |
| Algeria (2) | 6 (3) | 7 (2) | 1 (1) | 11 (7) | 6 (6) | - | 31 (19) |
| Egypt (4) | 18 (3) | 4 (2) | 9 (7) | 8 (7) | 10 (10) | - | 49 (29) |
| Iraq (3) | 11 (5) | 8 (4) | 7 (3) | 5 (3) | 2 (2) | 2 (2) | 35 (19) |
| Jordan (1) | 3 (3) | 1 (1) | - | - | - | - | 4 (4) |
| Lebanon (1) | 1 (1) | 3 (3) | 4 (4) | - | - | - | 8 (8) |
| Libya (2) | - | 2 (1) | 3 (3) | 10 (5) | 2 (2) | 6 (3) | 23 (14) |
| Morocco (5) | 9 (3) | 10 (2) | 3 (2) | 12 (7) | 10 (9) | - | 44 (23) |
| Sudan (1) | - | - | 2 (2) | 6 (5) | 5 (5) | - | 13 (12) |
| Syria (2) | 12 (3) | 9 (3) | 29 (8) | 25 (7) | 21 (7) | 25 (5) | 121 (31) |
| Tunisia (5) | 6 (3) | 9 (3) | 18 (8) | 28 (10) | 12 (10) | 2 (2) | 75 (36) |
| Turkey (12) | 19 (3) | 7 (3) | 12 (6) | 14 (10) | 14 (14) | 4 (4) | 70 (40) |
| Total (38) | 85 (27) | 60 (24) | 88 (44) | 119 (61) | 82 (65) | 39 (16) | 473 (236) |

Note: 1 number of collaborators in each country across all cereal and legume nurseries

2 numbers in brackets represent sets received from a total available set of international nurseries.

Bread wheat

In 2011, the seed section of ICARDA distributed 14 different bread wheat international nurseries to NARS institutions in 10 countries involved in the project. In total 209 sets of nurseries were provided to NARS institutions in the project area. In 2012, three different bread wheat nurseries or trials were proposed and 85 sets were distributed – most reached the NARS with significant delays due to the prevalent situation in Syria.

The seed section conducted seed increase in the 2012/13 cropping season on 0.5 ha at the American University of Beirut (AUB) farm in Beka Valley, Lebanon, for 150 lines of bread wheat to be included in the international nurseries of 2013/14. Cognizant of circumstances, preparation and distribution of international nurseries for the 2013/14 cropping season will be handled from Lebanon.

Durum wheat

The seed section distributed two and three different durum wheat nurseries to NARS of 10 countries during the 2011/12 and 2012/13 cropping seasons, respectively: 58 and 60 sets were distributed to collaborators in the two respective seasons.

The seed section increased 239 lines of durum wheat on 3.3 ha of the AUB farm in Beka Valley, Lebanon, in the 2012/13 season. These are to be included in the international nurseries for 2013/14.

Faba bean

In 2011, the seed section distributed seven different faba bean international nurseries to NARS institutions from nine countries involved in the project – 85 sets were distributed. In 2012, there were eight faba bean nurseries provided and 88 sets were distributed to 10 countries – most reached the NARS with significant delays due to the situation in Syria.

The seed section increased 330 faba bean lines on 3.3 ha of the AUB farm in Lebanon, in the 2012/13 cropping season. These are to be included in the international nurseries of 2013/14.

Chickpea

In 2011, the seed section distributed 15 different chickpea international nurseries to NARS institutions from 10 countries involved in the project – a total of 130 sets were sent. In 2012, the number of proposed chickpea nurseries was 13 nurseries (119 sets) distributed to nine countries – some reached the NARS with delays due to the situation in Syria.

The seed section increased 389 chickpea lines on 4.3 ha of the AUB farm in Lebanon, in the 2012/13 cropping season. These will be included in the international nurseries of 2013/14.

Lentil

In 2011, the seed section distributed 15 different lentil international nurseries to NARS institutions from 10 countries involved in the project – 108 sets were sent. In 2012, there were 14 lentil nurseries (82 sets) distributed to nine countries; however, most reached the NARS with significant delays due to the situation in Syria.

The seed section increased 389 lentil lines on 2 ha of the AUB farm in Lebanon in the 2012/13 cropping season. These lines will be included in the international nurseries of 2013/14.

- Demonstrate IPM options for insect pests and soil-borne and foliar diseases

Integrated Management of Ascochyta Blight on Faba Bean under Northern Syria Conditions: Integrated disease management options with two sowing dates, three fungicides, and six faba bean genotypes were evaluated in northern Syria for their effects on disease parameters, seed quality, and dry seed yield.

Integrated Management of Fusarium Wilt on Chickpea: A study was conducted to develop integrated management of Fusarium wilt using chickpea genotypes, sowing dates, and fungicide seed treatments in naturally infested plots in farmers’ fields and research stations for two consecutive cropping seasons.

Integrated Management of Root Rot on Chickpea and Durum Wheat: In Tunisia, during the 2012/13 cropping season, one on-farm demonstration on root rot of chickpea was implemented in Mateur and another of foot rot of durum wheat in Boussalem (Annex A work plan Tunisia 2013).

Integrated Management of Winter and Spring Chickpea: On-farm demonstrations on control of diseases for winter and spring chickpea were conducted in Had Ait Mimoun and Marchouch, respectively, during the 2012/13 cropping season (Annex A work plan Morocco 2013).

Integrated Management of Foliar Diseases of Faba Bean and Chickpea: On-farm demonstrations were implemented in Fahs (faba bean and chickpea), Fernana (faba bean), and Beja (chickpea) during the 2012/13 cropping season (Annex A work plan Tunisia 2013).

Integrated Management of Weeds of Wheat and Grain Legumes: On-farm demonstrations on weed control in wheat in Marchouch and Had Ait Mimoun, and on grain legumes in Marchouch, were conducted during the 2012/13 cropping season (Annex A work plan Morocco 2013).

Integrated Management of Bromus on Durum Wheat: Three on-farm demonstrations on Bromus control in durum wheat at Nkhilat, Brachwa, and Had Ait Mimoun were conducted during the 2012/13 cropping season. Two Farm Field Schools (FFS) were conducted in 30 January and 19 February 2013, respectively, in Had Ait Mimoun and Marchouch with the participation of more than 90 farmers (Annex A work plan Morocco 2013).

Integrated Management for Control of Orobanche in Faba Bean: On-farm demonstrations for control of Orobanche in faba bean were conducted in 2012/13 in Egypt (20 fields), Morocco (two fields), and Tunisia (two fields).

In Egypt, in Dakahlia and Assiut, five on-farm demonstrations in fields infested with Orobanche crenata were implemented in each location using faba bean cv Giza 843; and in Sharkia, 10 on-farm demonstrations were conducted using faba bean cvs Giza 843 and Misr 3 – all were in combination with low doses of glyphosate (Annex A work plan Egypt 2013).

In Tunisia, on-farm demonstrations for Orobanche management in faba bean and winter chickpea were conducted in Hammam Sayala (Annex A work plan Tunisia 2013).

- Demonstrating CA technologies in farmers’ fields

Several on-farm demonstrations were conducted in Algeria, Egypt, Jordan, Lebanon, Morocco, and Tunisia in 2012/13 season.

In Algeria, on-farm demonstrations on CA for bread and durum wheat and lentil were conducted during the 2012/13 cropping season. For durum wheat, the demonstrations were planted in Milla, Sebaine, and Ain Arnat; for bread wheat in Sabaine; and for lentil in Sebaine and Ain Arnat (Annex A work plan of Algeria 2013).

In Egypt, two on-farm demonstration fields of CA with faba bean were implemented: in Al-Sharkia using cv Misr 3 (0.81 ha) and in Dakahlia with cv Giza 843 (0.41 ha) (Annex A work plan of Egypt 2013).

In Jordan, two on-farm demonstrations of CA technology for durum wheat were conducted during the 2012/13 cropping season in Raba and Mushager. There were six on-farm demonstrations of chickpea in Raba, Mushager, and Maru (three, one, and two fields, respectively) (Annex A work plan of Jordan 2013).

In Lebanon, on-farm demonstration of CA technology was conducted in Zahlé on durum wheat during the 2012/13 cropping season (Annex A work plan of Lebanon 2013).

In Morocco, on-farm demonstrations of CA technology were conducted on bread wheat and lentil in Brachwa and Ain Sbit during the 2012/13 cropping season (Annex A work plan of Morocco).

In Tunisia, on-farm demonstrations of CA were implemented on durum wheat in Kef, Fernana, and Koudia; and on faba bean at Fernana during the 2012/13 cropping season (Annex A work plan of Tunisia).

- Conduct regional courses for technical managers and technical staff on seed technology, seed marketing, and seed enterprise development

A regional course on Seed Science and Technology and Variety Maintenance is scheduled in Turkey for two weeks in June 2013. The course will include 12 participants from countries involved in the project.

- Monitor and assess technical performance and economic viability of farmer-based seed enterprises

In several countries involved in the project the seed production of food legumes is almost absent or cannot satisfy the need of farmers to access new varieties released and so benefit from their advantages. Therefore establishment of farmer groups that may take responsibility for increasing and selling the seed of improved varieties may enable farmers to access the technology and to use better genetic material. The project is seeking such groups of farmers to take the lead in ensuring this task is undertaken in the absence of state or private companies.

- Training of NARS in new techniques such as doubled haploid breeding, marker assisted selection, and transformation

Training of scientists was conducted in 2011 and 2012 on doubled haploid production and marker assisted selection as mentioned earlier in this report.

- Train two PhD, three MSc, and three long-term and 10 short-term trainees in breeding and associated disciplines

The project contributed in sponsoring research of some PhD and MSc students.

- One PhD student from Syria completed his thesis.

- Three PhD (two from Syria and one from Sudan) and one MSc (Syria) students are doing their theses research in chickpea and lentil diseases in Syria. Two of the PhD students are female.

- Ten students from Morocco (four in 2011 and six in 2012) completed their MSc under co-supervision of an ICARDA scientist (Dr. S. Udupa) and University/INRA Morocco within the ICARDA-INRA Cooperative Research Project in Morocco and the EU-IFAD project.

- During 2011 and 2012, a total of 12 trainees were trained on biotechnology.

The proposed training program for 2013 was prepared with Capacity Development Unit at ICARDA according to the needs expressed in the project document. During the last Steering Committee meeting (4 March 2013), it was decided to constitute a small group among the members to finalize the program according to the availability of funds and considering the cost of the course on Classical and Molecular Wheat Breeding as a reference (Egypt, 10–21 March 2013).

The initial program includes different courses:

- Classical and Molecular Approaches in Wheat Breeding in Egypt (10–21 March 2013): the project covered the participation costs of eight participants (young wheat breeders) from Algeria, Egypt, Jordan, Lebanon, Morocco, Sudan, Tunisia, and Turkey. Unfortunately, the Algerian candidate could not attend.

- Food Legume Breeding in Lebanon (8–19 April 2013): the project will cover the participation costs of 10 participants (young grain legume breeders) from Algeria, Egypt, Jordan, Lebanon, Morocco, Sudan, Syria, Tunisia, Turkey, and Yemen.

- Integrated Management of Cereal and Legume Pests in Algeria (21–30 April 2013): the project will cover the participation cost of eight participants from Algeria, Egypt, Jordan, Lebanon, Morocco, Sudan, Tunisia, and Turkey.

- Seed Science and Technology and Variety Maintenance in Turkey: (two weeks in June 2013): the project will cover the costs of participation of 12 participants from Algeria, Egypt, Iraq, Jordan, Lebanon, Libya, Morocco, Sudan, Syria, Tunisia, Turkey, and Yemen.

- Supplemental irrigation in Amman: (one week in May or June 2013): the project will cover the participation costs of 6–8 participants.

- GIS and Remote Sensing in Tunis: (one week in September 2013): the project will cover the participation costs of 4–6 participants.

- Marker Assisted Selection and Doubled Haploid breeding (to be determined): the project will cover the participation costs of four participants.

- MSc Student (Ms. Esra Kharabsheh): on supplemental irrigation (Jordan University of Science and Technology) with Dr. N. Vinay.

The project will continue to give partial financial support to PhD and MSc students from the involved countries in the project during 2013.

- Adoption and impact of improved wheat and legume varieties on crop productivity and household income documented in selected countries

The adoption and impact of improved wheat and legume varieties on crop productivity and household income will be assessed in the area of the project by estimating the increase in demand and use of the improved varieties and their effect in improving the income of farmers. Records on costs were taken by NARS involved in the project during the 2012/13 cropping season. The number of farmers visiting the on-farm demonstrations fields or on-farm/in-station verification trials requesting seeds of the new promoted varieties or willing to test other new technologies (CA, SI, IPM…) could be an immediate indicator to assess the success of the operation.

- Integrated supplemental irrigation and crop management techniques and deficit supplemental irrigation developed and tested in major agroecosystems of WANA

On-farm demonstrations were carried out in two fields located in Koudia using the recently released durum wheat cv Maali (Annex A work plan of Tunisia). Demonstration on supplemental irrigation of faba bean, chickpea, and lentil were also conducted in Al Gantra. In Algeria, on-farm demonstrations of supplemental irrigation were conducted on durum wheat in Mouzaia, Mellakou, El Amra, and Sidi Bel Abbes; and for bread wheat in Beriche (Annex A work plan of Algeria). In Egypt, on-farm demonstrations of faba bean varieties were conducted under supplementary irrigation. In most of the demonstrations implemented in northern Egypt, irrigation was limited to one or two irrigations; however, in Middle Egypt, two or three irrigations were applied. An experiment to study the effect of supplemental irrigation of spring sown chickpea under conventional and CA is planned to be conducted in LARI Tal Amara Research Station in 2013.

- One MSc student and 25 trainees trained through short courses and on-the-job for supplemental irrigation

Due to increased costs required for training outside of ICARDA’s Aleppo headquarters, it will be difficult to support training on supplemental irrigation for 25 attendees. Therefore the project will accept 6–8 participants for a regional or group training (Training of Trainers: ToT) and then each trainee will organize a national course in their country for local technicians and farmers. With this approach, much more than 25 participants will be trained in the region.

An MSc student from Jordan University of Science and Technology (Ms. Esra Kharabsheh) will be supervised on supplemental irrigation and scheduling the irrigation during 2013/14 by Dr. N. Vinay.

- Document and disseminate gender-related research to stakeholders, including policy makers

The documents produced by Socio-Economic Research Team and their partners in NARS on gender issues will be distributed to stakeholders and policy makers at the end of the project.

The main activities undertaken under Objective 2: ‘Development of new germplasm and production technologies to cope with climate change’ are:

- Strengthen pre-breeding and germplasm enhancement; including biotechnological approaches and genotyping and phenotyping of ICARDA’s genetic resource collections

The main objective of the breeding programs conducted at ICARDA is to develop pre-breeding genetic materials and improved breeding lines with tolerance to major abiotic stresses (cold, heat, and drought) and major diseases and pests of durum wheat, bread wheat, chickpea, faba bean, and lentil targeted to climate variability. The genetic materials proposed for NARS are bred in different environments making them largely adapted to the contrasting environments of WANA.

Bread wheat

- About 1000 new crosses were performed in spring of 2011 and 2012 to combine different traits among them: essentially yellow rust resistance, drought tolerance, yield potential, grain quality, and Hessian fly resistance.

- A nursery composed of 150 high yielding bread wheat spring genotypes with resistance/tolerance to major biotic and abiotic factors were distributed to project member countries for the 2011/12 and 2012/13 cropping seasons.

- CWANA yield trials for spring bread wheat, with 24 elite germplasm lines, targeting rain fed and irrigated wheat production systems separately were distributed to project member countries for the 2011/12 and 2012/13 cropping seasons.

- About 211 elite spring bread wheat genotypes were planted in large strip plots (10 m length, eight rows) each at Marchouch (Morocco), Terbol (Lebanon), and Sids (Egypt). At Marchouch, breeders and farmers from Morocco will be invited to undertake participatory variety selection. Sufficient seed of the selected varieties will be provided to the breeders of the respective countries. Similar demonstrations were carried out at Terbol (Lebanon) and Sids (Egypt) Research Stations for breeders and farmers of the respective countries.

Durum wheat

In the 2011/12 season, 1544 crosses were made for different required traits: 30% were with Triticum wild relatives; and 44 and 20% were crosses for Septoria tritici and Hessian fly resistance, respectively. These crosses were made with high yielding, improved quality, and abiotic stress-tolerant lines. The remaining crosses (6%) were for specific crosses (e.g. root rots, blackpoint, Sunn pest, and salt tolerance).

During the 2011/12 season, a set of 240 durum lines, with five durum checks, were tested for yield performance and morpho-physiological traits in five contrasting environments, including drought, heat, and cold stressed and high yielding environments. Promising durum advanced lines were identified with drought, heat, and cold tolerance; high yield potential and yield stability. The identified promising lines for the traits of interest were used extensively in the breeding program and/or shared with national programs in the region for testing in research sites and on-farm trials.

In the winter cycle of 2011/12, 1877 segregating populations were selected under double-gradient selection techniques (water and temperature regimes) for yield potential; tolerance to cold, drought and terminal stress; and resistance to yellow and leaf rust, Septoria tritici, blackpoint, and sawfly. In the summer cycle, 11,739 populations were selected for agronomic performance, tolerance to heat/drought and high radiation, and for resistance to dryland root rots, stem rust, BYDV, and aphids; bulked populations were advanced to winter 2013 selection.

Marker assisted selection was employed in bulked lines to select those with high water use efficiency (WUE), Septoria tritici and stem rust resistance, and high gluten strength and high levels of yellow pigment.

From the 240 advanced lines tested, those combining yield and tolerance to drought and temperature extremes, resistance to multiple diseases and insects, and improved grain quality were selected. They were multiplied and distributed in the 36th International Durum Observation Nursery (IDON) to NARS in CWANA (36 sites). Also, 19 of the most promising durum lines from the previous (i.e. 35th) IDON were advanced to 36th International Durum Yield Trial (IDYT) and distributed to NARS (45 sites).

The phenotyping performed included for traits such as grain yield, phenology, plant height, and morpho-physiological traits related to drought and heat. These trials were statistically analyzed for the phenotyped traits in different environments. Several drought-tolerant lines were identified and promoted for testing in farmers’ fields. The following physiological traits were scored: chlorophyll content, water index, normalized difference vegetation index.

Microsatellite markers (SSR) linked to drought and heat tolerance, which had been detected in ICARDA durum mapping populations, were probed on the promising durum lines within the marker assisted selection program. Associations were detected between identified drought quantitative trail loci (QTLs) discovered earlier in JKC1 and MDM populations with the grain yields of promising durum lines. Clustering analysis was performed for grain yield in different stress environments with the drought QTLs’ SSR. The 4B QTLs (gwm368) were detected on the population derived from JKC1 (Jennah Khetifa/Cham1) and the 3B QTLs (gwm376) on the population derived from Omrabi5/T. diccocoides//Omrabi5.

Faba bean

Faba bean is grown mainly under rainfed conditions with average annual rainfall above 400 mm in the CWANA region, except in the Nile Valley where it is irrigated. Due to climatic change and climatic variability faba bean suffers different stresses such as drought, heat, cold, and frost damage, as well as diseases and pests. The breeding objectives of the ICARDA program consist in development of high yielding autofertile genotypes with heat, drought, and cold tolerance, photoperiod insensitivity and resistance to different foliar diseases such as chocolate spot, Ascochyta blight, rust, and also to Orobanche parasitic weed. Segregating populations combining sources for resistance to diseases with materials adapted to different environments are generated. The F2 seed generation was advanced in the off-season in Terbol Station (Lebanon) with the goal to develop two generations per year and select genotypes insensitive to photoperiod with tolerance to heat stresses. Lines with resistance to diseases were developed in Lattakia (Syria) and Kafachajna (Lebanon) in semi-controlled environments with mist irrigation and spraying a mixture of the most virulent isolates. Faba bean segregating populations were screened for Orobanche crenata resistance in heavily infested soils in Lattakia and Tel Hadya (Syria) and in Giza (Egypt). Testing of faba bean for heat tolerance was done in Terbol (during summer) and in Sudan. Screening for drought was performed at Tel Hadya and in the 2012/13 season at Kafardan (Lebanon) and at Marchouch (Morocco).

In 2011 and 2012, the faba bean program performed 192 different crosses per year targeting the combination of different characters: high yield, autofertility, low tannin, low vicin and co-vicin, and resistance to foliar diseases, Orobanche, heat, drought, and cold.

Chickpea

During 2011 and 2012, there were 239 and 197 different crosses performed, respectively. The aim of these crosses is to improve the level of resistance to some diseases and pests, particularly Ascochyta blight, Fusarium wilt, and leaf miner and tolerance to drought, cold, and heat with high yield production and grain quality.

Lentil

In 2011 and 2012, the lentil breeding program performed around 250 different crosses per year targeting the combination of different characters: resistance to rust, Fusarium wilt, and sitona weevil and high yield, drought tolerance, and mechanical harvestability.

- Identify and characterize new sources of resistance/tolerance to biotic and abiotic stresses and their introgression into adapted germplasm

The new sources of resistance and tolerance to different abiotic and biotic stresses identified in the different crop species and in wild relatives are characterized and introduced into the high yielding genotypes. In wheat more than 2500 crosses are done annually and on food legume more than 600.

To determine the role of oxalic and malic acids in resistance to leaf miner, eight chickpea genotypes, with varying levels of resistance/susceptibility to leaf miner were evaluated at Tel Hadya under two planting dates (winter and spring). The collected leaf samples were analyzed at ICARDA using High Performance Liquid Chromatography (HPLC) for the different chemicals. Preliminary results showed a correlation between concentration of oxalic acid in leaves and resistance to leaf miner. These results show the potential of using oxalic acid content in leaves as a marker for resistance to leaf miner.

- Screen for abiotic stresses (drought, heat, and cold)

The screening for abiotic stresses is conducted in different locations for different crops. Several sources of resistance/tolerance have been identified and confirmed.

- Screening chickpea for cold tolerance at Tel Hadya (Syria): In 2011, chickpea advanced lines originating from F8 and F9 bulks (140 and 1439 lines, respectively), international nurseries (471 lines), international collections (Australia and Canada, 120 and 258 lines, respectively), Recombinant Inbred Lines - RILs (328 lines), known sources of resistance (58 lines), and wild species (65) were tested for cold tolerance. Twelve chickpea lines were used for demonstration trials. In 2012, chickpea advanced lines originating from F9 and F10 bulks (529 and 1437 lines, respectively), international nurseries (475 lines), international collections (Australia, Canada, Ethiopia, and USA: 221, 384, 143, and 212 lines, respectively), RILs (328 lines), known sources of resistance (208 lines), and wild species (65 lines) were tested for cold tolerance. Thirteen chickpea lines were used for demonstration trials.

- Screening chickpea for drought tolerance at Tel Hadya (Syria): In 2011, chickpea advanced lines originating from F7 and F8 bulks (117 and 119 lines, respectively), international nurseries and Preliminary Yield Trial for Drought Resistance – PYT-DR (548 lines), international collections (India: 300 lines), RILs (613 lines), and known sources of resistance (559 lines) were tested for drought tolerance. In 2012, chickpea advanced lines originating from F9 and F10 bulks (1024 and 1436 lines, respectively), international nurseries (472 lines), international collections (Australia, Ethiopia, and USA: 172, 143, and 212 lines, respectively), RILs (124 lines), and known sources of resistance (262 lines) and also for reconfirmation (820 lines) were tested for drought tolerance. Twenty chickpea lines were used for demonstration trials.

- Screening chickpea for heat tolerance at Terbol in summer sowing: In 2011 and 2012, 486 and 288 lines were evaluated for heat tolerance, respectively.

- Screening lentil for drought and heat tolerance: In 2011/12, the breeding program screened 150 lines for drought and heat tolerance.

- Screening of durum wheat for salt tolerance: Screening for salt tolerance was done at Fayoum Station in Egypt.

- Screening of wheat and faba bean for drought tolerance: Drought tolerance was assessed previously at Tel Hadya and in the 2012/13 cropping season at Kafardan (Lebanon) and Marchouch (Morocco).

- Screen for biotic stresses (diseases and insects pests)

Screening and evaluation of food legumes (faba bean, chickpea, and lentil) and durum and bread wheat were done on a large collection of improved lines and national and international collections against different biotic stresses during the 2010/11 and 2011/12 cropping seasons. Several new sources of resistance were identified and confirmed, and most were integrated into the breeding program.

Food legumes:

- Screening chickpea for Ascochyta blight resistance at Tel Hadya (Syria): In 2011, chickpea advanced lines originating from F8 and F9 bulks (162 and 1470 lines, respectively), international nurseries (490 lines), international collections (Canada and Australia: 882 and 120 lines, respectively), and known sources of resistance (160 lines), and also for reconfirmation (647 lines), were tested for Ascochyta blight resistance. In 2012, chickpea advanced lines originating from F9 and F10 bulks (742 and 1436 lines, respectively), international nurseries (472 lines), international collections (Australia and Ethiopia: 172 and 143 lines, respectively), RILs (124 lines), and known sources of resistance (420 lines), and also for reconfirmation (295 lines), were tested for Ascochyta blight resistance. Twelve chickpea lines were used for demonstration trials in 2010/11 and 2011/12.

- Screening chickpea for Fusarium wilt resistance at Tel Hadya (Syria): In 2011, chickpea advanced lines originating from F7 and F9 bulks (440 and 1470 lines, respectively), international nurseries (499 lines), international collections (Canada and Australia: 882 and 120 lines, respectively), and from known sources of resistance (674 lines), and also for reconfirmation (258 lines), were tested for Fusarium wilt resistance. In 2012, chickpea advanced lines originating from F9 and F10 bulks (469 and 1436 lines, respectively), international nurseries (471 lines), international collections (Australia, USA, and Ethiopia: 172, 212, and 143 lines, respectively), RILs (393 lines), and known sources of resistance (215 lines), and also for reconfirmation (717 lines), were tested for Fusarium wilt resistance. Twenty four chickpea lines were used for demonstration trials in 2010/11 and 2011/12.

- Screening lentil for Fusarium wilt resistance at Tel Hadya (Syria): During the 2011/12 cropping season, 300 lentil accessions were screened for Fusarium wilt resistance in wilt sick plots.

- Screening of Ethiopian lentil germplasm accessions for rust resistance: One hundred lentil accessions were screened under natural rust (Uromyces fabae) epidemics. The genotypes were rated using a 1–9 rating scales (1 = resistant and 9 = highly susceptible). Only four accessions were rated as resistant (i.e. 1–3 rating) and most accessions were susceptible to rust. The selected accessions will be used as parents in the crossing program.

- Screening faba bean germplasm for resistance to chocolate spot (Botrytis fabae): A collection of 384 Moroccan land races of faba bean was screened for resistance to Botrytis fabae (chocolate spot disease) under ﬁeld conditions in Sidi El Aidi Experimental Station in Morocco, during the 2011/12 cropping season. Eight showed moderate resistance (tolerant) to chocolate spot and 358 lines were susceptible. Further screening is necessary to confirm the tolerance during the coming season. The results indicated that the identified resistant landraces have great potential for faba bean improvement in Morocco and can be used as donors in conventional and molecular breeding programs.

- Screening for foliar disease resistance in faba bean: During 2012, 1200 lines were assessed for resistance to foliar diseases in Lebanon and Tel Hadya (Syria).

- Screening for resistance to Orobanche crenata in faba bean: In Egypt, 250 and 300 lines were evaluated for Orobanche resistance in the 2010/11 and 2011/12 cropping seasons, respectively.

- Screening lentil for Orobanche resistance at Tel Hadya (Syria): During the 2011/12 cropping season, 94 cultivated and 102 wild accessions of lentil were screened for Orobanche resistance in infested plots.

- Screening chickpea and lentil genotypes for virus resistance: During the 2010/2011 growing season, 100 chickpea and 100 lentil genotypes from ICARDA’s Gene Bank were evaluated for their reaction to local Syrian isolates of BWYV, Chickpea chlorotic stunt virus (CpCSV), and AMV under field conditions. Several genotypes were found tolerant/resistant as follows: in lentil for CpCSV (ILL 1769 and ILL 8283), BWYV (ILL 6546, ILL 7099, and ILL 7600), and AMV (ILL 268, ILL 5424, and ILL 5578); and in chickpea for CpCSV (ILC 6971, and ILC 9869), BWYV (ILC 7758), and AMV (ILC 236, ILC 346, and ILC 1446). In 2012/13, 100 lentil and 100 chickpea genotypes from ICARDA’s Gene Bank, in addition to 15 lentil and 16 chickpea lines from Tunisian breeders, were evaluated for their reaction to BWYV, CpCSV, AMV, and cucumber mosaic virus (CMV) at Mornag INRAT Research Station in Tunisia.

- Screening faba bean lines for FBNYV resistance: During the 2012/13 cropping season, 43 faba bean lines from ICARDA’s materials and 30 lines from the INRAT breeder were evaluated for their reaction to FBNYV in Mornag, Tunisia.

- Screening chickpea for leaf miner resistance: In 2011, of a total of 415 F4 rows, selected from single plants in 2010, 188 single chickpea plants with good resistance to leaf miner were selected. From 643 F2 lines (15 crosses), 324 single plants were selected with resistance to leaf miner. In 2012, from a number of crosses for leaf miner resistance evaluated at Tel Hadya (Syria), 124 F3, 177 F5, and 120 single plants were selected with good resistance to leaf miner and good agronomic characteristics.

Wheat

- Screening of wheat for resistance to BYDV-PAV virus: Four barley, 48 oat, 36 bread wheat, and 19 durum wheat lines from INRAT breeders, 150 barley lines from ICARDA’s breeder, and 330 wheat lines (WKL-13) from ICARDA’s cereal pathologist were evaluated for their reaction to BYDV-PAV in Mornag, Tunisia, during the 2012/13 cropping season.

- Resistance to stripe rust in synthetic hexaploid wheat: A total of 653 of Synthetic Hexaploid Wheat (SHW) lines derived from Aegilops tauschii and Triticum turgidum subsp. durum were evaluated for resistance to Pst at the adult plant stage, at Meraro and Kulumsa Research Stations in Ethiopia and Tel Hadya in Syria. Of these, 644 entries were further tested against a Pst race virulent for Yr2, Yr6, Yr7, Yr8, Yr9, YrA, Yr25, and Yr27 at the seedling stage at Tel Hadya. A total of 116 exhibited a resistant to moderately resistant reaction under field conditions in both locations. Of these, 40 and 76 SHWs showed susceptible and resistant reactions at the seedling stage, respectively. The resistant SHWs identified could be useful in broadening the genetic bases of stripe rust resistance and should be further characterized to uncover potentially new resistance gene(s) in SHWs effective against prevalent races currently attacking wheat in both countries.

- Resistance evaluation against Pst Yr27 virulent: In assessment of seedling and adult-plant resistance to Yr27 race of 522 advanced spring wheat germplasm lines, 232 genotypes were scored for seedling infection types in the range of 0–2, and 290 had high infection scores of 3–4 based on a 0–4 scale. Adult-plant evaluation of the same genotypes, following artificial inoculation at Tel Hadya in 2012, showed a high proportion of resistant and moderately resistant lines. The same genotypes evaluated against Pst, were screened for seedling and adult-plant resistance against a mixture of leaf rust races. In total 150 genotypes were seedling resistant, whereas 372 genotypes showed seedling susceptibility to the mixed races of leaf rust. At adult-plant stage, genotypes were scored for disease severity (0–100%) and major adult-plant responses at flag leaf stage. Among the 372 susceptible seedlings, 227 genotypes showed field responses of Resistance to Moderate Resistance at the adult plant stage, and disease severity in the range of 10–60%. This group is considered as sources of adult-plant resistance.

- Resistance evaluation against Pgt TKTTC: The genotypes tested against Pst and Pt were also evaluated for adult-plant resistance against TKTTC race of stem rust. Adult-plant assessments were conducted under plastic house conditions at Tel Hadya (Syria). Artificial inoculation was carried out at three stages of tillering, booting, and flag leaf using race TKTTC (according to the North American race analysis system). Adult-plant assessments indicated that 192 genotypes showed a resistant reaction and with disease severity in the range of 1–20%. This group is mainly considered as sources of effective seedling resistance gene(s) –most likely Sr31.

- Seedling and adult-plant assessment of resistance to leaf rust and stem rust in durum wheat advanced lines: At Tel Hadya (Syria), 162 durum advanced lines were screened at seedling and adult-plant stages against the same mixture of leaf rust races used in bread wheat screening, and at adult-plant stage against the Pgt TKTTC. At seedling stage, 114 genotypes were resistant, with seedling infection types of 0–2 to the leaf rust race mixture, and 48 genotypes recorded high infections of 3–4. The majority of tested genotypes were resistant to the same race mixture at adult-plant stage. Adult-plant tests of durum genotypes to Pgt race TKTTC indicated that of 162 genotypes, 144 were resistant to TLTTC with disease severity in the range of 1–20%, and 18 genotypes within 20–50%. This indicates a high level of resistance in durum genotypes to the Pgt race used in this study.

- Screening bread and durum wheat lines against barley yellow dwarf virus: A total of 301 durum and 284 bread wheat lines from the previous season were evaluated for resistance to barley yellow dwarf virus during the 2011/12 growing season at Tel Hadya. There were 207 durum and 152 bread wheat lines resistant to BYDV infection on the basis of disease score, plant height, and grain weight. These lines will be further evaluated in future growing seasons.

- Screening for resistance to Russian wheat aphid (RWA): Screening in 2011 of USDA bread wheat germplasm, in the field and greenhouse at Tel Hadya, identified seven lines to resistant the Syrian RWA biotype. Of 339 winter bread wheat nursery (FWW-F6-2011) lines screened in 2011, 49 lines were selected with high levels of resistance to RWA, yellow rust resistance, and good agronomic characters. In 2012, seven spring wheat and nine bread wheat lines carrying wheat/rye translocations were confirmed resistant to RWA (Syrian biotype) in the greenhouse. Since the resistance came from rye, these sources of resistance may carry novel resistance genes to this pest. Eleven bread wheat lines from Australia and 58 from South Africa were also found resistant to the Syrian RWA. One accession of Aegilops taushii from the ICARDA Gene Bank was found resistant to RWA.

- Sunn pest: Of 196 synthetic bread wheat lines identified as promising accessions in 2010, 23 had confirmed resistance to Sunn pest at the vegetative stage. Nine durum wheat lines were also confirmed resistant to Sunn pest at the vegetative stage. Of 340 F4 durum wheat lines, 69 were selected resistant to Sunn pest at the vegetative stage. Sunn pest testing was carried out with artificial infestation in cages at Tel Hadya. From a sub-set of 524 bread wheat and 441 durum wheat accessions, 52 and 67 accessions, respectively, were found resistant at the vegetative stage to the overwintered Sunn pest feeding. The test was carried at Tel Hadya in 2012 with artificial infestation. These identified accessions need to be rescreened in one more season for confirmation.

- Hessian fly: In 2012, five accessions of Aegilops taushii were found resistant to the Syrian Hessian fly biotype. Eleven spring and nine winter bread wheat lines carrying wheat rye translocations were found resistant to Hessian fly in Syria. The screening test was carried out in the insect rearing room at Tel Hadya. Since the resistance came from rye, it is very likely that these sources of resistance may be carrying new resistance genes to Hessian fly.

- Evaluate grain quality of breeding lines

The grain quality tests for durum wheat are done in Syria, Lebanon, and Egypt. Ongoing work succeeded in identifying lentil genotypes with higher contents of iron and zinc.

- Information databases on dry area farming systems and GIS–remote sensing based spatial analysis of diseases, pests, crop distribution, and yield

Surveys of wheat and food legume diseases were done in Morocco during the 2011/12 cropping season, and disease and insect suitability maps were developed by the GIS Unit of ICARDA.

For 2012/13, it was planned to assess diseases of faba bean (mainly chocolate spot and rust) and of wheat (mainly Septoria and rust) in the on-farm CA demonstration field in the Fernana region, Morocco, and in farmers’ fields surrounding this field. Similar work will also be done in Marchouch, Morocco. This work will be done in collaboration with NARS institutions involved in the project.

- Methodology development for using supplemental irrigation for climate change adaptation

A trial will be conducted on supplemental irrigation of chickpea in the spring crop of 2013. Another trial will be implemented on wheat during the 2013/14 cropping season. This activity will be initiated by Dr. N. Vinay from Integrated Water and Land Management Program (IWLMP) at ICARDA.

# 7. Progress towards component objectives

Most progress occurred with the better genetic material sent to NARS for the different crops in regard to grain yield, quality, disease and pest resistances, and tolerances to heat, cold, drought, and salinity. The multiple stress resistant/tolerant varieties developed will allow small-holder farmers to grow wheat and food legumes at lower cost and improve their income by getting better yields. This will help to improve the food security status in the region and in the world and preserve the environment. Great progress was achieved in variety release mainly for wheat (durum and bread). However, the process of release of food legumes is still slow and few varieties were released in the countries involved in the project. This is likely due to the lack of human resources working on food legume breeding in NARS institutions and also to the lack of adaptation of the supplied material to the different growth conditions. Food legume researchers at ICARDA are working to establish close collaboration with some NARS food legume breeding programs in order to select and to develop more preferred and adapted lines and to solve the many constraints facing food legume crops in the CWANA region.

The implementation of on-farm activities (i.e. variety popularization, CA, supplemental irrigation, and IPM) specific to the project in the countries involved and also of the activities associating NARS (e.g. baseline studies and seed sector studies) only commenced in the 2012/13 cropping season due to the long process taken for the signing of the project grant and therefore delays in the disbursement of the budget. However, NARS institutions executing the project, once receiving official notification, very rapidly prepared work plans of activities to be implemented in the 2012/13 cropping season.

Progress in achievements of activities and outcomes is shown in the log-frames of activities and outcomes (Annex D). Most of the activities for which ICARDA was directly responsible were executed on time; however, due to late involvement of NARS in the project it was not possible to make much progress in some activities, especially those specifically related to Objective 1.

# 8. Use of communication tools and innovative approaches

Farmers have access to information concerning wheat and food legumes crops through different channels. In some countries, telecommunication tools (e.g. the internet and SMS) have become commonly used to access information, but this is generally for medium or large farmers. Traditional extension with direct contact between farmers and extension agents still operates in most countries. Some countries have invested more in communications with farmers by developing agricultural TV channels (e.g. Egypt) or newspapers specialized in agriculture that can promote new technologies in wheat/food legume systems.

In Tunisia, the National Field Crops Institute (INGC) is using SMS to communicate with farmers. Their database contains a list of 1500 farmers (around 500 small-holders) and 500 extension agents. This system is used to transfer some messages related to cereal and food legume crops during the cropping season and to inform farmers about field days or any activities that may interest them. The Ministry of Agriculture of Tunisia has a project to install a call center to respond to different questions raised by farmers.

In Egypt, a field day organized by the project on 5 March 2013 benefited from large media coverage (e.g. 6 newspapers and TV). Egyptian researchers working on field crops (cereals and legumes) and extension agents are frequently invited to present recent results of research and recommended packages to farmers. This TV channel also serves to communicate recommendations and alerts to farmers. Extension agents have access to the expert systems developed by the Central Laboratory for Agricultural Expert Systems of ARC (CLAES/ARC) on wheat and faba bean crops.

Nowadays, most NARS institutions have a webpage that can be used to communicate with farmers for access to technologies (e.g. downloading brochures or contacting researchers and technicians). The use of social networks (e.g. Facebook, Twitter, Skype …) will be developed to better communicate with farmers and between the project team to share experiences and inform farmers of activities and to report success stories.

# 9. Participatory development and evaluation of best-bet technology options

Modern methods for technology transfer consider involving farmers in the experimental process in determining the experiments to be implemented in their fields, in the follow-up to the experiment across the season, and in the evaluation. These methods have proved their effectiveness in better technology adoption by farmers. Farm field schools are becoming commonly used for technology transfer in many countries in the project area. Establishment of farm field schools needs to involve the farmers from the beginning of the conception of the experiment to solve their problems. Among the elements of success of the method, the existence of proven technology that can be easily seen by the farmers, e.g. a variety tolerant to Orobanche being tested in an infested field versus a traditional susceptible variety used by farmers. It is recommended that the package to be tested by farmers is not complicated, and new elements be progressively introduced so that farmers can adopt and apply them more easily. One example is from an on-farm demonstration in Al-Ghar (Al-Sharkia Governorate, Egypt) in the field of Amroe’s farmer, where in the 2012/13 cropping season the Field Crop Research Institute FCRI/ARC in collaboration with the regional extension service implemented with the farmer a package testing the Orobanche tolerant cv Giza 843 at low seed density (75 kg/ha). The crop performed well and the expected yield will be over 4.5 t/ha and at least 4–5 times better than the neighboring field sown with susceptible cv Sakha 1, which was highly infested with Orobanche. The farmer conducting the demonstration sowed faba bean after rice and plowed his field many times before planting faba bean. The direct seeding after rice proved to be appropriate in reducing the Orobanche infestation in the field, therefore it is planned to introduce this technique to complete the package in the 2013/14 cropping season with the same farmer.

In 2012/13, the NARS implemented a series of promising lines in farmers’ fields and research stations – farmers are or will be involved in evaluation of the improved lines of wheat and legumes before their release. Therefore farmers can feel more confident in the material proposed for them to grow in the future. The ICARDA breeding program sowed several advanced lines of cereals and food legumes in different locations in 2012/13 for participatory evaluation. Farmers and breeders will identify the best material to be released and promoted.

During 2012/13, several farmers implemented demonstration trials for variety testing and popularization, CA, supplemental irrigation, and IPM of wheat and food legumes. It is expected that the number of demonstrations will increase and the area sown to the varieties tested will increase in at least the neighboring regions. The farmers included in the 2012/13 program benefited from the testing of advanced technologies and other farmers indirectly take advantage through their participation in the field days or FFS organized. At the date of preparing this report, the cropping season has not yet ended in the involved countries, except for Sudan.

Experiences of the involved countries with processing technologies at the household level to add value to wheat and food legume products, thus improving family income, will be documented and shared during 2013. A way will be sought to encourage families to develop small activities around processing technologies mainly using preferred varieties. In the CWANA region, several processed products with higher added values and derived from wheat and food legumes have been developed over time. In some regions of the involved countries, such businesses are well developed at the household level and generate a high income – these could be extended to other poor regions so they can also benefit from their production. In Tunisia, for example, Sfax is well known for the diversity of pastries using wheat and food legumes (mainly chickpea) and other agricultural products developed at the family level. It is planned to transfer the knowledge developed in this region to other regions in Tunisia to develop these small business activities to improve livelihoods. Similar experiences will be encouraged in other countries.

# 10. Links, if any, with other IFAD-supported activities and/or other partners

The project has established links mainly with ‘Enhancing Food Security in Arab Countries’ project in the countries where both projects conduct activities – particularly in Egypt, Jordan, and Tunisia where some on-farm activities are conducted at the same sites. The Regional Coordinator of the ‘Enhancing Food Legume in Arab Countries’ project) participated in the coordination meeting of the EU-IFAD project, held in Amman (Jordan) on 12 and 13 December 2012. In Tunisia, both projects co-organized a field day on IPM on faba bean in Fernana on 19 March 2013 – this was attended by more than 80 farmers as well as extension agents and researchers from the national institutions involved in the project and ICARDA.

The project is part of the CRP programs, particularly CRP3.1 on Wheat and CRP3.5 on Grain Legumes, mainly in regard to breeding and development of the use of improved varieties and seed sector analysis and development. Complementary actions are undertaken to produce better and consolidated results.

# 11. Lessons learned and knowledge shared

It is very important to learn from previous experiences – either positive or negative. In Tunisia, during the last decade, the winter chickpea area has shown an important increase compared to spring chickpea, which was more common before the 2000s. With the selection of the high yielding cv Beja 1, which carries dual resistance to Fusarium wilt and Ascochyta blight, the chickpea cultivated area has rapidly increased mainly using this variety, and the national average yield has substantially improved. The cultivated area of cv Beja 1 extended rapidly even before its registration in 2003 and the start of its commercialization in 2006 by the Tunisian seed company CCSPS (Coopérative Centrale des Semences et Plants Selectionnés). INRAT concluded an agreement in the late 1990s for popularization of cv Beja 1 and two faba bean varieties with farmer associations, providing seeds at a moderate price and ensuring technical backstopping to farmers involved in the program. The best farmers applying the recommended package were rewarded by getting higher yields. These actions ensured that the variety was well known before its official release and commercialization, and also due to the organization of several field days in the best fields with large participation by farmers. More than 80% of the winter chickpea area in Tunisia is sown with cv Beja 1. There was a similar experience with a pilot farmer in the Fernana region (north-west Tunisia) to promote the faba bean cvs Badi and Bachaar and chickpea cv Beja 1. Both actions contributed considerably to the diffusion of these varieties and in improving the national yields of chickpea and small-seeded faba bean.

ICARDA and the national programs have selected several wheat and food legume lines carrying resistance or tolerance to more than one stress and also with high yields. Strategies promoting the new varieties, similar to that used for cv Beja 1, could be followed to enhance the process of release which usually requires about two years. The activities undertaking with farmers should not be limited to only varieties released but must be extended to promising lines; the only constraint is the availability of sufficient seed in some cases, therefore a special program for seed increase of promising lines has been established.

# 12. Dissemination activities and farmer’s involvement

A number of farmers contributed in the implementation of several activities planned for the 2012/13 cropping season.

Several fields’ days were organized and planned during the 2012/13 cropping season to show, compare, and evaluate with farmers the different alternatives proposed. Although the cropping season is not yet completed and most of the field days are planned for spring when we can better appreciate the behavior of the different varieties tested, we present in the following tables 15 and 16 most of the activities undertaken in the eight countries. The number of field days and FFS organized by March 2013 are shown in Table 15. In Sudan, eight field days were organized in different locations involving 198 farmers, and one FFS with 25 farmers was conducted. In Egypt, 32 field days were conducted and involving more than 1500 farmers – each field day had 25–150 participants. In Al-Ghar (Zakazik), 150 farmers attended the field day organized on 5 March 2013. In addition, five FFS were organized and involved around 100 farmers. In Morocco, three field days and six FFS were organized by March 2013 and involved about 300 farmers. In Algeria, four field days were performed with the majority of the 89 participants being farmers. Several field days are planned for April and May. In Tunisia, one field day was organized in collaboration with the ‘Enhanced food security in Arab countries’ project in Fernana, and the 81 participants were mostly farmers. In Turkey, numbers of field days were organized on different topics.

Table 15. Number of field days and farm field schools conducted during the 2012/13 cropping season (by 31 March 2013)

| Countries | Algeria | Egypt | Jordan | Lebanon | Morocco | Sudan | Tunisia* | Turkey |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of field days | 4 | 32 |  |  | 3 | 8 | 1 |  |
| Participation in field days | 89 | >1500 |  |  | 60 | 198 | 81 |  |
| Number of FFS |  | 5 |  |  | 6 | 1 |  |  |
| Participation in FFS |  | > 100 |  |  | 240 | 25 |  |  |
| Other training activities targeting farmers or other stakeholders |  |  |  |  |  |  |  |  |

*: co-organized with ‘Enhanced food security in Arab countries’ project with INGC

# 13. Gender mainstreaming

The involvement of females in the consortium was estimated to be 1/3 (Table 16). The greatest involvement of females was in Tunisia (about 50%) and the lowest in Turkey and Jordan.

Table 16. Participant involvement by gender in the transfer of technology activities

| Countries | Female | Male | Total |
| --- | --- | --- | --- |
| Algeria | 12 | 25 | 37 |
| Egypt | 10 | 69 | 79 |
| Jordan | 3 | 8 | 11 |
| Lebanon | 1 | 3 | 4 |
| Morocco | 7 | 19 | 26 |
| Sudan | 13 | 23 | 36 |
| Tunisia | 15 | 14 | 29 |
| Turkey | 2 | 8 | 10 |
| Total | 63 | 169 | 232 |

# 14. Publications

Several publications were done by the research team, mostly in international impacted journals. The references are listed in annex E.

# 15. Backstopping to the countries

The regional coordinator and some ICARDA researchers visited different on-farm demonstrations and research station in Egypt, Sudan, Lebanon and Tunisia in 2012 and 2013 to supervise the implementation of project activities and to discuss with the project team the dissemination and other activities conducted or to be undertaken in the next period. The other countries will be visited in April, May, and June of 2013.

# 16. Meetings

A coordination meeting was held in Amman on 12–13 December 2012 with the participation of national coordinators and several researchers from the different programs and units of ICARDA to discuss the implementation of activities for 2012/13 and finalize the work plan.

The Steering Committee meeting of the project was organized in Egypt on 4 March 2013 in collaboration with ARC. It was followed by a visit to Zakazik district to attend a field day in Al-Ghar on faba bean. His Excellency Mr. Hassan Najjar, Governor of Al-Sharkia attended the field day as well the members of the Steering Committee of the project, many farmers and engineers from the extension services, and many researchers from ARC and universities.

# 17. Shortcomings and problems encountered in grant implementation and actions suggested

The delay of grant contract signature and thereafter in the disbursement of the budget delayed the work to be done with NARS, which mostly started in November 2012. An extension with no-cost of the project is recommended to continue the activities initiated in the 2012/13 cropping season and to ensure the transfer of technologies and their adoption. This extension is preferably to cover three cropping seasons of work with farmers.

# 18. Other events and relevant issues during the reporting period

The most important event is the relocation of ICARDA staff to different countries after the tragic events in Syria and the obligation of staff to leave the Tel Hadya headquarters in July 2012.

#### Annexes

Annex A

COUNTRIES WORK PLANS

CROPPING SEASON 2012/13

Annex A

COUNTRIES WORK PLANS

CROPPING SEASON 2012/13

ALGERIA

WORK PLAN 2012/13

| Activity | Number of implemented on-farm demonstration fields |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration of recently released varieties | 3 | 2 |  | 4 | 3 | Didouche Mourad (DW: 1) Guellal (DW: 3, BW: 1, L: 1) Mellakou (BW: 1) Ferdjioua (BW: 1) Ain Smara (L: 1) Mouzaia (CP: 1) Saf-Saf (CP: 1) Ammari (CP: 1; L: 1) SidiKhelifa (CP : 1) | Didouche Mourad (DW: 0.0125 ha) Guellal (DW: 0.09 ha ; BW: 0.03 ; L: 0.05) Mellakou (BW: 0.5) Ferdjioua (BW: 0.036 ha) Ain Smara (L: 1) Mouzaia (CP: 1) Saf-Saf (CP: 1) Ammari (CP: 1; L: 1) SidiKhelifa (CP : 1) Total (ha) DW : 0.1025 BW : 0.566 CP : 4 L : 2.05 | DW: (Didouche Mourad : 26/12/2012; Guellal: 26/11/2012) BW: (Guellal: 26/11/2012; Ferdjioua : 20/12/2012; Mellakou: 17/12/2012) CP: (SidiKhelifa: 08/01/2013; Mouzaia: march; Saf-Saf: 11/02/2013; Ammari: 21/12/2012) L: (Ammari : 20/12/2012; Ain Smara: 04/01/2013; Guellal: 18/12/2012) | Visits for backstopping: (Didouche Mourad: 2 ; Guellal : 2; Mellakou : 1 ; Mouzaia: 3 ; Ain Defla : 1 ; Bouira: 1 ; Tissemsilt: 1) Field days : (Didouche Mourad: 1; Ferjioua: 1; Ain Smara: 1; Sidi Khelifa; Saf-Saf : 1 ; Mouzaia: 1) |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

| Activity | Number of implemented on-farm verification trials |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm verification trials of promising lines | 1 | 3 |  |  |  | Didouche Mourad : (DW: 2; BW: 4) Benifouda: (DW: 1) Ain Abessa (DW: 1) | Didouche Mourad: (DW: 0.018; BW: 0.036) Benifouda: (DW: 0.025) Ain Abessa (DW: 0.025) Total (ha) : DW : 0.068 BW : 0.036 | DW : (Didouche Mourad: 26/12/2012; Benifouda : 12/11/2012; Ain Abessa: 18/11/2012) BW: (Didouche Mourad : 26/12/2012) |  |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

| Activity | Number of implemented on-station seed increase of recently released varieties |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of recently released varieties | 3 | 6 |  | 4 | 4 | El Khroub (DW: 3; BW: 1; CP: 1, L: 2) Sétif (DW: 5; BW: 2, CP: 2; L: 1) Oued Smar (DW : 1 ; CP : 1) Tiaret (DW: 1; BW: 1; L: 1) Guelma (DW: 1; CP: 2; L: 2) Sidi Bel Abbes: (DW: 1) | El Khroub (DW: 5750 HR+15.6 ha; BW: 1500 HR+1.7 ha; CP: 1 ha, L: 2 ha) Sétif (DW: 9000 HR, BW: 3000 HR+11.7ha, CP: 1000 plants+2.65 ha; L: 1000 plants+1.69 ha) Oued Smar (DW : 2000 HR+0.5 ha ; CP : 1500 plants) Tiaret (DW: 1.5 ha; BW: 0.5 ha; L: 1 ha) Guelma (DW: 800 HR+0.6 ha; CP: 6000 plants+2.2 ha; L: 6000 plants+2.1 ha) Sidi Bel Abbes (DW: 2500 HR+1 ha) Total (ha): DW: 20,050 HR+18.7 ha BW: 4500 HR+13.9 ha CP: 6000 plants+5.85 ha L: 7000 plants+6.79 ha | DW: - El Khroub: - Bousselam: G0: 11/12/2012 G1,G2: 16/12/2012 - Cirta: G0: 26/12/2012 G1,G2: 02/12/2012 - Wahbi: G0: 12/12/2012 G1: 08/12/2012 -Sétif: - Setifis, Zairi, Mansoura: 13/11/2012 - Bousselam: 22/11/2012 - Megress : 21/11/2012 -Oued Smar: 16-17/12/2012 - Tiaret: 24/11/2012 - Guelma: 02/12/2012 - Sidi Bel Abbes: G0: 22/11/2012; G1: 13/12/2012 BW: - El Khroub: G0: 13/12/2012 G1,G2: 03/12/2012 - Sétif: - Wifak : 21/11/2012 - R’Mada : 03/12/2012 - Tiaret: 25/11/2012 CP: - El Khroub: 13/01/2013 -Sétif: - Flip84-92c: 23/12/2012 -Oued Smar: 09/01/2013 - Guelma: 13/12/2012 - Sidi Bel Abbes: 07/02/2013 L: - El Khroub: 13/01/2013 -Sétif: 13/12/2012 -Tiaret: 23/12/2012 - Guelma: 13/12/2012 |  |

HR : head row

| Activity | Number of implemented on-station seed increase of promising lines |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of promising lines | 1 | 3 |  |  |  | El Khroub (DW: 3; BW: 4) Setif (DW: 1) Guelma (DW: 1) | El Khroub (DW: 0.027 ha; BW: 0.036) Setif (DW: 1000 HR) Guelma (DW: 0.123 ha) Total : DW: 1000 HR+0.15 ha BW: 0.036 ha | DW : (El Khroub : 30/12/2012; Setif :13/12/2012; Guelma:18/12/2012) BW: (El Khroub : 30/12/2012) |  |

| Activity | Number of implemented On-station ICARDA Trials |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station ICARDA and NARS Trials evaluation | 9 | 9 |  | 0 | 0 | Beni Slimane (DW: 10; BW: 5; L: 4; CP: 11) El Khroub (DW: 50; BW: 40) Sétif (DW: 6; BW: 11) Oued Smar (DW: 100; BW: 100) Sebaine (DW: 24) Ain El Hadjer (DW: 10; BW: 12) Guelma (DW: 29; BW: 27) Sidi Bel Abbes (BW: 10) | Beni Slimane (DW: 0.024; BW: 0.012; L: 0.0096; CP: 0.0264) El Khroub (DW: 0.12; BW: 0.096) Sétif (DW: 0.009; BW: 0.005) Oued Smar (DW: 0.012; BW: 0.012) Sebaine (DW: 0.011) Ain El Hadjer (DW: 0.0048; BW: 0.0057) Guelma (DW: 0.015; BW: 0.014) Sidi Bel Abbes (BW: 0.,0048) Total (ha) DW: 0.662 BW: 0.1447 CP: 0.0264 L: 0.0096 | DW: (Beni Slimane: dd/mm/yy; El Khroub : 17/12/2012; Setif : 26-27/12/2012; OuedSmar: 18-19/12/2012; Sebaine: 17/12/2012; Ain El Hadjer: 19/12/2012; Guelma: 10/01/2013) BW: (Beni Slimane: dd/mm/yy; El Khroub : 17/12/2012; Setif : 04/12/2012; Oued Smar: 18-19/12/2012; Ain El Hadjer: 19/12/2012; Guelma:10/01/2013; Sidi Bel Abbes: 23/12/2012) |  |

| Activity | Number of implemented on-farm demonstration on supplemental irrigation |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration on supplemental irrigation | 1 | 4 |  |  |  | Beriche (BW: 1) Mouzaia (DW: 1) Mellakou (DW: 1) El Amra (DW: 1) Sidi Bel Abbes (DW: 1) | Beriche (BW: 1) Mouzaia (DW: 1) Mellakou (DW: 0.5) El Amra (DW: 1) Sidi Bel Abbes (DW: 4) Total: 7.5 ha | DW: (Mouzaia: 10/12/2012;Mellakou: 17/12/2012; El Amra: 29/12/2012; Sidi Bel Abbes: December) BW: (Beriche: 10/12/2012) | Field days: (Beriche: 1; El Amra: 2; Sidi Bel Abbes: 3; Mouzaia: 2; Chlef: 2) Information and awareness technical days: (Guelma: 4; Tebessa: 1; Médea: 1, Ain Témouchent: 1; Sidi Bel Abbes: 2) |

| Activity | Number of implemented on-farm demonstration on Conservation Agriculture |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration on Conservation Agriculture | 1 | 3 |  |  | 2 | Mila (DW: 1) Sebaine (DW : 1 ; BW : 2 ; L : 1) Ain Arnat (DW: 1 ; L : 1) | Mila (DW: 1) Sebaine (DW : 0.5 ha ; BW : 9 ; L : 1.25 ha) Ain Arnat (DW: 1.16 ha ; L : 0.36 Total (ha) DW : 2.21 ha BW : 9 ha L : 1.61 ha | DW: (Milla: 26/11/2012; Sebaine: 31/12/2012; Ain Arnat: 22/11/2012 ) BW: (Sebaine: - Ain Abid: 31/12/2012 - HD 1220: 12/01/2013 L : (Sebaine: 31/12/2012; Ain Arnat: 22/11/2012) | Demonstrationday: (Mila: 1) |

EGYPT

WORK PLAN 2012/13

| Activity | Number of implemented on-farm demonstration fields | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- |
|  | FB |  |  |  |  |
| On-farm demonstration of recently released varieties (free Orobanche soils) | 15 | Nubaria region: (10 FB fields, 2 Var.: Nubaria 2, Nubaria 3) Kafr Al Sheikh region: (5 FB fields: 1 Var: Sakha 4) | 6 | Nubaria: Field 1: 11/11/2012; Field 2: 19/11/2012; Field 3: 19/11/2012; Field 4: 15/11/2012; Field 5: 08/11/2012; Field 6: 13/11/2012 Field 7: 21/11/2012; Field 8:21/11/2012; Field 9: 24/10/2012; Field 10: 21/11/2012 (discarded). Kafr Al Sheikh: Field 1: 17/11/2012; Field 2: 17/11/2012; Field 3: 15/11/2012; Field 4:14/11/2012; Field 5: 20/11/2012 | * A total of 15 demonstration fields were conducted as follows: -10 at Nubaria (New reclaimed lands); where 4 solid fields (one discarded), and 6 intercropped with young trees. -5 at Kafr Al-Sheikh. * Intercropping was performed at Nubaria because this is the only way to increase faba bean cultivated area in such region. * All the agronomic practices were applied as recommended. * Hand weeding was performed. *Infection level with foliar diseases was mild due to shortage of rain fall and relative humidity. * Flowering and pod setting were recorded. * The cultivated varieties performed well. * A total of 8 field days were held during January: three at Kafr El-Seikh and five at Nubaria to follow up the application of crop production package and to solve the problems with extension agent and farmers. |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

+: indicate dissemination activities projected and achieved (FFS, Field days); FB: Faba Bean

| Activity | Number of implemented on-farm IPM demonstration | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- |
|  | FB |  |  |  |  |
| On-farm IPM demonstration of recently released varieties in Orobanche infested soil | 20 | Dakahlia, 5 fields (FB: 1; var. Giza 843) Sharkia, 10 fields (FB: 2; var.Giza 843 and Misr 3) Assiut, 5 fields (FB: 1;var.Giza 843) | 8.4 | Dakahlia: Field 1:29/11/2012 Field 2 :29/11/2012 Field 3:22/11/2012 Field 4:22/11/2012 Field 5: 12/11/2012 Sharkia: Field 1: 12/11/2012 Field 2: 19/11/2012 Field 3: 13/11/2012 Field 4: 17/11/2012 Field 5: 14/11/2012 Field 6: 09/11/2012 Field 7: 05/11/2012 Field 8: 14/11/2012 Field 9: 12/11/2012 Field10: 16/11/2012 Assiut: Field 1:05/11/2012 Field 2:08/11/2012 Field 3:05/11/2012 Field 4:03/11/2012 Field 5:01/11/2012 | * A total of 20 demonstration fields were conducted at Dakahlia, Sharkia and Assiut Governorates. *The recommendation package of faba bean production was followed. * Flowering and pod setting were recorded. *Orobanche expected to be appeared early march. * A total of 11 field days were held during January: three at Dakahlia, three at Assuit and five at Sharkia, to follow up the application of crop production package and to solve the problems with extension agent and farmers. |

*: Indicate within parenthesis number of varieties; FB: Faba Bean;

| Activity | Number of implemented on-farm verification trials | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- |
|  | FB |  |  |  |  |
| On-farm verification trials of promising lines | 9 | North Egypt (FB: 3 var.: Sakha, Behira, Nubaria). Middle Egypt (FB: 3 var.: Minia, Mallawy, Sids.) Upper Egypt (FB: 3 var.: Mataana, Assiut, New Valley). | 0.2 0.2 0.2 | FB: North Egypt: Sakha: 22/11/2012 Behira: 12/11/2012 Nubaria: 22/11/2012 Middle Egypt: Minia: 27/11/2012 Mallawy: 26/11/2012 Sids: 22/10/2012 Upper Egypt: Mataana: 1/11/2012 Assiut: 19/10/2012 New Valley: 24/10/2012 | *Flowering and pod setting were recorded. *All the evaluated lines promising and performing well. |

* Indicate within parenthesis number of varieties; FB: Faba Bean;  +: indicate dissemination activities projected and achieved (FFS, Field days, );

| Activity | Number of implemented on-station seed increase of recently released varieties | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- |
|  | FB |  |  |  |  |
| On-station seed increase and maintenance of recently released varieties (Foundation seed) | 2 | Nubaria: (3 Var.: Nubaria 2, Nubaria 3; Misr 3) Sakha: (2 Var.: Sakha 4, Giza 843) | 4.2 8.4 | Nubaria: 22/10/2012 24/10/2012 24/10/2012 Sakha: 12/11/2012 09/11/2012 | *Flowering and pod setting were recorded. Varieties at Sakha and Nubaria perform well. |

| Activity | Number of implemented on-station seed increase of promising lines | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- |
|  | FB |  |  |  |  |
| On-station breeder seed increase | 2 | Nubaria: (3 Var.: Nubaria 2, Nubaria 3, Misr 3) Sakha: (2 Var.: Sakha 4, Giza 843) | 0.32 0.84 | Nubaria: 22/10/2012 24/10/2012 24/10/2012 Sakha: 12/11/2012 09/11/2012 | Flowering and pod setting were recorded. Varieties at Sakha and Nubaria perform well. |

*: Indicate within parenthesis number of varieties; FB: Faba Bean

| Activity | Number of implemented On-station ICARDA Trials | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- |
|  | FB |  |  |  |  |
| On-station ICARDA and NARS Trials evaluation | 1 | Gemmiza Research Station | 0.0051 | First sowing date: 15/11/2012 Second sowing date: 1/12/2012 | Y=1 X=3 (2 tolerant; Giza 843 and Misr 3, and 1 susceptible as check; Giza 3). *This experiment conducted at Gemmiza Res. Sta., using Lysometers. -Sowing dates=2 -Soil samples=7 (6 infested + 1 free as control, were collected from 7 different locations, i.e.Shandaweel, Mallawy, Sids, Giza, Nubaria, Sakha and Gemmiza). *Diffrences in the degree of infestation were observed due to the source of infested soil. * Giza 843 and Misr 3 showed tolerance compered with the susceptible variety Giza 3. |

*: Indicate within parenthesis number of varieties; FB: Faba Bean; y: number of trials; x: number of lines

| Activity | Number of lines screened for biotic tolerance | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- |
|  | FB |  |  |  |  |
| Screening for yield and its components | * 260 * (2 PYT; 20 Lines each) | Sids Research Station | 0.05 0.09 | 14/11/2012 14/11/2012 | * All the agronomic practices were applied as recommended. * Hand weeding was applied twice * Flowering and pod setting were recorded. |

*: Indicate within parenthesis number of varieties; FB: Faba Bean;

| Activity | Number of implemented demonstration on conservation agriculture | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- |
|  | FB |  |  |  |  |
| On-farm demonstration on Conservation Agriculture | 2 | Al Sharkia(1 FB: Misr 3) Al Dakahlia (1 FB: Giza 843) | 0.81 ha 0.41 ha | 12/11/2012 29/12/2012 |  |

*: Indicate within parenthesis number of varieties; FB: Faba Bean;

JORDAN

WORK PLAN 2012/13

| Activity | Number of implemented on-farm demonstration fields |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration of recently released varieties | 1 | 3 |  |  |  | Irbid: Field 1 (DW: 2) Irbid: Field 2 (DW: 2) Ma’daba: (BW: 1; DW: 3) | 4.4 | BW: (Madaba: 22/1/2013) DW: (Irbid Field 1: 22/1/2013- Irbid: Field 2: 2/12/2012; Madaba: 22/1/2013) | Field days |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

| Activity | Number of implemented on-farm or on station participatory evaluation trials |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm or on-station participatory evaluation trials (ICARDA and NARS Trials) |  | 6 |  | 3 |  | Maru (24) Mushager (24) Rabba (24) | 0.4 |  |  |

| Activity | Number of implemented on-station seed increase of recently released varieties |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of recently released varieties | 1 | 3 |  | 1 |  | Mushagher: (BW: 1; DW: 3; CP:1) | 9 | BW: (Mushagher: 28/11/2012) DW: (Mushagher: 29/12/2012) CP: (Mushagher: 20/12/2012) |  |

| Activity | Number of implemented on-farm demonstration on Conservation Agriculture |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration on Conservation Agriculture and Wheat/Fallow Rotation trial |  | 1 |  |  |  | Ma’daba: (DW: 2) | 1.2 | Ma’daba: 12/1/2013 |  |

| Activity | Number of conducted experiments |  |  |  |  | Locations * | Total size (ha) | Duration | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration on Conservation Agriculture and Wheat/Chickpea Rotation trial |  | 2 |  | 6 |  | Raba Field 1: (CP: 1; DW: 1) Raba Field 2: (CP: 1; DW: 0) Raba Field 3: (CP: 1; DW: 0) Mushager: (CP: 1; DW: 1) Maru Field 1: (CP: 1; DW 0) Maru Field 2: (CP: 1; DW: 0 | 11 | DW: (Raba Field 1: 27/1/2013; Raba Field 2: dd/mm/yy; Raba Field 3: dd/mm/yy; Mushager Field 1: 15/1/2013) CP: (Raba Field 1: 27/1/2013; Raba Field 2: ~26/2/2013; Raba Field 3: ~26/2/2013) Mushager: 15/1/2013; Maru Field 1: 16/1/2013; Maru Field 2: 21/2/2013; |  |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

LEBANON

WORK PLAN 2012/13

| Activity | Number of implemented on-farm demonstration fields |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration of recently released varieties |  | 6 |  | 7 |  | Al Qaa Field 1: (DW: 1; CP:1) Al Qaa Field 2: (DW: 1; CP:1) Deir Al Ahmar: (DW: 1; CP:1) Majdaloun: (DW: 1; CP:1) Zahle Field 1: (DW: 1; CP:1) Zahle Field 2: (DW: 1; CP:1) Taanayel: (CP:1) | DW= 11000 m² CP= 9000 m² | DW: (Al Qaa Field 1: 03/12/12; Al Qaa Field 2: 03/12/12; Deir Al Ahmar: 30/11/12; Majdaloun: 30/11/12; Zahle Field 1: 01/12/12; Zahle Field 2: 01/12/12) CP: (Al Qaa Field 1: 03/12/12; Al Qaa Field 2: 03/12/12; Deir Al Ahmar: 30/11/12; Majdaloun: 30/11/12; Zahle Field 1: 01/12/12; Zahle Field 2: 01/12/12; Taanayel: 03/12/12) | Plants DW & CP stand well And it is tillering stage 3 field days: Between 10 of May to 10 of June (feeling stage). 1°- AL Qaa Region 2°- Majdaloun 3°- Zahle (Conservation Agriculture) (Exact date of each will be sent later). |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

| Activity | Number of implemented on-station seed increase of recently released varieties |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of recently released varieties |  |  |  | 1 |  | Kferdan Station: (CP: 2 varieties) |  | CP: (Kferdan Station: 15/12/2012) | Vegetative growth |

| Activity | Number of implemented on-station seed increase of promising lines |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of promising lines |  |  |  | 1 |  | Kferdan Station: (CP: 2 lines) |  | CP: (Kferdan Station: 15/12/2012) | Vegetative growth |

| Activity | Number of implemented on-farm demonstration on Conservation Agriculture |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration on Conservation Agriculture |  | 1 |  |  |  | Zahlé Field 1: (DW: 1) | DW= 2000 m² | DW: (Zahlé Field 1: 01/12/12) | Tillering stage |

MOROCCO

WORK PLAN 2012/13

| Activity | Number of implemented on-station seed increase of recently released varieties |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of recently released varieties | 1 | 1 | 1 | 1 | 1 | Marchouch: (FB: 4 Varieties, L: 6, CP: 4, DW:8, BW: 1) | FB: 0.6 L: 0.5 CP: 0.5 BW: 0.02 DW: 0.16 | FB: 10/12/12, 28/12/12 L: 10/12/12, 28/12/12 CP: 10/12/12, 27/12/12 BW: 17/12/12 DW: 17/12/12 |  |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

| Activity | Number of implemented on-station seed increase of promising lines |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of promising lines | 2 |  | 1 |  |  | Jmaat Shim (BW: 96 lines) Sidi Aidi (BW: 96 lines) Marchouch: (FB: : 6 lines) | 0.25 ha 0.25 ha 0.25 ha | BW: Jmaat Shim: 15/12/12 Sidi Aidi: 26/11/12 FB: Marchouch: 24/12/12 | Hessian fly resistant BW lines 3 lines of Faba bean minor and 3 Faba bean major |

| Activity | Number of implemented on-farm IPM demonstration |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm IPM demonstration | 3 | 1 | 1 | 2 | 1 | Had Ait-Mimoun (BW: 2; FB: 1; CP: 1) Marchouch (BW: 1; DW: 1; CP: 1; L: 1) | 2 2 | BW: (Had Ait Mimoun: 13/12/12 ; Marchouch: 10/12/12) DW: (Marchouch: 10/12/12) FB: : (Had Ait Mimoun: 17/12/12) CP: (Had Ait Mimoun: 18/12/12; Merchouch: 21/02/13) L: (Marchouch: 11/12/12) | - Winter chickpea in Had Ait Mimoun and spring chickpea in Merchouch - FFS on: Cereals: *weed treatments at Had Ait Mimoun (31/01/13) *weed treatments at Merchouch (7/2/13) Food legume *Weed treatments at Merchouch (19/02/13) |

| Activity | Number of implemented on-farm demonstration on Conservation Agriculture |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration on Conservation Agriculture | 2 |  |  |  | 2 | Brachoua : (BW:1; L : 1) Ain Sbit: (BW:1; L : 1) | 2 ha 2ha Total : 4 ha | BW: (Brachoua: 25/11/2012; Ain Sbit: 26/11/2012) L: (Brachoua: 12/12/2012; Ain Sbit: 13/12/2012) |  |

| Activity | Number of implemented on-station demonstration on Conservation Agriculture |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-Station demonstration on Conservation Agriculture | 1 |  |  |  |  | Marchouch : (BW: 1) | 2 Ha | BW: (Marchouch: 25/11/2012) | FFS: 7/02/13 Testing 2 seed rates and 3 amounts of Nitrogen fertilization |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

| Activity | Number of implemented on-station demonstration on Conservation Agriculture |  |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | CP | L | C | V |  |  |  |  |
| On-Station demonstration on Conservation Agriculture |  |  | 1 | 1 | 1 | 1 | Marchouch : (FB: 1; CP : 1 L : 1 ; C : 1 ; V : 1) | 2 Ha | FB: (Marchouch: 12/12/2012) CP: (Marchouch: 12/12/2012) L: (Marchouch: 12/12/2012) C: : (Marchouch: 12/12/2012) V: : (Marchouch: 12/12/2012) | FFS: 7/2/13 |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil; C: Canola; V: Vetch

| Activity | Number of realized on farm control of cereals and food legume diseases, pests, weeds, and orobanche |  |  |  |  | Locations * | Total size (ha) | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |
| On farm control of cereals and food legume diseases, pests, weeds, and Orobanche | 3 |  | 2* |  |  | Nkhilat : weed treatment Brachoua : Weed treatment Had Ait Mimoun : weed treatment | 2 1 1 | - Plots infested by weeds particularly bromus - FFS: *8/1/13 at Nkhilat *8/1/13 at Brachoua *31/1/13 at Had Ait Mimoun |

*2 on farm control of cereal and food legume diseases trials will be realized during next April

SUDAN

WORK PLAN 2012/13

| Activity | Number of implemented on-farm demonstration fields |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| - On-farm demonstration of recently released varieties |  |  | 13 | 3 |  | River Nile Village 1: 2 farmers : 2 FB Village 2: 3 farmers: 2 FB Village 3: 3 farmers: 2 FB Village 4: 3 farmers: 2 FB FB var. Ed-Damer and Hudeiba 93 | FB: 6.4 | FB: (River Nile Village 1: farmer 1: 16/11/2012 Village 1: farmer 2: 18/11/2012 Village 1: farmer 3: 26/11/2012 Village 1: farmer 4: 24/11/2012) | 3 Field days were organized; 15-25 farmers in each field day participated. |
|  |  |  |  |  |  | Lower Atbara : FB: 1 CP: 1 | FB: 0.5 CP: 0.25 | FB: 18/11/2012 CP: 22/11/2012 | One field day (20 farmers) |
|  |  |  |  |  |  | Salawa Area: CP: 2 | CP: 4.0 | CP: 22/11/2012 |  |
|  |  |  |  |  |  | Northern state Location 1: FB: 1 (SML) | FB: 1.0 | FB: 1/11/2012 | One field day (30 farmers) |
|  |  |  |  |  |  | Gezira state: CP: 3 | CP: 2.0 | Sowing date for all sites: 26/11/2012 | All genotypes performed good except, Shendi and Jebel Merra (3 field day in 3 sites) |
| 2- Reference site |  |  | 1 | 1 |  | Hudeiba Research Station Field FB 3 var: Hudeiba93+Basabeer+Ed-Damer CP: Atmour +Wad Hamid | 0.3 ha | Recommended sowing date: FB= 7 Feb CP=16 Feb | 2 field days were executed,32 farmers+ extensionist and researchers were participated |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

- On–farm : River Nile:FB=Ed-Damer and Hudeiba 93; CP= Wad Hamid

Northern State:FB= SML

Reference site            FB=Hudeiba93+Basabeer+Ed-Damer

CP= Atmour +Wad Hamid

- Gezira State              CP= Shendi +Burgieg +Wad Hamid  +Atmor +Hawata +Jebel Mara

| Activity | Number of implemented on-farm or on station participatory evaluation trials |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm or on-station participatory evaluation trials |  |  | 3 | 3 |  | Hudeiba: (FB : 6 varieties Merowe: (FB : 6 varieties) Shendi: (FB : 6 varieties) Medani: (CP: 22 resistant to FW and RR and large seeded) Merowe: (CP: 4 resistant to FW and RR ,large seeded and mechanical harvesting) Hudeiba: (CP: 4 resistant to FW and RR , large seeded and mechanical harvesting) | 0.3 0.3 | FB: (Hudeiba: 14/11/12, Merowe: 20/11/12. Shendi: 18/11/12) CP: (Hudeiba: 18/11/12; Merowe: 22/11/12, Medani: 25/11/12) | The 6 genotypes performed better, except at Hudeiba due to high temperature. The performance of all genotypes was much better at Medani and Merowe than Hudeiba |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

FB=Mass\25, Berber12, C.98\8,C.4\02,C.14\02 and C.28\02+2checks.

CP=FLIP02-15C, FLIP0359C, FLIP02-83C and FLIP02-79C

| Activity | Number of implemented on-station seed increase of recently released varieties |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of recently released varieties |  |  | 4 | 3 |  | ▪4 isolated FB fields at Hudeiba Research Station ▪ 3 CP varieties were grown at Hudeiba Research Station | 4.2 1.3 | FB: Field 1: 15/11/12 Field 2: 15/11/12; Field 3: 20/11/12 Field 4: 20/11/ 12 CP: 18/11/2012 | Expected yield= 1.3-1.6 t/ha Good performance |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

Field1(FB)=Hudeiba 93

Field2(FB)= BB7

Field3(FB):Ed-Damer

Field4(FB):SML

CP (Burgieg,Atmor, Hawata)

| Activity | Number of conducted experiments |  |  |  |  | Locations * | Total size (ha) | Duration | Objectives |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| Backup research: Chemical weed control |  |  | 1 | 1 |  | 1-Hudeiba research station 2-Shendi Research Station | 0.5 and 0.7 Pot experiment (FB) | 3 seasons 2 seasons | 1-To use the recommended package (Pendimethalin at 1.2 kg a.i /ha + Imazethapyr at 0.05 kg a.i/ha) applied as a pre-emergence as compared to untreated faba bean farm. 2-To evaluate the efficacy and selectivity of Glyphosate on control of Orobanche |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

FB=BB7(Basabeer)

CP=Burgieg

| Activity | Number of conducted experiments |  |  |  |  | Locations * | Total size (ha) | Duration | Objectives |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| Backup research: Effect of Chemical Fertilization on Faba bean and chickpea seed yields quality at reclaimed high terrace soils conditions, Northern State. |  |  | 1 | 1 |  | Northern state FB (one variety) CP (1 variety) | 0.25 | 2 seasons | To Increase the crop productivity and improve crop quality by using different fertilizers |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

Note: The fertilizers used: Humate, NPK, AS and DAP in addition to Nitrogen.

FB=SML

CP=Burgieg

| Activity | Number of conducted experiments |  |  |  |  | Locations * | Total size (ha) | Duration | Objectives |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| Backup research: Effect of Organic (Cattle, Goat and Chicken manures) and Chemical (N and P) Fertilizers on Yield of Faba bean Genotypes on the Karu soils |  |  | 1 |  |  | River Nile State, Hudeiba: (FB: 2 varieties) | 0.12 | Three seasons | To test the effect of organic fertilizers (balance nutrition) and P and N on yield of faba bean in karu soil. The effect of humate (powder and liquid forms) on faba bean yield was studied only on Basabeer variety. |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

Observation: Chicken manure and humus showed higher number of pods. Generally, the crop had good growth and in the maturity stage.

| Activity | Number of conducted experiments |  |  |  |  | Locations * | Total size (ha) | Duration | Objectives |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| Backup research: Irrigation Strategies to Improve Water Productivity of faba bean and Chickpea at Hudeiba Conditions |  |  | 1 | 1 |  | Hudeiba | 0.5 | 2 seasons | 1-Determination of crop water requirements. 2-Evaluation of crop water productivity and economic water productivity under deficit. 3- Effect of water stress on crop yield. |

CP= Burgieg and Wad Hamid

FB= Basabeer and Ed-Damer

| Activity | Number of visited fields (dd/mm/yy) |  |  |  |  | Locations * | Total size (ha) | Duration | Objectives |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| Backup research: Surveys of virus diseases and field screening for resistance/ tolerance of faba bean, chickpea and lentil in River Nile, Northern and Gezira States |  |  | 5 - | 4 60 | 1 - | River Nile, Gezira States | 50 200 | 2 seasons 3 seasons | To evaluate and assess the prevalence of viruses on these crops. To identify the viruses prevalent in Sudan and to assess their economic importance |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

FB+FC+L= All the released varieties

Survey was done only at RNS and Gezira

| Activity | Number of visited fields (dd/mm/yy) |  |  |  |  | Locations * | Total size (ha) | Duration | Objectives |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| Backup research: Surveys of virus diseases and field screening for resistance/ tolerance of faba bean, chickpea and lentil in River Nile, Northern and Gezira States |  |  | 1 | 1 |  | River Nile, | 0.3 (FB) 0.25 (CP) | Last season 3 seasons | 1-Identify FB genotypes resistant to root rot. 2- Identify CP genotypes resistant to wilt and root rots disease complex. 3- Determine the causal organisms of these diseases |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

1- 26 FB genotypes

2- 16 CP genotypes

TUNISIA

WORK PLAN 2012/13

| Activity | Number of implemented on-farm demonstration fields |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration of recently released varieties | 1 | 5 | 17 | 7 | 4 | Sidi Shili : 1 CP (3 var.: Beja1, Bouchra, Nayer) | Total: 2.8 ha | CP: (Sidi Shili: 28/12/12) | Sidi Shili: Well developed, an extra chemical weed control will be applied |
|  |  |  |  |  |  | Sidi Ismail : 1 CP + 1 FB : (CP: 4 var. Beja1, Bouchra, Nayer and Chetoui; FB : 2 var. Bachaar and Badï) | CP:1.5ha FB:1.5 ha Total: 3 ha | FB : 16/12/12 CP : 25/12/12) | Sidi Smail: faba bean: good vegetative development |
|  |  |  |  |  |  | Boussalem : (CP: 1 var. Beja1, FB: 2 var.: Bachaar and Badï) | CP:.0.5ha FB:0.5ha Total: 1 ha | FB : 30/12/12) CP : 30/12/12) | Boussalem: a relatively early sowing date for faba bean. Need hand weeding. Good development of the chickpea field |
|  |  |  |  |  |  | Fernana: 3 FB fields (FB: 3 var. : Bachaar, Badï and local pop) (3 DW fields DW:4 var. Karim, Salim, Maali and Nasr) | FB:3 ha DW:3 ha Total: 3*2=6 ha | FB: field 1: 27/11/12; field 2: 28/12/12; field 3: 29/12/12) DW : field 1: 27/11/12; field 2: 28/12/12; field 3: 29/12/12) | Fernana: FB and DW: Field 3: good development for faba bean and durum wheat varieties |
|  |  |  |  |  |  | Kef- Zafrana: 1 FB: Bachaar (7 ha) Kef- Mahassen: Farmer Yahyaoui: 1 FB: Bachaar 1.5 ha) Farmer Gmati: 1 FB: Bachaar (3 ha) Kef-Neber: Farmer Lasmar: 1 FB: Bachaar (1 ha) Farmer Dachraoui: 1 FB: Bachaar: (1.4 ha) Kef-Ferchan-Sakiet Sidi Youssef: Farmer Ouihichi: 1 FB : Bachaar: (1 ha) Kef-Ferchan-Sakiet Sidi Youssef: Farmer Kdhaouria: 1 FB: Bachaar (5 ha) Kef-Samana: 1 FB: Bachaar (5 ha) | Total=24.9 ha | FB: (Kef-Zafrana: 25/10/12; Kef- Mahassen: Farmer Yahyaoui: 01/11/12; Farmer Gmati: 01/11/12; Kef-Neber: Farmer Lahmar: 11/11/12; Kef-Neber:Farmer Dachraoui: 20/12/12; Kef-Farchen: farmer Ouihichi 01/11/12; Kef-Farchen: farmer Kdhaouria: 25/11/12; Kef-Samana: 15/12/12) | Kef- Zafrana and Kef- Mahassen: Well developed, an extra chemical weed control will be applied. Kef-Samana: a relatively early sowing date for faba bean. A chemical herbicide was applied. Kef-Neber: Need hand weeding |
|  |  |  |  |  |  | Kef -Touiref ●CP: 3 varieties: Beja 1, Bouchra and Neyer ●FB:2 varieties: Badi, and Bachaar ●L: 2 varieties: Siliana, and Kef | CP: 0.025 ha FB: 0.025 ha L: 0.025 ha Total: 0.075 ha | Kef -Touiref ●CP: 3 varieties: - Beja 1: 02/01/2013 - Bouchra: 02/01/2013 - Neyer :02/01/2013 ●FB:2 varieties: - Badi: 02/01/2013 - Bachaar: 02/01/2013 ●L: 2 varieties: - Siliana: 02/01/2013 - Kef :02/01/2013 | Well developed. Need hand weeding |
|  |  |  |  |  |  | Kef -Touiref DW: 3 varieties: Maali, Nasr, Selim BW:2 varieties: Tahent and Utique | DW: 270m² BW: 180m² Total: 450 m² | DW: 02/01/2013 BW: 02/01/2013 | Well developed A chemical herbicide will be applied |
|  |  |  |  |  |  | Kef -Borj El Ifa ●CP: 3 varieties: Beja 1, Bouchra and Neyer ●FB: 2 varieties: Badi and Bachaar ●L: 2 varieties: Siliana and Kef | CP: 0.05 ha FB: 0.05 ha L: 0.05 ha Total: 0.15 ha | Kef -Borj El Ifa ●CP: 3 varieties: - Beja 1: 10/01/2013 - Bouchra: 10/01/2013 - Neyer: 10/01/2013 ●FB:2 varieties – Badi: 10/01/2013 - Bachaar: 10/01/2013 ●L: 2 varieties: - Siliana: 10/01/2013 - Kef : 10/01/2013 | A relatively late sowing. Need hand weeding |
|  |  |  |  |  |  | Siliana-Elgantra ●CP: 3 varieties: Beja 1, Bouchra and Neyer ●FB: 2 varieties: Badi, and Bachaar ●L: 2 varieties: Siliana, and Kef | CP: 0.05 ha FB: 0.05 ha L: 0.05 ha Total: 0.15 ha | Siliana-Elgantra ●CP: 3 varieties: - Beja 1: 27/12/2013 - Bouchra: 27/12/2013 - Neyer: 27/12/2013 ●FB: 2 varieties: - Badi: 27/12/2013 - Bachaar: 27/12/2013 ●L: 2 varieties: - Siliana: 27/12/2013 - Kef: 27/12/2013 | Well developed. Need hand weeding |
|  |  |  |  |  |  | Siliana - Sidi Bourouis ●CP: 3 varieties: Beja 1, Bouchra and Neyer ●FB: 2 varieties: Badi, and Bachaar ●L: 2 varieties: Siliana, and Kef | CP: 0.025 ha FB: 0.025 ha L: 0.025 ha Total: 0.075 ha | Sidi Bourouis- Siliana ●CP: 3 varieties: - Beja 1: 28/12/2013 - Bouchra: 28/12/2013 - Neyer: 28/12/2013 ; ●FB: 2 varieties: - Badi: 28/12/2013 - Bachaar: 28/12/2013 ●L: 2 varieties: - Siliana: 28/12/2013 - Kef : 28/12/2013 | Need hand weeding |
|  |  |  |  |  |  | Mateur (DW: 3 var.: Maali, Khiar, Nasr) | DW: 1.5 ha | DW: 18/11/12 | Well developed |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

| Activity | Number of implemented on-farm verification trials |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm and on-station verification trials of promising lines | 4 | 5 |  |  |  | Kef - Borj Aifa: DW: 3 varieties: Maali, Nasr, Selim BW: 2 varieties: Tahent and Utique | DW: 0.063 BW: 0.042 Total area: 0.105 ha | 10/01/2013 | Not good developed A chemical herbicide will be applied |
|  |  |  |  |  |  | Siliana- Gantra (farmer field): DW: 3 varieties: Maali, Nasr, Selim BW:2 varieties: Tahent and Utique | DW: 0.063 BW: 0.042 Total area: 0.105 ha | 27/12/2012 | Well developed A chemical herbicide will be applied |
|  |  |  |  |  |  | Siliana- Gantra (Station) DW: 3 varieties: Maali, Nasr, Selim BW:2 varieties: Tahent and Utique | DW: 0.063 BW: 0.042 Total area: 0.105 ha | 27/12/2012 | Well developed A chemical herbicide will be applied |
|  |  |  |  |  |  | Siliana-Sidi Bourouis DW: 3 varieties: Maali, Nasr, Selim BW: 2 varieties: Tahent and Utique | DW: 0.027 BW: 0.018 Total: 0.045 ha | 28/12/2013 | Not good developed late sowing |
|  |  |  |  |  |  | Mateur : (DW : New line) | 0.5 ha | 18/11/12 | Well developed |

| Activity | Number of implemented on-farm or on station participatory evaluation trials |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm or on-station participatory evaluation trials |  |  | 2 | 10 |  | Boussalem (FB: 2 ICARDA trials: FBIN-LT and FBISP-N1) | 0.1 ha | FB: (Boussalem: 04/01/13) | Selection by farmers is planned |
|  |  |  |  |  |  | Kef -Touiref CP: 2 ICARDA trials: CIDTN and CIEN−S | 0.2 ha | Kef -Touiref CP: -CIDTN :02/01/2013 - CIEN−S :02/01/2013 | Selection by farmers will planned in April and May 2013 |
|  |  |  |  |  |  | Kef -Borj El Ifa CP: 2 ICARDA trials: CIDTN and CIEN−S | 0.2 ha | Kef -Borj El Ifa CP: CIDTN:10/01/2013 CIEN−S:10/01/2013 | Selection by farmers will planned in April and May 2013 |
|  |  |  |  |  |  | Siliana-Elgantra CP: 1 -CIDTN | 0.1 ha | Siliana-Elgantra CP: CIDTN:27/12/2013 | Selection by farmers will planned in April and May 2013 |
|  |  |  |  |  |  | Siliana - Sidi Bourouis CP: 1 -CIEN−S | - ha | Siliana- Sidi Bourouis CP: CIEN−S: 28/12/2013 | Selection by farmers will planned in April and May 2013 |
|  |  |  |  |  |  | Sidi Smail (CP: 2 ICARDA trials : CIEN-W and CIEN-S) | 0.2 ha | CP: 25/12/12; | Well developed. Selection by farmers is planned |
|  |  |  |  |  |  | Sidi Shili (CP: 1) | 0.1 ha | CP: 15/01/13 | 12 F9 chickpea populations were sown but poor emergence were recorded |
|  |  |  |  |  |  | Mateur (CP: 1 ICARDA trial CIFW-N) | 0.1 ha | Mateur: --/04/13; | The trial will be sown on April 2013 |

| Activity | Number of planned on-farm seed increase of recently released varieties |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm seed increase of recently released varieties |  |  | 2 | 3 |  | Sidi Shili (CP: 3 Var) | 2.8 ha | CP: (Sidi Shili: 28/12/12) | Well developed, good emergence. Chemical weeding control for grass weed. will be applied |
|  |  |  |  |  |  | Boussalem (FB:2; CP:1) | 0.8 ha | CP: 30/12/12; FB: 30/12/12; | Homogeneous emergence. Hand weeding will be applied |
|  |  |  |  |  |  | Sidi Ismail (CP: 4; FB : 2) | 3 ha | FB: 16/12/12 CP: 25/12/12 | Well performed |

| Activity | Number of implemented on-station seed increase of recently released varieties |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of recently released varieties | 1 | 2 | 3 | 3 | 1 | Beja ; (DW: 4; BW:4; FB: 2 ; CP: 4) | 6 ha | DW: (Beja: 25/11/12; Mateur: 25/11/2012) BW: (Beja: 25/11/12) FB: (Beja: 19/12/12; O. Mliz: 12/12/12;; Morneg: 25/11/2012) PC: (Beja: 04/01/12; O. Mliz: 25-27/12/12) | Oued Beja Station: well performed. Faba bean at flowering stage DW and BW: nitrogen and chemical weed control were performed Oued Meliz: well performed Good development |
|  |  |  |  |  |  | Mateur (DW: 3) |  |  |  |
|  |  |  |  |  |  | O. Mliz (FB: 2; CP: 3) | 3 ha |  |  |
|  |  |  |  |  |  | Morneg (FB: 1) | 0.01ha |  |  |
|  |  |  |  |  |  | Station kef ●CP: 4 varieties: Nour, Bouchra, Beja 1, Neyer, ●FB:1 variety: Chahbi ●L: 3 varieties: Kef, Siliana, Boulifa | ●CP: 0.3 ha ●FB:0.025 ha ●L: 0.3 ha | ●CP: 6 varieties: Nour: 20/12/2012 Bouchra: 21/12/2012 Beja 1: 21/12/2012 Neyer: 21/12/2012 ●FB:1 variety: Chahbi:26/11/2012 ●L: 3 varieties: Kef: 27/11/2012 Siliana : 27/11/2012 Boulifa: 27/11/2012 | Good development |

| Activity | Number of implemented on-station seed increase of promising lines |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station seed increase and maintenance of promising lines | 2 |  | 1 |  |  | Chbika; (10 lines) Boussalem; (BW: 10 lines) Morneg (FB: 10 Lines) | Beja: 0.3 ha Kef: 0.06 ha | BW: Chbika 25/12/2012; Boussalem: 25/12/2012) FB: (Morneg: 17/12/2012) |  |

| Activity | Number of implemented On-station ICARDA or NARS Trials |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station ICARDA and NARS Trials evaluation |  |  | 8 | 2 | 1 | Beja (FB: 75 lines; CP: 40 Lines) O. Mliz (FB: 75 lines; CP: 40 Lines) Kef (CP: 40 lines; L:20 lines) | 2 ha 2 ha 1 ha | FB: Beja: 23-28/11/12; CP: Beja: 25/12/12; FB: O.Mliz: 20-25/11/12; CP: O. Mliz: 20-25/12/12 | Beja: FB-5 trials free orobanche field and 3 trials in a highly infested field with Orobanche foetida. Flowering date and vegetative vigor were recorded (differences between lines were observed). Beja: CP. Trials well implemented in specific fields and good vegetative development is observed |
| Activity | Number of lines screened for biotic tolerance |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
|  | BW | DW | FB | CP | L |  |  |  |  |
| Screening for biotic stress tolerance |  |  | 1 |  |  | Ariana (FB:34 Lines) | 0.09 ha | FB: (Ariana: 30/11/12) | Tolerance to Aphids |

| Activity | Number of implemented on-farm IPM demonstration |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm IPM demonstration |  | 1 | 3 | 4 |  | Hammam Sayala (FB: 1 IPM Orobanche; CP: 1 IPM Orobanche) | 0.8 ha | FB: (Fernana : 27/11/12; Hammam Sayala: 08/12/12) CP: (Hammam Sayala: 15/01/12; Fahs: 11/01/13, Beja: 03/01/13; Mateur: Not yet) DW: (Boussalem: 25/11/2012) | Hammam Sayala: Good development of chickpea and faba bean varieties. Chemical weed control will be performed for grass weed. FB: the first chemical treatment for orobanche (Glyphosate) will be applied in March followed by two other treatments every 15 days. CP: Hand weeding control will be applied due to the little infestation level previously recorded for chickpea Fernana: CA field well implemented with the variety bachaar. This field will be subjected to chemical control of foliar diseases and weeds. |
|  |  |  |  |  |  | Mateur : (CP Beja 1: 1 IPM root rot) | 1 ha |  |  |
|  |  |  |  |  |  | Fernana (FB; 1 IPM Foliar diseases and orobanche) | 1 ha |  |  |
|  |  |  |  |  |  | Béja (CP: Beja 1IPM ascochyta blight | 1 ha |  |  |
|  |  |  |  |  |  | Fahs (CP: Beja 1 and Bouchra; FB: Bachaar and Badi) | 1ha |  |  |
|  |  |  |  |  |  | Boussalem (DW: 1 IPM foot and root rot) | 0.01ha |  |  |

| Activity | Number of implemented on-farm demonstration on supplemental irrigation |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration on supplemental irrigation |  | 2 | 1 | 1 | 1 | Koudia (DW: Maali) 2 fields | 5 ha | DW: (Koudia 1: 24/11/12; Koudia 2: 24/11/12) |  |
|  |  |  |  |  |  | Elgantra- Siliana ●CP: 3 varieties: - Beja 1, - Bouchra - Neyer ●FB:2 varieties - Badi, - Bachaar ●L: 2 varieties - Siliana, - Kef | CP: 0.05 ha FB: 0.05 ha L: 0.05 ha Total: 0.150 ha | Siliana-Elgantra ●CP: 3 varieties: - Beja 1: 27/12/2013 - Bouchra, 27/12/2013 - Neyer:27/12/2013 ●FB:2 varieties: - Badi: 27/12/2013 - Bachaar:27/12/2013 ●L: 2 varieties: - Siliana: 27/12/2013 - Kef: 27/12/2013 | - Well developed, - Need hand weeding and - A chemical fungicide will be applied |

| Activity | Number of implemented on-farm demonstration on Conservation Agriculture |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration on Conservation Agriculture |  | 3 | 1 |  |  | Kef (DW): Maali and Chili | 2 ha | DW: (Kef: 22/11/2012; Koudia: 24/11/12; Fernana: 25/11/12) FB: (Fernana: 25/11/12) | Koudia: well performed and good development And to study the root rot disease |
|  |  |  |  |  |  | Koudia (DW: Maali) | 0.2 ha |  |  |
|  |  |  |  |  |  | Fernana (FB: Badi; DW: Maali) | 0.75 ha 0.75 ha |  |  |

| Activity | Number of conducted experiments |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| Backup research: Control of stem borer on faba bean |  |  | 2 |  |  | Beja (FB. 3) | 0.0020 ha | FB: (Beja: chemical 31/12/12; cultural control : 28/11/12) | Chemical control: Well performed at flowering stage Cultural control (cutting stems) : at flowering stage, the first cultural application was performed |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

| Activity | Number of conducted experiments |  |  |  |  | Locations * | Total size (ha) | Duration | Objectives |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| Backup research: Effect of some cultural practices (rouging, plant density) and insecticides (seed-dressing, foliar spraying) in integrated management of Faba bean necrotic yellow virus infecting faba bean |  |  | 1 |  |  | Morneg (FB: 4) | 0.0150 ha | FB: (Morneg: 1/01/2013) | Well established |

*: Indicate within parenthesis number of varieties; BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil

TURKEY

WORK PLAN 2012/13

| Activity | Number of implemented on-farm demonstration fields |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm demonstration of recently released varieties | 2 | 2 |  | 4 |  | Siverek (DW: 5) TDOKoruklu: (DW:5) Araban : (CP: 4) Yavuzeli : (CP: 4) Eskisehir-Hamidiye: (CP: 5; BW: 3) Usak: (CP: 5; BW: 4) |  | DW: (Siverek) : 27/12/2012; DW TDO Koruklu: 14/12/2012 CP: (Araban) :01/12/2012 ; Yavuzeli: 01/12/2012 BW-CP: (Eskisehir-Hamidiye): BW: 15/10/2012 CP: March - April.2013 BW-CP:Usak: BW: 17/10/2012 CP: March – April 2013 | One workshop Field days |

*: Indicate within parenthesis number of varieties; +: indicate dissemination activities projected and achieved (FFS, Field days, …);

BW: Bread Wheat; DW: Durum Wheat, FB: Faba Bean; CP: Chickpea; L: Lentil; x: number of varieties

| Activity | Number of implemented on-farm verification trials |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-farm verification trials of promising lines | 2 | 1 |  | 4 |  | Siverek (DW: 5) Araban (CP: 4) Yavuzeli (CP: 4) Eskisehir-Hamidiye: (CP: 5; BW: 3) Usak: (CP: 5; BW: 4) | 0.5 0.5 0.25 0.5 0.5 | DW: 27/12/12 CP: 01/12/12 CP: 01/12/12 BW: 15/10/12 CP: Between end of March and early April BW: 17/10/12 CP; Between end of March and early April | Workshop, Field day Field day Field day Field Day |

| Activity | Number of implemented on-station verification trials |  |  |  |  | Locations * | Total size (ha) | Date of sowing of each field | Observations + |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BW | DW | FB | CP | L |  |  |  |  |
| On-station verification trials of promising lines |  | 1 |  |  |  | TDO Koruklu research station: (DW: 5) | 0.5 | 14/12/12 | Workshop Field day |

Annex B

Members of the Steering Committee

| Name | Address | Email |
| --- | --- | --- |
| Dr. Abdel Moneim El-Banna | President, Agricultural Research Center (ARC)9, El-Gama'a Street- 12619 Giza, EGYPT | arcpresident@claes.sci.eg drelbanna@yahoo.com |
| Dr. Omar Zaghouane | Director General Institut Technique des Grandes Cultures (ITGC)1 Avenue Hassan Badi, 16000 El Harrach, Algiers, ALGERIA | Zaghouaneo@yahoo.fr |
| Dr. Dr. Fawzi Al-Sheyab | Director general Center for Agricultural Research and Extension (NCARE), P.O Box 639, Baqa' 19381, JORDAN | director@ncare.gov.jo |
| Dr. Michel Afram | Director General Lebanese Agriculture Research Institute (LARI)Tal Amara, Rayak, P.O. Box Zahle 287, LEBANON | lari@lari.gov.lb |
| Dr. Mohamed Badraoui | Director General Institut National de la Recherche Agronomique (INRA) Avenue de la victoire, B.P 415 Rabat, MAROC | badraoui@inra.org.ma |
| Dr. Ibrahim Adam Ahmed El-Dukheri | Director General, Agricultural Research Corporation (ARC) ARC, P.O. Box 126, Wad Medani, SUDAN | arcdg@sudanmail.mail dukheri@yahoo.com |
| Dr. Mohamed Aziz Darghouth | President Institution de la Recherche et de l'Enseignement Superieur Agricoles (IRESA) 30 rue Alain Savary, 1002 Tunis, TUNISIA | damaziz@yahoo.fr |
| Dr. Hichem Ben Salem | Director General Institut National de la Recherche Agronomique de Tunisie (INRAT) Rue Hédi Karray, 2049 Ariana, TUNISIA | bensalem.hichem@yahoo.com |
| Dr. Ali Osman Sari | Deputy Director General General Directorate of Agricultural Research and Policy (GDAR), Ankara, TURKEY | aosari@tagem.gov.tr |
| Dr. Kamel Shideed | Assistant Director General International Cooperation and Communication ICARDA Northern Um Al Summaq Rajab Al Sleibi St. Building 2, P.O. Box 950764 Amman JORDAN | k.shideed@cgiar.org |
| Dr. Michael Baum | Director of Biodiversity Integrated Gene Management Program ICARDA Mohamed Al Sadeq St. Building 11-B, P.O; Box 950764 Amman, 11195 Rabieh, JORDAN | m.baum@cgiar.org |
| Dr. Mohamed Kharrat | EU-IFAD Project Coordinator ICARDA P.O. Box 6299 Rabats-Instituts, MOROCCO | m.kharrat@cgiar.org |
| Dr. Amine Belhamissi | IFAD representative Coordinator, European Commission/IFAD programs to support CGIAR Via Paolo di Dono 44, 00142 Rome, ITALY | a.belhamissi@ifad.org |

List of National Coordinators

| Name | Country / Institution | E-mail | Phone/Fax | Address |
| --- | --- | --- | --- | --- |
| Mr. Abdenour Zibani | Algeria / ITGC | zibaniabdenour@yahoo.fr | +213 775804731 | No. Aitoukli-Cne Mikira Tizi Ouzou-Algeria |
| Dr. Mohamed Soliman | Egypt / ARC | m.soliman41@yahoo.com | +201145640270 | Field Crop Institute- Food Legume Research Section 9 Gamaa St. Giza; Cairo, Egypt |
| Dr. Faddel Ismail | Jordan / NCARE | faddel@yahoo.com | +962 4725071 | NCARE, P.O. Box 639 Baqa’a 19381 Amman, Jordan |
| Mr. Chafik Stefan | Lebanon / LARI | Cstephan@lari.gov.lb | +961 3 567543 | LARI, Rayak-Tal Amara Bekaa-Lebanon |
| Mr. Fouad Abbad Andaloussi | Morocco / INRAM | abbadandaloussi@yahoo.fr | +212537727274 | Avenue Ennasr, BP 415 RP Rabat, Morocco |
| Dr. Khalifa Gamal El Kheir | Sudan / ARC | gamalhrs@yahoo.com | +241 22496971 | River Edmader, Huckiebu RS, Sudan |
| Dr. Hamadi Ben Salah | Tunisia / INRAT | Bensalah.hbs@gmail.com | +216 23 300 842 | INRAT Rue Hedi Karray 2049 ARIANA-Tunisia |
| Dr. Huseyin Arslan | Turkey / SI | huarslan@hotmail.com | +905445378940 | Recep Zayrip Erdogen balpari; Sanliurfa, Turkey |

List of NARS Staff Involved in 2012/13 Activities

Algeria

| Name | Title (researcher, engineer, technician, …) | Institution |
| --- | --- | --- |
| Abdenour Zibani | Engineer (National Coordinator) | ITGC, Alger |
| Youcef Ghalem | Engineer (Head of service) | ITGC, Alger |
| Malika Souici | Engineer | ITGC, Alger |
| Assia Douici | Engineer (Head of service) | ITGC, Alger |
| Khadidja Hadj Moussa | Engineer | ITGC, Alger |
| Lila Saidi | Engineer | ITGC, Alger |
| Rosa Aid | Engineer | ITGC, FDPS, El Khroub |
| Abdessalem Zeltni | Technician (Local Coordinator) | ITGC, FDPS, El Khroub |
| Abdia Kentour | Engineer | ITGC, FDPS, El Khroub |
| Rédha Bouarroudj | Engineer (Head of service) | ITGC, FDPS, El Khroub |
| Nouri Bouchbout | Engineer | ITGC, FDPS, Guelma |
| Sofiane Boukhenaf | Engineer (Local Coordinator) | ITGC, FDPS, Guelma |
| Nabil Athmania | Engineer | ITGC, FDPS, Guelma |
| Nadia Fellahi | Engineer (Head of service) | ITGC, FDPS, Setif |
| Omar M’hanni | Engineer (Local Coordinator) | ITGC, FDPS, Setif |
| Nadir Harkati | Technician | ITGC, FDPS, Setif |
| Achour Lamrani | Engineer | ITGC, FDPS Beni Slimane |
| Nouredine Sabour | Technician (Local Coordinator) | ITGC, FDPS Beni Slimane |
| Yahia Saadi | Engineer | ITGC, FDPS Beni Slimane |
| Bouelem Mouhou | Engineer | ITGC, FDPS Beni Slimane |
| Kahina Imine | Engineer | ITGC, FDPS Beni Slimane |
| Yamna Ziane | Engineer | ITGC, FDPS Beni Slimane |
| Ahmed Rebita | Engineer (Local Coordinator) | ITGC, FDPS Khemis Meliana |
| Mohamed Boussadi | Engineer (Head of service, Local coordinator) | ITGC, FDPS Oued Smar |
| Mohamed Réda Gaidi | Technician | ITGC, FDPS Oued Smar |
| Chahrazed Tahmi | Engineer | ITGC, FDPS Oued Smar |
| Nadia Boutbila | Engineer | ITGC, FDPS Oued Smar |
| Bouhalouane Amrani | Engineer (Local Coordinator) | ITGC, FDPS Saida |
| Ali Yesli | Technician | ITGC, FDPS Saida |
| Djamel Lakhdar Oulhaci | Engineer | ITGC, FDPS Saida |
| Benali Sakkal | Technician | ITGC, FDPS Sidi Bel Abbes |
| Fatima Zohra Benmansour | Engineer (Head of service, Local coordinator) | ITGC, FDPS Sidi Bel Abbes |
| Labadi Kardi | Technician (Local Coordinator) | ITGC, FDPS Tiaret |
| Brahim Natech | Engineer | ITGC, FDPS Tiaret |
| Laid Bourmel | Technician | ITGC, FDPS Tiaret |
| Yahi Djajati | Technician | ITGC, FDPS Tiaret |
| Mustapha Feknous | Technician | ITGC, FDPS Tiaret |

ITGC: Technical Institute for Field Crops; FDPS : Demonstration and Seed Production Farm.

Egypt

| Name | Title (researcher, engineer, technician, .) |  | Institution |
| --- | --- | --- | --- |
| Mohamed Soliman Mohamed | Deputy director of FCRI, Nat. Coordinator |  | FCRI |
| Mahmoud Abdel Mohsen | Head of Food Legume Res. Department |  | FLRD – FCRI |
| Shaaban Ali Khalil | Researcher Head |  | FLRD, FCRI, Giza |
| Samia Ali Mahmoud | Researcher Head |  | FLRD, FCRI, Giza |
| Ahmed Helmy Abdallateef | Researcher Head |  | FLRD, FCRI, Giza |
| Mamdoh Ahmed Omar | Researcher Head |  | FLRD, FCRI, Giza |
| Hamdy Aziz Saber | Researcher Head |  | FLRD, FCRI, Giza |
| Mounir Mohamed Elhady | Researcher Head |  | FLRD, FCRI, Giza |
| Sabah Mahmoud Atteia | Researcher Head |  | FLRD, FCRI, Giza |
| Azzam Abd-Elrazik | Senior Researcher |  | FLRD, FCRI, Giza |
| Rehab A.M. Abd El-Rahman | Researcher and Focal Point |  | FLRD, FCRI, Giza |
| Mostafa Abd-Elmoamen | Researcher |  | FLRD, FCRI, Giza |
| Mohamed Abd-Elrahman Alboraai | Researcher Head |  | FLRD, FCRI, Sakha |
| Mostafa Mohamed Radi | Researcher Head |  | FLRD, FCRI, Sakha |
| Ola Ahmed Mokhtar | Researcher Head |  | FLRD, FCRI, Sakha |
| Refaat Abd-Elsalam | Researcher Head |  | FLRD, FCRI, Sakha |
| Waleed Mohamed Alrodeny | Researcher |  | FLRD, FCRI, Sakha |
| Alsaid Mohamed Rabeea | Senior Researcher |  | FLRD, FCRI, Gemmeza |
| Aza Fathi Alsaid | Researcher |  | FLRD, FCRI, Gemmeza |
| Abo-Zaid Abd-Elmohsen | Assistant Researcher |  | FLRD, FCRI, Nubaria |
| Reda Ali Mohamed | Assistant Researcher |  | FLRD, FCRI, Nubaria |
| Waleed Raafat Nakhla | Assistant Researcher |  | FLRD, FCRI, Nubaria |
| Saied Halem Mansour | Researcher Head |  | FLRD, FCRI, Nubaria |
| Melad Shendi Said | Researcher Head |  | FLRD, FCRI, Nubaria |
| Mohamed Abd-Almonaem | Researcher Head |  | FLRD, FCRI, Nubaria |
| Gamal Abd-Alaziz | Senior Researcher |  | FLRD, FCRI, Mallawy |
| Mostafa Mohamed Soliman | Senior Researcher |  | FLRD, FCRI, Mallawy |
| Nagat Gabr Abdalla | Researcher |  | FLRD, FCRI, Mallawy |
| Adel Magdi Gabra | Researcher |  | FLRD, FCRI, Mallawy |
| Magdi Mohamed Alkhadary | Engineer |  | FLRD, FCRI, Mallawy |
| Sanad Reiad Saleeb | Researcher Head |  | FLRD, FCRI, Shandweel |
| Ragab Ahmed | Socio-economist |  | Economic Res. Ins. |
| Ehab Sarhan | Pathologist |  | Pathology Res. Ins. |
| Mahmoud Mohamed Kheua | Entomologist |  | Plant protection |
| Sanaa Abd El-Monaem | Researcher Head |  | Soil, Water and Env. Res. Ins. |
| Akram Nassar | Researcher Head |  | Central Lab for Weed Control |
| Extension staff involved in the project |  |  |  |
| Central Administration for Extension |  |  |  |
| Mohamed Shaaban Rakha | Engineer |  | H.Q., Giza |
| Radwan Ali Muhammad | Engineer |  | H.Q., Giza |
| Al-Sharkia Governorate |  |  |  |
| Alaa Mohammed Afifi | Engineer | Agriculture Directorate |  |
| Mohamed Mohamed Abdel-Hamid | Engineer | Agriculture Directorate |  |
| Diaa Eldin Abdel-Alim | Extension Specialist | Agriculture Directorate |  |
| Zainab Bakr Eldsoqi | Extension Specialist | Agriculture Directorate |  |
| Buthaina Abdel Aziz Ngida | Extension Specialist | Agriculture Directorate |  |
| Hassan Mohamed Ali | Extension Specialist | Agriculture Directorate |  |
| Khaled Shaaban | Extension Specialist | Agriculture Directorate |  |
| Adel Elhadidi | Extension Specialist | Agriculture Directorate |  |
| Mohammed Abdallah | Extension Specialist | Agriculture Directorate |  |
| Ahmed Mahmoud Hassan | Extension Specialist | Agriculture Directorate |  |
| Atwa Mohammed Atwa | Extension Specialist | Agriculture Directorate |  |
| Assiut Governorate |  |  |  |
| Hassanein Sid Ahmed | Engineer | Agriculture Directorate |  |
| Mohamed Mahmoud Sultan | Engineer | Agriculture Directorate |  |
| Mahmoud Abdel-Salam Hassan | Extension Specialist | Agriculture Directorate |  |
| Mohamed Abdel-Shafi Mohamed | Extension Specialist | Agriculture Directorate |  |
| Kafr El-Sheikh Governorate |  |  |  |
| Lotfi Kamal Demerdash | Engineer | Agriculture Directorate |  |
| Saad Ali Sakr | Engineer | Agriculture Directorate |  |
| Samir Abd al-Majid Minshawi | Extension Specialist | Agriculture Directorate |  |
| Mohammed Mustafa Fayed | Extension Specialist | Agriculture Directorate |  |
| Yossef Bassiouni Al-Shami | Extension Specialist | Agriculture Directorate |  |
| Ahmed Mohamed Gouda | Extension Specialist | Agriculture Directorate |  |
| Mamdouh Morsi Abdul Latif | Extension Specialist | Agriculture Directorate |  |
| Dakahlia Governorate |  |  |  |
| Ahmed Awad Ahmed | Engineer | Agriculture Directorate |  |
| Mahmoud Mahmoud Younis | Engineer | Agriculture Directorate |  |
| Hassan Elsaid El-Sharkawy | Extension Specialist | Agriculture Directorate |  |
| Hamed Mohamed El Ghazlawi | Extension Specialist | Agriculture Directorate |  |
| Emad Mohammed Ferjani | Extension Specialist | Agriculture Directorate |  |
| Salim Elsaid Salim | Extension Specialist | Agriculture Directorate |  |
| Ayman Mohammed Abu Alhamail | Extension Specialist | Agriculture Directorate |  |
| Nubaria Governorate |  |  |  |
| Salah Eldin Ahmed Ali | Engineer | Agriculture Directorate |  |
| Yonan Aqladeus rasan | Engineer | Agriculture Directorate |  |
| Ahmed Mohamed Abdel Monein | Extension Specialist | Agriculture Directorate |  |
| Sameh Abdel Bari | Extension Specialist | Agriculture Directorate |  |
| Sami Ashmawi Sied Ahmed | Extension Specialist | Agriculture Directorate |  |
| Ashraf Mohammed Abu Zaid | Extension Specialist | Agriculture Directorate |  |
| Alkhedawy Hassouna Mohamed | Extension Specialist | Agriculture Directorate |  |
| Emad Abdel Mawla | Extension Specialist | Agriculture Directorate |  |
| Moman Yassin Mohammed | Extension Specialist | Agriculture Directorate |  |
| Ahmed Mohammed Anani | Extension Specialist | Agriculture Directorate |  |
| Khamis Zakaria Ali | Extension Specialist | Agriculture Directorate |  |
| Sameh Rada | Extension Specialist | Agriculture Directorate |  |

Jordan

| Name | Title (researcher, engineer, technician, …) | Institution |
| --- | --- | --- |
| Faddel Ismail | Researcher, PhD, National Coordinator | NCARE, Head quarter |
| Yahia Shakhatreh | Researcher, PhD | NCARE, Head quarter |
| Amal Alkhateb | Researcher, MSc | NCARE, Head quarter |
| Yahia Ban Khalaf | Researcher, BSc | NCARE, Maru station |
| Ahmmad Albataineh | Researcher, BSc | NCARE, Maru station |
| Mahmod Hwayan | Researcher, BSc | NCARE, Mushager station |
| Awad Al-Kaabneh | Researcher, BSc | NCARE, Mushager station |
| Abd El-Rahem Bawalize | Researcher, PhD | NCARE, Rabba station |
| Maysa Hadaden | Researcher, MSc | NCARE, Rabba station |
| Doa Al-Majale | Researcher, BSc | NCARE, Rabba station |
| Mosa Sawalha | Technician, Diploma | NCARE, Head quarter |

NCARE: National Center for Agricultural Research and Extension

Lebanon

| Name | Title (researcher, engineer, technician, …) | Institution |
| --- | --- | --- |
| Chafic Estephan | Researcher, MSc (National Coordinator) | LARI |
| Racha El Moussawe | Assistant researcher, Engineer | LARI |
| Hussein Hajj Hassan | Technician | LARI |
| Joseph Aziz | Technician | Support LARI’s Team |

LARI: Lebanese Agricultural Research Institute

Morocco

| Name | Title (researcher, engineer, technician, …) | Institution |
| --- | --- | --- |
| Fouad Abbad Andaloussi | Researcher, National Coordinator | INRA/DS |
| Hamida Hilali | Researcher | INRA/DS |
| Rachid Mossadek | Researcher | INRA/Rabat |
| Maadoudi Lhaj | Researcher | INRA/Rabat |
| Mohamed Khadir | Researcher | INRA/Rabat |
| Ahmed Douiek | Researcher | INRA/Rabat |
| Abdelmajid Zouahri | Researcher | INRA/Rabat |
| Hamza Laaich | Researcher | INRA/Rabat |
| Hasnae Yachou | Researcher | INRA/Rabat |
| Fatima Gaboune | Researcher | INRA/Rabat |
| Saadia Lhaloui | Researcher | INRA/Settat |
| Nasrolhaq Nasrollah | Researcher | INRA/Settat |
| Chafika Houasli | Researcher | INRA/Settat |
| Abdellah El Aissaoui | Researcher | INRA/Settat |
| Jamal El Haddoury | Researcher | INRA/Settat |
| Sanae Benchekroun Krimi | Researcher | INRA/Settat |
| Mohamed Boughlala | Researcher | INRA/Settat |
| Abdelhamid Hamal | Researcher | INRA/Meknès |
| Abdelhamid Ramdani | Researcher | INRA/Meknès |
| Zine El Abidine Fatemi | Researcher | INRA/Meknès |
| Sahar Bennani | Researcher | INRA/Meknès |
| Allal Souihka | Technician | INRA/ Rabat |
| Moubarek El Ouadi | Technician | INRA/Rabat |
| Beggali Elghazouani | Technician | INRA/Rabat |
| Bouazza Ibriz | Technician | INRA/Meknès |
| Hillal Bahadou | Technician | INRA/Settat |

INRA: National Institute for Agricultural Research

Sudan

| Name | Title (researcher, engineer, technician, …) | Institution |
| --- | --- | --- |
| Khalifa Gamal El Kheir | Researcher, PhD (National Coordinator) | ARC |
| Omer H. Ibrahim | Researcher | ARC-Hudeiba Research Station |
| Hassan K. Ali | Researcher | ARC-Hudeiba Research Station |
| Mai K. Allajabo | Researcher | ARC-Hudeiba Research Station |
| Amel A. Mohamed | Researcher | ARC-Hudeiba Research Station |
| Haider S. Abdalla | Researcher | ARC-Hudeiba Research Station |
| Khalid M. Ali | Researcher | ARC-Hudeiba Research Station |
| Ayman Elamin | Researcher | ARC-Hudeiba Research Station |
| Khali H. Elhassan | Researcher | ARC-Hudeiba Research Station |
| Zayed B. Mahgoub | Researcher | ARC-Hudeiba Research Station |
| Alaeldin M. Elhassan | Researcher | ARC-Hudeiba Research Station |
| Hassan A. Ali | Researcher | ARC-Shendi Research Station |
| Nasereldeen M. Kheri | Researcher | ARC-Shendi Research Station |
| Safa H. Basheer | Researcher | ARC-Shambat Research Station |
| Noha Abdelwahab | Researcher | ARC-Soba, R.S. (Khatoum) |
| Abdelmagid A. Hamed | Researcher | ARC-Gezira Research Station |
| Omyma Elmahi | Researcher | ARC-Gezira Research Station |
| Fathelaleim M. Hamza | Researcher | ARC-Merowe Research Station |
| Eltyeb M. Abdelgadir | Researcher | ARC-Dongola Research Station |
| Somia O. Ebaeed | Technician | ARC- Hudeiba Research Station |
| Hisham M .Balla | Technician | ARC-Hudeiba Research Station |
| Yassmin Khidir | Technician | ARC-Hudeiba Research Station |
| Nizar B. Elnour | Technician | Min. of Agri. River Nile State |
| Hadia Abdelmagid | Technician | ARC-Hudeiba Research Station |
| Mariam Idrris Saad | Technician | ARC- Hudeiba Research Station |
| Eltyeb A .Ali | Technician | Min of Agri. River Nile State |
| Nusiba Yousif | Technician | ARC-Hudeiba Research Station |
| Fatma Haroon | Technician | ARC-Hudeiba Research Station |
| Adel M .Abdalla | Technician | ARC-Dongola Research Station |
| Amani Eltigani | Technician | ARC-Gezira Research Station |
| Hafiz E. Ahmed | Technician | ARC-Merowe Research Station |
| Abdelmonim G.Suliman | Extensionist | Min of Agri. River Nile State |
| Salih A.Saeed | Extensionist | Min of Agri. River Nile State |
| Lubna F.Abddella | Extensionist | Min of Agri. River Nile State |
| Suzan H. Abdella | Extensionist | Min. of Agri. River Nile State |
| Musa Abdelraheem | Extensionist | Min of Agri. Northern State |

Tunisia

| Name | Title (researcher, engineer, technician, …) | Institution |
| --- | --- | --- |
| Hamadi Ben Salah | Head of Field Crop Lab., Nat. Coordinator | INRAT (Tunis) |
| Med Salah Gharbi | Researcher | INRAT (Tunis) |
| Noura Omri | Researcher | INRAT (Tunis) |
| Sonia Bouhachem | Researcher | INRAT (Tunis) |
| Meriam Bouhdida | Researcher | INRAT (Tunis) |
| Samia Gargouri | Researcher | INRAT (Tunis) |
| Hatem Becheikh | Researcher | INRAT (Tunis) |
| Jouda Mediouni | Researcher | INRAT (Tunis) |
| Asma Najar | Researcher | INRAT (Tunis) |
| Olfa Mlayeh | Technician | INTRAT (Tunis) |
| Basma Bergaoui | Technician | INRAT (Tunis) |
| Mouheddine Mouelhi | Technician | INRAT (Kef) |
| Mosen Rezgui | Researcher | INRAT (Kef) |
| Salah Becherif | Technician | INRAT (Kef) |
| Tarek Jarahi | Engineer (Local coordinator) | INGC (Boussalem) |
| Houcine Anguer | Engineer | INGC (Boussalem) |
| Dorsaf Hlel | Engineer | INGC (Boussalem) |
| Moez Amri | Researcher (Local Coordinator) | CRGRC (Béja) |
| Kalthoum Harbaoui | Researcher | CRRGC (Béja) |
| Lazhar Sakkouhi | Engineer | CRRGC(Béja) |
| Fadhel Sellami | Technician | CRGRC (Béja) |
| Yamonta Sallami | Technician | CRGRC (Béja) |
| Laila Dakhli | Ingénieur | CRGRC (Béja) |
| Mouna Guesmi | Technician | CRGRC (Béja) |
| Mongi Ben Younes | Researcher (Local Coordinator) | PRRDANO Kef |
| Ali Ouji | Researcher | PRRDANO Kef |
| Samira Chkili | Researcher | PRRDANO Kef |
| Sourour Ayed | Researcher | PRRDANO Kef |
| Mounir Rezgui | Technician | PRRDANO Kef |
| Houcine Chuili | Technician | PRRDANO Kef |

INRAT : National Agricultural Research Institute of Tunisia, CRRGC : Regional Research Center for Field Crop of Beja, INGC: National Institute of Field Crops of Boussalem; PRRDANO Kef : Regional Pole for Research and Agricultural Development of North West -Kef

Turkey

| Name | Title (researcher, engineer, technician, …) | Institution |
| --- | --- | --- |
| Hüseyin Arslan | PhD, National Coordinator | GAPARI (Şanliurfa) |
| Ali İlkhan | MSc, Researcher, Wheat breeder | GAPARI (Şanliurfa) |
| İ. Halil Cömert | MSc, Researcher, Wheat breeder | GAPARI (Şanliurfa) |
| Savaş Belen | MSc, Researcher, Wheat breeder | TZARI (Eskişehir) |
| Muammer Tekatli | MSc, Researcher, Chickpea breeder | TZARI (Kahramanmaraş) |
| Evren Atmaca | MSc, Researcher, Chickpea breeder | TZARI (Eskişehir) |
| Tali Monis | MSc, Agricultural Economist | GAPARI (Şanliurfa) |
| Şeyda İpekçioğlu | MSc, Agricultural Economist | GAPARI (Şanliurfa) |
| Şehnaz Buyukhatipoglu | MSc, Agricultural Economist | GAPARI (Şanliurfa) |
| Muhammet Sami Bayraktar | MSc, Agricultural Economist | GAPARI (Şanliurfa) |

GAPARI: GAP Agricultural Research Institute, TZARI : Transitional Zone Agricultural Research Institute

Annex C

List of Trainees

|  |  | Participants in the training course on Classical and Molecular Approaches in Wheat Breeding Egypt (Sids & Cairo) – 10 - 21 March 2013 |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Name of participants |  | Gender | Country | Institutions |
| 1 | Mr Khaled Ibrahem Gad |  | M | Egypt | ARC |
| 2 | Ms Doua'a Abed Al Hameed Al Majali |  | F | Jordan | NCARE |
| 3 | Ms Rola Mohammed Bouzeid |  | F | Lebanon | LARI |
| 4 | Ms Sahar Bennani |  | M | Morocco | INRA |
| 5 | Mr Elfadil Mohammed Eltayeb Elbashier |  | M | Sudan | ARC |
| 6 | Ms Sourour AYED |  | F | Tunisia | IRESA/PRDNOSA Kef |
| 7 | Mr Ali IlKhan |  | M | Turkey | GAPARI Sanliurfa Institute |
| 8 | Ms Guerfa Wafa* |  | F | Algeria | ITGC |

*: Could not come

|  |  | Participants in the training course on Food Legume Breeding Lebanon (Terbol) – 08 - 19 Avril 2013 |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Name of participants |  | Gender | Country | Institutions |
| 1 | Mr. Bouarroudj Rédha |  | M | Algeria | ITGC |
| 2 | Mr. Mostafa Abdelmoamen Mohamed Ibrahem |  | M | Egypt | ARC, FCRI |
| 3 | Mr. Yahya Mustapha Bani-Khalaf, |  | M | Jordan | NCARE |
| 4 | Ms. Chafika Houasli |  | F | Morocco | INRA |
| 5 | Mrs. Amel Adam Mohamed Ibrahim |  | F | Sudan | ARC |
| 6 | Mr. Kifah Gharzeddin |  | M | Syria | GCSAR |
| 7 | Mr. Arslan Uzun |  | M | Turkey | Black Sea Agricultural Research Institute of Field Crops Samsun |
| 8 | Mrs. Mariem Bouhdida Ksiaa |  | F | Tunisia | INRAT |
| 9 | Mr. Ebrahim Abdulwahab Yahya |  | M | Yemen | Central Highlands Research Station, Dhamar |
| 10 | Ms. Rasha Moussawi |  | F | Lebanon | LARI |

|  |  | Participants in the training course on Integrated Pest Management for Cereals and Food Legumes Algeria (Algiers) – 21 - 30 Avril 2013 |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Name of participants |  | Gender | Country | Institutions |
| 1 | Assia Douici Khalfi |  | F | Algeria | ITGC |
| 2 | Reda Ibrahim Ammar |  | M | Egypt | ARC-PPRI |
| 3 | Nawal Al-Hajaj |  | F | Jordan | NCARE |
| 4 | Hiba Dokmak |  | F | Lebanon | LARI |
| 5 | Abdellah El Aissaoui |  | M | Morocco | INRA |
| 6 | Asrar Elgasim El Basheir Mustafa |  | F | Sudan | ARC- Dongola/North Sudan |
| 7 | Noura Ben Yousef Omri |  | F | Tunisia | INRAT |
| 8 | Abdallah Taner Kilinc |  | M | Turkey | TZAI-GDAR |

Annex D

RESULTS-BASED LOGICAL FRAMEWORK

Enhanced small-holder wheat-legume cropping systems to improve food security under changing climate in the drylands

of West Asia and North Africa

| Objectives | Indicators | Means of Verification | Progress in achievements |
| --- | --- | --- | --- |
| GOAL (Impact): Enhanced food and nutritional security, improved livelihoods of rural communities and agricultural sector growth in the countries of West Asia and North Africa (WANA) in the face of increasing climatic variability and change | - Increased national food and nutritional security. - Reduced vulnerability of farm families whose livelihood depends on income from wheat-food legume based farming systems. - Improved agricultural productivity, better quality of wheat and food legume products and more sustainable utilization of natural resources. - Risk for disease epidemics reduced | - National economic statistics - National income statistics - National food trade statistics |  |
| PURPOSE (Outcome): To deliver pro-poor scientific and technological innovations to increase and stabilize the productivity of wheat and food legume based production systems in the dry areas of WANA. | - Improved varieties released and adopted by farmers - Improved production technologies and crop management practices adopted by farmers. - Measurable increase in productivity in farmers’ fields - Reduced losses from diseases and increased stability of wheat-grain legume yields. - Enhanced professional capacity of NARS and increased research efficiency and exchange of knowledge | - National agricultural production statistics - Adoption and impact studies - NARS annual work programs and reports |  |
| Specific Objective 1: Promotion of proven and tested technologies for wheat-legume rotation systems, by scaling out existing improved wheat and food legume varieties and associated production technologies, while concurrently identifying and testing appropriate new technologies to sustainably improve productivity and production. |  |  |  |
| OUTPUTS | Indicators | Means of Verification | Progress in achievements |
| - High yielding and stress tolerant wheat and food legume germplasm and associated technologies tested and adapted to farmers’ production environments and end-user requirements | - Number of farmers in target areas adopting new germplasm and associated technologies - Increased yields in farmers’ fields - Reduced costs and increased returns of production in farmers’ fields | Project report & field records | - Several on-farm demonstrations of recently released varieties of wheat and food legumes are conducted in 7 countries in 2012/13 - Preliminary results from Egypt showed the superiority of the varieties tested in 2012/13 with recommended package - Field days are organized in Egypt, Sudan, Tunisia, Algeria, Turkey - Many farmers in Egypt and Sudan already claimed for testing the new varieties - Progress (%) in implementing the activities: 35% |
| - Preferred genotypes identified in participatory varietal selection trials, submitted by national programs for varietal release in targeted production areas | - Number of varieties submitted for national release | Records of national variety release programs | - Participatory evaluation trials are planted in farmer fields in some of the involved countries during the cropping season 2012/13. - Farmers are invited to research stations to evaluate with breeders the improved lines included in Yield Trials or in verification trials - Submission for release will be done accordingly and the evaluation of farmers considered - Progress (%) in implementing the activity: 30% |
| - New and emerging constraints to the adoption by farmers of improved technologies identified and feedback provided to technology development and adaptive research program. | - Further adaptive research to address emerging constraints - Recommended policy and institutional options for relieving constraints | - Farmer surveys & constraints analyses - Research plans - Project reports | Surveys are done in some countries during 2012 (diseases and pests of food legumes in Morocco; virus diseases in Sudan and Tunisia particularly on food legume) Other surveys are planned in 2013, Progress (%) in implementing the activity : 50% |
| - National seed systems strengthened through technical training and advisory services | - National seed systems trained in seed technology, seed marketing and seed enterprise development | - Project reports - Training programs & reports - National seed systems business plans | - Mission of ICARDA scientists from seed section and socio economic policy research program to Morocco last week of January 2013 to establish contact and collecting basic data to initiate the seed sector study focusing on faba bean - Questionnaire has been developed - Mission of scientist from seed section to evaluate the possibility of development of informal seed production in Algeria and Tunisia - Regional course is planned in 2013 in Turkey in June 2013 with one participant by country (12 participants). - Progress (%) in implementing the activity : 20% |
| - Financially viable community- or farm-based seed production enterprises, capable of producing quality-assured seed, established in pilot sites | - Number of community- or farm-based seed production enterprises established in target areas - Quantity of seed produced | - Project reports - Seed enterprise business plans and records | Countries are requested to determine their needs in small equipment for establishment of farmer community based seed production. Progress (%) in implementing the activity : 5 % |
| - New conservation agriculture-based wheat-legume rotation systems developed and tested in farmers’ fields | - Number of farmers in target areas adopting conservation agriculture systems - Yields in farmers’ fields - Costs and returns of production in farmers’ fields | Project reports & field records | - Conservation agriculture on-farm demonstrations are implemented in 2012/13 in 6 countries (Morocco, Lebanon, Tunisia, Egypt, Algeria, Jordan) - Progress (%) in implementing the activity : 30 % |
| - Integrated supplemental irrigation and crop management packages that conserve water and maximize crop productivity developed and tested in the target areas | - Number of farmers in target areas adopting supplemental irrigation and crop management packages - Yields in farmers’ fields, and water productivity - Costs and returns of production in farmers’ fields | Project reports & field records | - Supplemental irrigation is demonstrated in Algeria, Egypt, Tunisia and Lebanon mainly on wheat and faba bean - Progress (%) in implementing the activity : 30% |
| - Results from wheat and food legumes baseline and variety adoption surveys and constraints analysis communicated to users including research, extension, development agencies and policy decision-makers | - Data base of baseline production and varietal adoption - List and ranking of major constraints to adoption of modern varieties - Recommendations to address constrains to technology adoption | - Research reports, farm surveys, policy briefs, seminar presentations - Meetings with decision-makers | - Initiated in Morocco (done in collaboration with CRP3.1 - Enumerators will be trained in Morocco in Mai 2013 Progress (%) in implementing the activity: 30% |
| - Gender analysis including the differentiation of the constraints that men and women face in accessing technologies, information and markets communicated to relevant stakeholders including to research, extension development organizations and policy decision-makers | - Institutional and policy options the remove gender inequity delivered to and discussed with decision-makers | - Project reports & field records - Publications - Meetings with decision-makers | Gender analysis initiated in 2012 in Morocco and in 2013 in Egypt Progress (%) in implementing the activity : 30% |
| - Analysis of productivity trends and gaps on wheat and food legume based systems made available to relevant institutions and policy decision-makers | - Data base, productivity gap estimates | Project reports | Will be initiated in 2013 |
| - Research capacity of national programs enhanced through training and networking | - NARS trained in new techniques such as double haploid breeding, marker-assisted selection and transformation - 2 PhD, 3 MSc, 3 long term and 10 short term trainees trained in breeding and associated disciplines | - Training programs & reports - Graduate student degrees | Training of young scientists initiated Progress (%) in implementing the activity : 20% |

| ACTIVITIES | Indicators | Progress in achievements |
| --- | --- | --- |
| - Baseline studies, gender and constraints analysis | Baseline data and information on farmers’ constraints used in the other research activities | - Started in Morocco since 2012 and will be finalized in 2013 - Just initiated in Egypt in April 2013 |
| - Adoption studies | State of technology adoption | - Started in Morocco since 2012 and will be finalized in 2013 - Just initiated in Egypt in April 2013 |
| - Analysis of wheat and food legumes systems productivity gaps and determinants of these gaps | Data base and productivity gap analysis | - Started in Morocco since 2012 and will be finalized in 2013 - Just initiated in Egypt in April 2013 |
| - On farm varietal trials for wheat and legumes | Number of trials established in farmers’ fields | - Started in 7 countries in the WANA region in 2012/13 cropping season |
| - WANA yield trials for wheat and legumes | Number of trials established in farmers’ fields | - Several nurseries and trials of food legumes trials have been distributed to NARS in 2011 and 2012 - Some of them are implemented in farmer fields in 2012 - Progress (%) in implementing the activity: 70% |
| - Demonstrate IPM options for soil-borne, foliar diseases, insect pests. | Number of trials established in farmers’ fields | - IPM packages for controlling diseases, insects and Orobanche are implemented in several countries in farmers’ fields in 2012/13 - Progress (%) in implementing the activity:30% |
| - Demonstrate conservation agriculture technologies in farmers’ fields | Number of trials established in farmers’ fields | - Conservation agriculture on wheat, faba bean, chickpea and lentil are implemented in several countries in cropping season 2012/13 - Progress (%) in implementing the activity: 30% |
| - Conduct regional courses for technical managers and technical staff on seed technology, seed marketing, seed enterprise development | Number of training courses and number of staff trained | - A training course on “Seed technology, seed marketing and seed enterprise development is scheduled for June 2013 in Turkey |
| - Monitor and assess technical performance and economic viability of farmer-based seed enterprises | Business plans of farmer-based seed enterprises | - NARS are contacted to identify the group of farmers potentially interested by developing farmer-based seed enterprises |
| - Training of NARS in new techniques such as doubled haploid breeding, marker-assisted selection and transformation | Number of training courses and number of staff trained | - Students are received for training in MAS and DH - Training will continue in 2013 |
| - Train 2 PhD, 3 MSC, 3 long term and 10 short term trainees trained in breeding and associated disciplines | Trained staff | Contribution in supporting some PhD and MSc students 25 trainees where fully supported by the project in 3 short terms courses organized in spring 2013 |
| - Adoption and impact of improved wheat-legume varieties on crop productivity and household income documented in selected countries | Reports of adoption and impact studies | Is in course of study in Morocco and in Egypt Progress (%) in implementing the activity: 30% |
| - Integrated supplemental irrigation and crop management techniques and deficit supplemental irrigation developed and tested in major agroecosystems of WANA | Number of trials established in farmers’ fields | Some countries are conducting trials on supplemental irrigation Progress (%) in implementing the activity: 30% |
| - One MSc student and 25 trainees trained through short courses and on-the-job on supplemental irrigation | Trained staff | Student identified starting 2013 Training is planned in May 2013 for at least 6-8 trainees and then they will organize in country training for farmers. |
| - Document and disseminate gender related research to stakeholders including policy makers. | Reports of gender related research | Is scheduled for 2013 |

| Specific Objective 2: Development of new germplasm and production technologies to cope with climate change. |  |  |  |
| --- | --- | --- | --- |
| OUTPUTS | Indicators | Means of Verification | Progress in achievements |
| - New wheat and food legume genotypes, better adapted to climate variability and change | - Number of new genotypes with required resistance and end use quality | - Project reports, lab records - Results of breeding programs | - Several promising lines of wheat and food legumes with resistance and tolerance to different stresses are proposed - Progress (%) in implementing the activity: 70 % |
| - Sustainable wheat-legume rotation system established at farm level. | - Number of farmers in target areas adopting wheat-legume rotation systems - Cropping systems productivity in farmers’ fields | - Project reports & field records | - Crop rotation including food legume are established. - Progress (%) in implementing the activity: 30% |
| - IPM options for key diseases, insect pests and parasitic weeds with wide effectiveness demonstrated on farmers’ fields. | - Farmers in target areas adopt IPM options - Strategies for further dissemination of IPM practices | - Project reports & field records - NARS work programs and reports | - Several resistant varieties to pests and diseases have been released in wheat and food legumes and recommended as component of IPM - Other elements are proposed for IPM (glyphosate application for Orobanche, fungicide, sowing date, …) - Progress (%) in implementing the activity: 70% |
| - GIS spatial analysis of dry area farming systems and geo-statistics of crop adaptation and disease/pest prevalence to help target technology interventions. | - NARS use information for targeting technology interventions - Strategies for control of emerging pests and diseases | - Project reports, databases and maps - NARS work programs and reports | - GIS and Geo statistics started to be used (Morocco) and will be developed in Tunisia in 2013 - Progress (%) in implementing the activity: 30% |
| - Tools for determining new supplemental irrigation schedules and packages for better adaptation of wheat-legume systems to climate change | - NARS use a validated model for simulating the effect of climate change on rainfed wheat-legumes areas and develop adaptation strategies using supplemental irrigation and other water management option - NARS use spatial maps for identifying areas to apply supplemental irrigation | - Project reports, databases, maps and simulation models - NARS work programs and reports | - Will be developed in 2013 and 2014 - Progress (%) in implementing the activity: 10% |
| - Ex-ante assessments of the potential impact of improved wheat-legume varieties and associated technologies on crop productivity, household income and food supply documented in selected countries | - Ex-ante assessments of the potential impact of new technologies delivered to, and discussed with, decision-makers | - Project report - Survey results - Impact briefs - Seminar presentations | - Progress (%) in implementing the activity: 20% |
| - The impacts of selected crop diseases evaluated and farmers’ perceptions and practices in managing plant diseases analyzed | - Estimates of costs of major crop disease communicated with stakeholders | - Project report - Survey results - Impact briefs - Seminar presentations | - In progress |

| ACTIVITIES | Indicators | Progress in achievements |
| --- | --- | --- |
| - Strengthen pre-breeding and germplasm enhancement components of breeding programs | Established program of biotechnological innovations and genotyping and phenotyping of ICARDA’s genetic resources | Genotyping and phenotyping is conducted Progress (%) in implementing the activity: 70% |
| - Identification and characterization of putative new sources of resistance/tolerance to biotic and abiotic stresses and their introgression into adapted germplasm | New desirable genes identified and used in broadening genetic base and in enhancement programs | Several new sources of resistance have been identified in wheat and food legumes to either biotic and abiotic stresses Several crosses where performed in wheat and food legumes Progress (%) in implementing the activity: 80% |
| - Screening for abiotic stresses (drought, heat, and cold) | Screening trials established at ICARDA and at NARS research sites | Several trials for abiotic stresses have been established at ICARDA and some NARS research stations Progress (%) in implementing the activity: 70% |
| - Screening for biotic stresses (diseases and insects pests) | Screening trials established at ICARDA and at NARS research sites | Several trials for biotic stresses have been established at ICARDA and some NARS research stations Progress (%) in implementing the activity: 70% |
| - Grain quality analysis | Cultivars with improved nutritional and end-use quality | Analysis where performed for nutritional quality (high level of iron and zinc in lentil) and technological analysis on wheat |
| - Information databases on soil profiles of dry area farming systems and GIS–remote sensing based spatial analysis of crop distribution and yield | Databases, maps, etc | Initiated in spring in 2013 In Tunisia and in Morocco |
| - Modeling tools for determining supplemental irrigation schedules for adaptation of wheat-legumes system to climate change. | Simulation models | Study scheduled for 2013/14 in Jordan |
| - Potential supplemental irrigation and implementation consequences on productivity and sustainability developed for WANA | Recommended supplemental irrigation schedules | Studied in some countries in 2013 |
| - Ex ante assessments of wheat and food legumes research | Benefit-cost estimates of crop improvement research | In progress in Morocco and Egypt |
| - Analyze the economic impacts of major crop diseases | Data base, costs of major crop diseases | In progress in some countries. |

Annex E

Publications

Publications in scientific journals

Abdul Hai, M., M. El Bouhsinni, M. Jamal, B. Parker, M. Skinner and Z. Sayyadi. 2011. Characterization and Laboratory Evaluation of Efficacy of Five Isolates of the Fungus, Paecilomyces farinosus (Holm.) Brown & Smith on Sunn Pest Overwintered Adults Eurygaster integriceps Put. Arab Journal of Plant Protection, 29: 214-218.

Abdulhai, M., G. Mustapha, M. El Bouhssini, M.N. Al Salti and A.N. Trissi. 2012. Some Biological Characteristics of Sunn pest Eurygaster integriceps Puton in Northern Syria. Arab Journal of Plant Protection, 30: 153-156.

Ahmed, S., S. Pigginn, A. Haddad, S. Kumar,Y. Khalil, and B. Geletu 2012.  Nematode and fungal diseases of food legumes under conservation cropping systems in northern Syria. Soil Tillage Res., 121: 68-73.

Atik, O., A. El-Ahmed, M. Baum, S. Ahmed, M.M. Yabrak, A. Al-Assaf and S. Kabbabeh 2012. The Effects of Different BION® Treatments on Ascochyta Blight (Didymella rabiei) of chickpea. Arab Journal of Plant Protection. 30: 101-109.

Atik O., S. Ahmed, M. M. Abang, M. Imtiaz, A. Hamwieh, M. Baum, A. El-Ahmed, S. Murad, and M. M. Yabrak 2013. Pathogenic and genetic diversity of Didymella rabiei affecting chickpea in Syria. Crop Protection 46: 70-79.

Bouajila, A., N. Zoghlami, M. Al Ahmed, M. Baum, A. Ghorbel and K. Nazari 2012. Pathogenicity spectra and screening for resistance in barley against Tunisian Pyrenophora teres f. teres. Plant Dis. 96:1569-1575.

Bouajila, A., N. Zhoglami, S. Murad, M. Baum, A. Ghorbel, and K, Nazari 2013. Genetic differentiation in Pyrenophora teres f. teres populations from Syria and Tunisia as assessed by AFLP markers. Letters in Applied Microbiology. Lett Appl Microbiol. 2012 Dec 1. doi: 10.1111/lam.12029. [Epub ahead of print].

Bousba R., Baum M., Djekoune A., Lababidi S., Jighly A., Benbelkacem K., Labhilili. M, Gaboun F and Ykhlef N 2012. Screening for Drought Tolerance Using Molecular Markers and Phenotypic Diversity in Durum Wheat Genotypes. World Applied Sciences Journal 16(9):1219-1226.

El Bouhssini, M.,  F. C. Ogbonnaya, H, Ketata, M. M. Mosaad, K. Street, A. Amri, M. Keser, S. Rajaram, A. Morgounov, F. Rihawi, A. Dabus and C. M. Smith. 2011. Progress in host plant resistance in wheat to Russian wheat aphid (Hemiptera: Aphididae) in North Africa and West Asia. Australian Journal of Crop Science 5(9): 1108-1113.

El Bouhssini, M., K. Street, A. Amri, M. Mackay, F. C. Ogbonnaya, A. Omran, O. Abdalla, M. Baum, A. Dabbous, and F. Rihawi. 2011. Sources of resistance in bread wheat to Russian wheat aphid (Diuraphis noxia) in Syria identified using the Focused Identification of Germplasm Strategy (FIGS). Plant Breeding 130: 96-97.

El Bouhssini, M., F. C. Ogbonnaya, M. Chen, S. Lhaloui, F. Rihawi, A. Dabbous. 2012. Sources of Resistance in Primary Synthetic Hexaploid Wheat (Triticum aestivum L.) to Insect Pests – Hessian fly, Russian wheat aphid and Sunn pest in the Fertile Crescent. Genetic Resources and Crop Evolution, DOI 10.1007/s10722-012-9861-3.

Elhaddoury J, Lhalouia S, Udupa SM, Moatassima B, Taiqa R, Rabeha M, Kamlaouia M, Hammadia M. 2012 Registration of ‘Kharoba’: A bread wheat cultivar developed through doubled haploid breeding. Journal of Plant Registrations, 6: 169–173. (https://www.crops.org/publications/jpr/pdfs/6/2/169) Open Access

Hussien, N. H., B. Bayaa, S. Ahmed, M. Baum and M. M. Yabraq. 2012. Distribution and factors affecting lentil wilt epidemics in Syria. Arab Journal of Plant Protection (Accepted for 2013 issue)

Idrissi O., Sakr B., Dahan R., Houasli C., Nsarellah N., Udupa S.M., Sarkar A. (2012) Registration of ‘Chakkouf’ Lentil in Morocco. Journal of Plant Registrations, 6:268–272. (https://www.crops.org/publications/jpr/articles/6/3/268) Open Access

Imtiaz M., Abang M.M., Malhotra R.S., Ahmed S., Bayaa B., Udupa S.M., Baum M. (2011) Pathotype IV, a New and Highly Virulent Pathotype of Didymella rabiei, Causing Ascochyta Blight in Chickpea in Syria. Plant Disease 95: 1192.

Katerji N., M. Mastrorilli, F.Z. Lahmer, F. Maalouf, T. Oweis (2011) Faba bean productivity in saline–drought conditions. European Journal of Agronomy 35: 2–12.

Kumar J., Basu P.S., Srivastava E., Chaturvedi S.K., Nadarajan N. and Kumar S. 2012. Phenotyping of traits imparting drought tolerance in lentil. Crop & Pasture Science 63:547-554. Published Online Sept2012 http://dx.doi.org/10.1071/CP12168

Kumar S, Kumar J, Singh RG, Sarker A, and Baum M. 2011. Lentils for Dryland Agriculture: Present Status and Future Strategy. International J Fauna and Flora 17(1):100-107.

Maalouf M., S. Khalil; K. Ahmed Seid; A. N. Akintunde; M. Kharrat ; S. Hajjar; K. El Shama'a (2011) Yield stability of faba bean lines under diverse broomrape prone production environments. Field Crop Research, 124:288-294.

Sahile S, M.M. Abang, C. Fininsa, Seid Ahmed, P.K. Sakhuja & M. Baum 2012. Pathogenic and genetic diversity of Botrytis fabae Sard. isolates from faba bean fields in different agro-ecological zones of Northern Ethiopia, Archives Of Phytopathology and Plant Protection, DOI:10.1 bbnngtg80/03235408.2012.664710

Singh M., van Ginkel M., Sarker A., Malhotra R.S., Imtiaz M. and Kumar S. 2012. Increasing precision of even otherwise well-run trials by capturing heterogeneity of plot error variances. Agricultural Research. DOI 10.1007/s40003-012-0024-8Tadesse W, M. Inagaki, S. Tawkaz, M. Baum and M. van Ginkel (2012). Recent advances and application of doubled haploids in wheat breeding. African Journal of Biotechnology Vol.11 (xxx), pp. XXX-XXX, xxx 2012. DOI:10.5897/AJB12.843

Trissi, A., M. El Bouhssini, M. N.  Al Salti, M. Abdulhai, M. Skinner and B. L. Parker.  2012. Virulence of Beauveria bassiana against Sunn pest, Eurygaster integriceps Puton (Hemiptera: Scutelleridae) at different time periods of application. Journal of Entomology and Nematology 4(5): 49-53.

Zarkti H., Ouabbou H., Udupa S.M., Gaboun F., Hilali A. (2012). Agro-morphological variability in durum wheat landraces of Morocco. Australian Journal of Crop Science, 6:1172-1178.

Book chapter

Gupta S, Kumar S, Singh BB, and Gupta DS. 2012. Urdbean. pp. 237-254. In: Breeding Field Crops (D.N. Bharadwaj Ed.), Agrobios, New Delhi, India.

Publications in proceedings of congress or workshops

Benjelloun I., Thami Alami I., El Khadir M., Udupa S.M., Douira A. (2012). Phenotypic diversity of rhizobia nodulating chickpea in Morocco. In: Proceeding of the second edition of the international congress ‘Microbial Biotechnology for Development’ (MICROBIOD 2), from 2-4 October, 2012, held at Marrakech, Morocco. pp. 59

El-Haddoury J, Udupa SM, Abbad-Andaloussi F, Ramdani A (2011) Des outils de la biotechnologie pour une nouvelle stratégie en amélioration génétique des blés. Abstract of oral presentation, Troisième Edition du Congrès International Amélioration de la Production Agricole (APA3), 17-18 March 2011, Settat, Morocco, pp. 84 -85.Gaur, P.M., S.K. Chaturvedi, Shiv Kumar, P.S. Basu, H. Nayyar4, A. Babbar5, V. Jayalakshmi6, S. Srinivasan1, N. Mallikarjuna1, L. Krishnamurthy1 and C.L.L Gowda1 2013. High temperature tolerance in food legumes to mitigate impact of climate change". National conference on “Crop Improvement and Adaptive Strategies to Meet Challenges of Climate Change” at UAS, Bangalore during 22-24 February, 2013.

Henkrar F., Elhaddoury J., Bendaou N., Udupa S.M. (2012) Integration of molecular markers and doubled haploid techniques for genetic improvement of wheat for rust resistance. In: Proceeding of the second edition of the international congress ‘Microbial Biotechnology for Development’ (MICROBIOD 2), from 2-4 October, 2012, held at Marrakech, Morocco. pp.135

Houasli C., Elbouhmadi K., Nsarellah N., Imtiaz M., Udupa S.M., Said M. (2012) Physiological and biochemical responses of nine chickpea genotypes (Cicer arietinum) to water deficit under greenhouse conditions. In: Proceeding of the second edition of the international congress ‘Microbial Biotechnology for Development’ (MICROBIOD 2), from 2-4 October, 2012, held at Marrakech, Morocco. pp.136

Krimi Bencheqroun S., Hamwieh A., Imtiaz M., Kemal S.A., Lhaloui S., Boutfirass M., Udupa S.M. (2012) Potential of sexual reproduction in Ascochyta rabiei of chickpea in Morocco based on distribution of mating types alleles. In: Proceeding of the second edition of the international congress ‘Microbial Biotechnology for Development’ (MICROBIOD 2), from 2-4 October, 2012, held at Marrakech, Morocco. pp.138

Krimi Bencheqroun S., Ouabbou H., Fatemi Z., Udupa S.M. (2012) Screening of Moroccan faba bean landraces for resistance to Botrytis fabae. In: Proceeding of the second edition of the international congress ‘Microbial Biotechnology for Development’ (MICROBIOD 2), from 2-4 October, 2012, held at Marrakech, Morocco. pp.138

Kumar S, Maalouf M, Hamwieh A, Imtiaz M, and Sarker A. 2013. Breeding food legumes for enhanced drought tolerance to revive its cultivation in Mediterranean region. International Conference on Sustainable Water Use for Securing Food Production in the Mediterranean Region under Climate Change. 10-15 March 2013, Agadir, Morocco. P 5.

Kumar S, Sarker A, Bejiga G, Nangia V, Singh M and Qadir M. 2013. Performance of lentil genotypes under rainfed conditions and their response to supplemental irrigation. International Conference on Sustainable Water Use for Securing Food Production in the Mediterranean Region under Climate Change. 10-15 March 2013, Agadir, Morocco. P 7.

Lanouari S, El-Haddoury J, Bencharki B, Udupa S (2011) Etude de l’effet traitement foliaire par l’acide 2,4-dichlorophenoxyacetique sur l’aptitude à l’androgenèse in vitro chez le blé tendre (Triticum aestivum). Abstract of poster presentation, Troisième Edition du Congrès International Amélioration de la Production Agricole (APA3), 17-18 March 2011, Settat, Morocco, pp.193.

Lanouari S, El-Haddoury J, Udupa S, Bencharki B, Nasser B. (2011) Application de la sélection assistée par marqueurs moléculaires dans l’amélioration génétique de blé tendre. Abstract of poster presentation, Troisième Edition du Congrès International Amélioration de la Production Agricole (APA3), 17-18 March 2011, Settat, Morocco, pp.194.

Maalouf M, Kumar S, Imtiaz M, Kemal S, Kharrat M and El Abidine Fatemi Z. 2012. North Africa-ICARDA Partnership on Food Legumes Research for Development: Present Status and Future Strategy. 3rd International Ascochyta blight Workshop, 21-25 April 2012, Cordoba, Spain. P 77.

Nsarellah N, Udupa S, Amamou A, Ramchoun M, Nachit M (2011) Phenotypic associations between durum wheat plant traits under field irrigation, salt and drought. Abstract of poster presentation, Troisième Edition du Congrès International Amélioration de la Production Agricole (APA3), 17-18 March 2011, Settat, Morocco, pp.148

Nsarellah N, Amamou A, Karimi H, Udupa S, (2011) Contribution à l’étude de l’effet du stress hydrique sur la relation entre le rendement grain et ses composantes chez des accessions Méditerranéennes de blé dur. Abstract of poster presentation, Troisième Edition du Congrès International Amélioration de la Production Agricole (APA3), 17-18 March 2011, Settat, Morocco, pp.150.

Nigusie Girma, Kumar S, Ahmed S, Million E, Asnake F, Tsigereda W and Bejiga G. 2012. Resistance sources for Ascochyta blight resistance in lentil germplasm. 3rd International Ascochyta blight Workshop, 21-25 April 2012, Cordoba, Spain.

Singh S, Kumar S, Gill RK, Kaur L, Ahmed S, Kumar J and Sarker A. 2012. Combining Ascochyta blight resistance and high yield in lentil cultivars. 3rd International Ascochyta blight Workshop, 21-25 April 2012, Cordoba, Spain. P 42.

Tinak Ekom D.C., Udupa S.M., Benchekroun M.N., Ennaji M.M., Iraqi D. (2012) Genetic transformation of Moroccan bread wheat by biolistic using plasmid pBY520 containing barley HVA1 gene. In: Proceeding of the second edition of the international congress ‘Microbial Biotechnology for Development’ (MICROBIOD 2), from 2-4 October, 2012, held at Marrakech, Morocco. pp.153

Udupa S.M., Elhaddoury J., Krimi Bencheqroun S., Thami-Alami I., Henkrar F., Baresel J.P., Finckh M.R. (2012) Optimizing Subsidiary Crop Applications in Rotations (OSCAR): A Perspective for the North Africa Region. In: Proceeding of the second edition of the international congress ‘Microbial Biotechnology for Development’ (MICROBIOD 2), from 2-4 October, 2012, held at Marrakech, Morocco. pp.154

Zarkti H, Henkrar F, Ouabbou H, Hillali A, Udupa SM (2011) Genetic diversity at trait linked DNA marker loci in Moroccan durum wheat varieties. Abstract of oral presentation, Troisième Edition du Congrès International Amélioration de la Production Agricole (APA3), 17-18 March 2011, Settat, Morocco, pp.90.

Zarkti H, Ouabbou H, Hillali A, Udupa SM (2011) Keeping diversity alive: An analysis of microsatellite diversity in Moroccan durum wheat landraces and varieties. Abstract of poster presentation, Troisième Edition du Congrès International Amélioration de la Production Agricole (APA3), 17-18 March 2011, Settat, Morocco, pp.162.

Extension brochure

Integrated Sunn pest Management: Approaches for reducing the threat of Sunn pest to wheat harvests (Borchure in English and Arabic), ICARDA, 2012.

Annex G

Media Coverage

03/07/2013 - 16:30

# نجاح تجربة الحقل الإرشادي لزراعة الفول البلدي بالشرقية

نجاح تجربة الحقل الإرشادي لزراعة الفول البلدي بالشرقية

أشاد محافظ الشرقية المستشار حسن النجار بنجاح تجربة الحقل الإرشادي لزراعة الفول البلدي، التي تنفذ لأول مرة بالشرقية حيث بلغت نسبة المساحة المنزرعة 10 أفدنة ومن المتوقع زيادة إنتاجية الفدان الواحد من 8 أردب إلى 12 أو 15 أردب، حيث جاء ذلك خلال الاحتفال بيوم الحقل الإرشادي لمحصول الفول البلدي التابع لمشروع تعزيز الأمن الغذائي للدول العربية وذلك بقرية الغار التابعة لمركز الزقازيق بحضور الدكتور فوزي كراجة مدير مكتب إليكاردا بالقاهرة، وقال الدكتور فوزى كراجة إن الهدف من الحقل الإرشادي لمحصول الفول البلدي زيادة دخل المزارع وزيادة إنتاجية الفدان لتحقيق الاكتفاء الذاتي من المحصول الغذائي الشعبي لكافة المواطنين.

وأضاف كراجة أنه كان هناك اكتفاء ذاتى من محصول الفول البلدي حتى عام 2007 حيث كانت تتم زراعة 322 ألف فدان لإنتاج 405 ألف طن بمتوسط إنتاج الفدان 8.2 أردب للفدان، كان يمثل اكتفاءا ذاتيا بنسبة 100%، ثم بدأت تتناقص المساحة المنزرعة تدريجيا لتتم زراعة 98 ألف فدان لإنتاج 139 ألف طن بمتوسط إنتاج الفدان 9.2 أردب للفدان وبرغم ارتفاع متوسط إنتاجية الفدان إلا أنه لم تحقق اكتفاء ذاتي وبدأ الاستيراد من الخارج بنسبة 70% وأوضح المهندس محيي الدين عوض الله وكيل وزارة الزراعة أن المشاكل التي تواجه الفلاحين في زراعة الفول البلدي تتمثل في فيروسي 92 وحشيشة الهالوك التي تسبب خسائر عالية للمحصول فضلا عن الأمراض الورقية التي تصيب المحصول، لافتا إلى أن تجربة الحقل الإرشادي من شأنها التقليل من نسبة هذه المخاطر بالإضافة لتوفير ثلث كمية المياه المستخدمة، وبالتالي تقليل التكلفة وزيادة كمية الإنتاج.

الجدير بالذكر أن مساحة محافظة الشرقية 4911 كم بمساحة 1072470 فدان، وإجمالى المساحة المنزرعة 854673 فدان

في يوم الاحتفال بيوم الفول البلدي بالشرقية "ابتكار أصناف مقاومة للأمراض وتضاعف الإنتاج-

07 مارس2013

0  0  0

كتب - وائل عبد الغني وأحمد فوزي

قال المستشار حسن النجار محافظ الشرقية أن مصر هي النمر الاقتصادي القادم بشهادة وتأكيد دول العالم المتقدم بما تمتلكه من مقومات مختلفة تؤهلها لإحداث طفرة في نموها الاقتصادي بعد استكمال الدولة لمؤسساتها الدستورية ، حيث ستشهد البلاد قريبا انتخابات مجلس النواب.

جاء هذا خلال مؤتمر مركز البحوث الزراعية في الأراضي الجافة والصحراوية "ايكارد" الذي تواكب مع الاحتفال بيوم الفول البلدي ، وبحضور ممثلين من عدة دول عربية وأوربية.

وبحضور الدكتور مظهر فوزي الملقب بأبو الفول البلدي في مصر ، وعدد من أساتذة وباحثين مركز البحوث الزراعية ومعهد بحوث الأمراض النباتية.

وأشار الدكتور عبد الغني الفرماوي أستاذ المحاصيل البقولية بمعهد البحوث الزراعية إلي أن الهدف من الاحتفال بيوم الفول بمحافظة الشرقية هو توصيل أهمية التعامل مع التكنولوجيا الجديدة والخاصة بالأصناف المبتكرة والتي تتحمل الإصابة بأخطر أمراض الفول "الهالوك" عن طريق تعريف المزارع بمحتوي التوصيات من حيث موعد الزراعة والتسميد ومقاومة الحشائش ومعاملات المحصول خلال موسم الزراعة بحيث نضمن الحصول علي اعلي إنتاج محصول واعلي إنتاج بروتين وتحقيق جودة عالية للمنتج من حيث الطهي وامتصاصا المياه فضلا عن المساهمة في الحد من الاستيراد لتحقيق الاكتفاء الذاتي من الفول مسمار البطن للمواطن المصري.

وأكد الدكتور محمود عبد المحسن رئيس قسم البقوليات بمركز البحوث الزراعية أن إنتاجية الفدان بالنسبة للأصناف المبتكرة مثل 843 المقاوم للهالوك ومصر 1 ، ومصر3 أضعاف إنتاجية الأصناف العادية حيث ينتج الفدان ما يقرب من 12 إلي 15 اردب ، في حين أن الأصناف العادية تنتج ما يقرب من 6 غلي 8 اردب ، كما أن الأصناف المبتكرة تزرع باحتياجات مائية قليلة .

وأضاف د.عزام عبد الرازق الأستاذ بمركز البحوث الزراعية قسم البقوليات أن أصناف حيزه 716 وجيزة 3 وسخا 1 وسخا 4 وسخا 2 وسخا 3 أصناف مقاومة للأمراض الورقية فضلا عن نوبارية1 الذي ينصح بزراعته في الأراضي المستصلحة حديثا مثل النوبارية والصالحية ويبين الدكتور إيهاب سرحان الباحث في قسم بحوث أمراض البقوليات أن أهم عوامل انخفاض إنتاجية الفول في مصر في الآونة الأخيرة وضعف العائد الاقتصادي للمحصول ودخوله في المنافسة مع المحاصيل الشتوية التي تحقق عائد اقتصادي اعلي ، بعد أن كنا نزرع 310 ألف فدان في عام 2001 ، بما يحقق الاكتفاء الذاتي تراجعت المساحة المزروعة علي 111 ألف فدان ، المر الذي لا يحقق سوي 30 إلي 35 % من احتياجاتنا المحلية كما أن انتشار الهالوك في الأراضي والذي ستمر في الأرض المصابة من 20 غلي 30 سنة ساهم في هذا بشكل كبير.

وذكر أن معهد الأمراض الزراعية قام بتربية سلالات من الفول مقاومة لحشائش الهالوك فضلا عن مقاومتها لمراض الصدئ والبقع البنية والأمراض الفطرية وبما يحقق إنتاجية وفيرة للمزارع التي تنتشر في الدلتا بسبب انخفاض درجات الحرارة وارتفاع الرطوبة ووجود الأمطار ، كما أن هذه الأصناف المقاومة لا يتم استخدام المبيدات الزراعية أثناء زراعتها غلا في أضيق الحدود.

وأوصت الادارة المركزية للإرشاد الزراعي بضرورة مراعاة الصرف الجيد من مصدر موثوق منه ومراعاة التاريخ الزراعي المناسب حيث يفضل أن يكون من منتصف شهر 10 إلي منتصف شهر 11 ، وان تكون الرية الأولي بعد ريه الزراعة من 30 الي 35 يوم وان يكون الري حسب نزول الأمطار كما أن التزام المزارع بالتوصيات الخاصة بطرق المقاومة للأمراض والحشائش يساهم بشكل كبير في تحقيق أعلي إنتاجية للمزارع.

|  | # الأخبار صحيفة روزاليوسف. ## وفد عربى ـ أوروبى يتفقد تجربة زراعة الفول البلدى بالشرقية; #### 309 مشاهدة. 7 مارس 2013; Share on linkedin Share on facebook Share on twitter Share on email More Sharing Services 0. الشرقية - عماد المعاملي.. قام وفد من 9 دول أوروبية وعربية بزيارة لمحافظة الشرقية، لتفقد تجربة زراعة الأصناف الجديدة لتقاوى الفول البلدى على المصاطب، التى يتم تنفيذها لأول مرة فى 10 حقول إرشادية بمختلف مراكز المحافظة. ورافق الوفد فى زيارته للحقل الإرشادى الكائن بقرية «الغار» مركز الزقازيق، المحافظ المستشار «حسن النجار» والمهندس «محيى الدين عوض الله» وكيل وزارة الزراعة وعدد من أساتذة مركز البحوث الزراعية وأعضاء منظمتى «إيكاردا» و «إيفاد» الدوليتين. وصرح المهندس «علاء عفيفى» مدير عام الإرشاد الزراعى بالشرقية بأنه تمت زراعة 3 أصناف جديدة بنظام المصاطب وهى جيزة 843 ومصر 1 و جيزة 3، وتتميز هذه الطريقة بتوفير 50% من التقاوى و30% من استهلاك المياه، كما أنها مقاومة للحشائش التى تدمر 25% من المحصول و للأمراض، وتتميز بالإنتاجية العالية التى تصل إلى 15 أردبا للفدان. وأضاف عفيفى إنه تمت زراعة هذه الأصناف فى مساحة 10 أفدنة فى الحقول الإرشادية هذا العام وسوف تزداد إلى 30 فدانا فى العام المقبل، مشيرا إلى أن تعميم زراعتها سوف يساهم فى تحقيق الاكتفاء الذاتى من محصول الفول البلدى الذى يتم استيراد 70% من احتياجاتنا المحلية منه من الخارج... |
| --- | --- |

جريدة الوفد رئيس مجلس الإدارة: 
د/السيد البدوى شحاتة

أسسها عادل القاضي - عادل صبري

دخـول عضو عضو جديد روابط الوفد بحث بالوفد ضبط الموقع

## الاحتفال بيوم الحقل بمحصول الفول البلدى بالشرقية

الشرقية – ياسر مطري

الخميس , 07 مارس 2013 15:07

أقام مركز البحوث الزراعية بالتعاون مع منظمة الإيكاردا والاتحاد الاوروبي، حفلا بإنتاجية الحقل الاسترشادي لمحصول الفول البلدي بقرية الغار التابعة لمدينة الزقازيق محافظة الشرقية.

حضر الحفل المستشار حسن النجار محافظ الشرقية، والمهندس محيى الدين عوض الله وكيل وزارة الزراعة بالشرقية، والدكتور كامل شديد مساعد المدير العام والتعاون الدولي والاتصالات بمظمة الايكاردا، والدكتور أمين بيلهاميسى ممثل الإيفاد ، والعديد من الأساتذة بمركز البحوث الزراعية.
ويأتي ذلك ضمن بدء مشروع الحقول الارشادية المطبق في 8 دول عربية  هما" مصر، الجزائر، المغرب، تونس، السودان، الأردن، لبنان، تركيا" ودولتين اوربيتين هم "ايطاليا، المانيا"، لنشر زراعة الفول البلدى فى خمس مناطق"الشرقية، النوبارية، الدقهلية، كفر الشيخ، اسيوط".
وتم تكريم صاحب الحقل الاسترشادي "عمرو محمد محمد احمد" ولقب بالمزارع المثالي لمحصول الفول البلدي علي مستوي الجمهورية، الذي اكد انه قام بزراعة  الصنف الجديد من الفول البلدي والمعروف بـــ "جيزة 843" المقاوم لحشائش الهالوك "نبات زهري متطفل يؤدي الي هلاك النبات وموته مبكرة قبل نضجه"، واوضح ان زراعة الصنف الجديد يساعد علي زيادة الانتاجية من 9 الي  15 اردبا للفدان الواحد، وتوفير في استحدام الميبدات، فضلا عن توفيرة 30% من المياه وهي من اهم المميزات خاصة في ظل ما تعانيه مصر من تناقص حصتها تناقص من المياه.
واوضح المهندس "محيى الدين عوض الله" وكيل وزارة الزراعة، ان الاهتمام الحالي بنشر زراعة الأصناف الجديدة من الفول البلدىالمقاومة للهلوك، وذلك من خلال عمل حقول إرشادية لنشر زراعة الفول البلدى فى خمس مناطق "الشرقية، النوبارية، الدقهلية، كفر الشيخ، أسيوط"، مشيرا إلى أن هذه الزراعات تعتمد عمل دورات تدريبية للمزارعين، وفتح حوار مشتركي معهم لمعرفة المشاكل التي تتعرض لهم زراعتهم، وتعليمهم كيفية التغلب عليها عن طريق نقل الخبرات والمهارات الجديدة والتكنولوجيا الزراعية الحديثة .

اقرأ المقال الأصلي علي بوابة الوفد الاليكترونية الوفد - الاحتفال بيوم الحقل بمحصول الفول البلدى بالشرقية

محافظات > أخبار وتقارير >

محافظ الشرقية في "يوم الفول البلدي": بشهادة دول العالم مصر النمر الاقتصادي القادم

الشرقية – عادل الشاعر

8-3-2013 | 17:13

محافظ الشرقية يتفقد مزارع الفول

قال المستشار حسن النجار، محافظ الشرقية، إن مصر النمر الاقتصادي المقبل بشهادة وتأكيد دول العالم المتقدمة، بما تمتلكه من مقومات مختلفة تؤهلها لإحداث طفرة بنموها الاقتصادي، بعد استكمال الدولة لمؤسساتها الدستورية، حيث ستشهد البلاد قريبًا انتخابات مجلس النواب. 

جاء ذلك خلال مؤتمر مركز البحوث الزراعية في الأراضي الجافة والصحراوية "إيكارد" الذي تواكب مع الاحتفال بيوم الفول البلدي، وبحضور ممثلين من عدة دول عربية وأوربية. 

وأكد الدكتور محمود عبد المحسن رئيس قسم البقوليات بمركز البحوث الزراعية، أن إنتاجية الفدان بالنسبة للأصناف المبتكرة مثل 843 المقاوم للهالوك بمصر ثلاثة أضعاف إنتاجية الأصناف العادية، حيث ينتج الفدان ما يقرب من 12 إلي 15 إردبا، في حين أن الأصناف العادية تنتج ما يقرب من 6 إلي 8 أرادب، كما أن الأصناف المبتكرة تزرع باحتياجات مائية قليلة. 

وأوضح الدكتور إيهاب سرحان الباحث في قسم بحوث أمراض البقوليات، أن أهم عوامل انخفاض انتاجية الفول بمصر في الآونة الأخيرة ترجع لضعف العائد الاقتصادي للمحصول ودخوله في المنافسة مع المحاصيل الشتوية التي تحقق عائدا اقتصاديا أعلى. 

وتابع: بعد أن كنا نزرع 310 ألف فدان في عام 2001، بما يحقق الاكتفاء الذاتي تراجعت المساحة المزروعة إلى 111 ألف فدان، الأمر الذي لا يحقق سوى 30 إلي 35% من احتياجاتنا المحلية، يضاف إلى ذلك انتشار الـ"هالوك"، حيث يعيش مختبئ في الأرض المصابة من 20 إلي 30 سنة. 

وأوصت الإدارة المركزية للإرشاد الزراعي، بضرورة مراعاة الصرف الجيد من مصدر موثوق منه ومراعاة التاريخ الزراعي المناسب، حيث يفضل أن يكون من منتصف شهر أكتوبر إلى منتصف شهر نوفمبر، وأن تكون الرية الأولى بعد رية الزراعة من 30 إلي 35 يوما وأن يكون الري حسب نزول الأمطار، كما أن التزام المزارع بالتوصيات الخاصة بطرق المقاومة للأمراض والحشائش يساهم بشكل كبير في تحقيق أعلي إنتاجية للمزارع.

# "يوم الحقل" بالزقازيق وبدء مشروع في 5 محافظات لزيادة إنتاجية الفول البلدي

بوابة الأهرام – الأربعاء، 6 مارس 2013

### محتويات ذات صلة

- عرض صورة

"يوم الحقل" بالزقازيق وبدء مشروع في 5 محافظات لزيادة إنتاجية الفول البلدي

قام مركز البحوث الزراعية وخبراء من الاتحاد الأوربى والإيفاد، ومنظمة الإيكاردا بتنظيم يوم الحقل بمدينة الزقازيق في محافظة الشرقية، وذلك ضمن بدء مشروع الحقول الارشادية لنشر زراعة الفول البلدى فى خمس محافظات، هى: كفر الشيخ، النوبارية، الدقهلية، الشرقية، وأسيوط.

ويأتى يوم الحقل فى إطار الاهتمام بنشر زراعة الأصناف الجديدة من الفول البلدى، وهي من إنتاج مركز البحوث الزراعية (نوبارية 2، نوبارية 3)، وهما صنفان يحتاجان لمياه قليلة وأهميتهما فى ظل تناقص المياه، بالإضافة إلى (سخا 4)، وهو صنف مقاوم لأمراض المجموع الخضري، والصنفين (مصر 3 وجيزة 843)، وهما صنفان مقاومان للهالوك (نبات زهري متطفل يسبب خسائر شديدة للفول البلدي في مصر ومحاصيل أخري) من خلال عمل حقول إرشادية لنشر زراعة الفول البلدى فى خمس محافظات هى: كفر الشيخ، النوبارية، الدقهلية، الشرقية، وأسيوط حيث تعتمد هذه الزراعات على التعاقب المحصولى بين القمح والبقوليات.

حضر يوم الحقل المستشار حسن النجار محافظ الشرقية ، وممثل الإيفاد الدكتور أمين بيلهاميسى، ومنسق المشروع الدكتور محمد خراط ، والدكتور كامل شديد مساعد المدير العام والتعاون الدولي والاتصالات إيكاردا، وممثل منظمة الإيكاردا الدكتور مايكل بوم مدير التنوع الحيوى وبرنامج الإدارة المتكاملة، والدكتور فوزى كراجه, من مكتب الإيكاردا بالقاهرة، و الدكتورة رحاب عبد الرحمان من مركز البحوث الزراعية والدكتور إيهاب سرحان من معهد بحوث أمراض النباتات، والعديد من الأساتذة بمركز البحوث الزراعية.

وتم التأكيد خلال يوم الحقل على القدرة على التطوير المشروع، من خلال الحوار مع المزارعين ومناقشتهم فيما يتعرضوا له من مشاكل، وكيفية تغلبهم عليها، وكذلك نقل التكنولوجيا من خلال الدورات التدريبية وأيام الحقل والمدارس الحقلية، التى تهدف إلى تعريف المزارعين بحزمة التوصيات الفنية الخاصة بتلك الأصناف، والتى تؤدى إلى زيادة الإنتاجية وزيادة الإنتاج.

ويشمل هذا المشروع العديد من الدول هى: مصر، الجزائر، المغرب، تونس، السودان، الأردن، لبنان وتركيا.

# . الشرقية تحتفل بنجاح زراعة الفول البلدى بالحقل الإرشادى

كتب في: مارس 07, 2013 | تعليقات : 0

أعرب المستشار حسن النجار محافظ الشرقية عن فرحته بنجاح تجربة الحقل الإرشادى لزراعة الفول البلدى التى تنفذ لأول مرة بالمحافظة، حيث بلغت نسبة المساحة المنزرعة 10 أفدنه ومن المتوقع زيادة إنتاجية الفدان الواحد من 8 أردبات إلى 12 أو 15 أردبا.

جاء ذلك خلال الاحتفال بيوم الحقل الإرشادى لمحصول الفول البلدى التابع لمشروع تعزيز الأمن الغذائى للدول العربية، وذلك بقرية الغار التابعة لمركز الزقازيق بحضور الدكتور فوزى كراجة مدير مكتب (اليكاردا بالقاهرة).

وقال الدكتور فوزى كراجة إن الهدف من الحقل الإرشادى لمحصول الفول البلدى زيادة دخل المزارع وزيادة إنتاجية الفدان لتحقيق الاكتفاء الذاتى من المحصول الغذائى الشعبى لكافة المواطنين.

وأضاف كراجة أنه كان هناك اكتفاء ذاتيا من محصول الفول البلدى حتى عام 2007، حيث كانت تتم زراعة 322 ألف فدان لإنتاج 405 ألف طن بمتوسط إنتاج 8.2 أردب للفدان، وكان يمثل اكتفاء ذاتيا بنسبة 100% ثم بدأت تتناقص المساحة المنزرعة تدريجيا لتتم زراعة 98 ألف فدان لإنتاج 139 ألف طن بمتوسط إنتاج الفدان 9.2 أردب للفدان، وبرغم ارتفاع متوسط إنتاجية الفدان إلا أنه لم يحقق اكتفاء ذاتيا وبدأ الاستيراد من الخارج بنسبة 70%.

وأوضح المهندس محى الدين عوض الله وكيل وزارة الزراعة أن المشاكل التى تواجه الفلاحين فى زراعة الفول البلدى تتمثل فى فيروسى 92 وحشيشة الهالوك، التى تسبب خسائر عالية للمحصول، فضلا عن الأمراض الورقية التى تصيب المحصول، لافتا إلى أن تجربة الحقل الإرشادى من شأنها التقليل من نسبة هذه المخاطر، بالإضافة لتوفير ثلث كمية المياه المستخدمة وبالتالى تقليل التكلفة وزيادة كمية الإنتاج.

الجدير بالذكر أن مساحة محافظة الشرقية 4911 كم بمساحة 1072470 فدانا وإجمالى المساحة المنزرعة 854673 فدانا.

2013-03-16 السبت

# وفد عربي أوروبي يتفقد تجربة جديدة لزراعة الفول بالشرقية

2013- م 05:16:56 الثلاثاء 05 - مارس

صورة أرشيفية

الشرقية - سناء عنان قام اليوم وفد من 9 دول أوروبية وعربية بزيارة لمحافظة الشرقية ، لتفقد تجربة زراعة الأصناف الجديدة لتقاوي الفول البلدي على المصاطب . يتم تنفيذ هذه التجربة لأول مرة في 10 حقول إرشادية بمختلف مراكز المحافظة . وقد رافق الوفد في زيارته للحقل الإرشادي الكائن بقرية "الغار" مركز الزقازيق ، المحافظ المستشار "حسن النجار" والمهندس "محيى الدين عوض الله" وكيل وزارة الزراعة و عدد من أساتذة مركز البحوث الزراعية و أعضاء منظمتي "إيكاردا" و "إيفاد" الدوليتين . وصرح المهندس "علاء عفيفي" مدير عام الإرشاد الزراعي بالشرقية ، أنه تم زراعة 3 أصناف جديدة بنظام المصاطب وهى جيزة 843 و مصر 1 و جيزة 3 ، وتتميز هذه الطريقة بتوفير 50% من التقاوي و30 % من استهلاك المياه ، كما أنها مقاومة للحشائش التي تدمر 25 % من المحصول و للأمراض ، و تتميز بالإنتاجية العالية التي تصل إلى 15 إردبا للفدان . و أضاف أنه تم زراعة هذه الأصناف في مساحة 10 أفدنة في الحقول الإرشادية هذا العام وسوف تزاد إلى 30 فدانا في العام القادم ، مشيرا إلى أن تعميم زراعتها سوف يساهم في تحقيق الاكتفاء الذاتي من محصول الفول البلدي ، الذي يتم استيراد 70 % من احتياجاتنا المحلية منه من الخارج .